## Work List
Exported on: 2026-10-05 05:09:14
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: KALSI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN / KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718001028/AV/3300 — Anganwadi/Other Rural Infrastructure,KHACHAROD | Completed | 195000 | 194796 | 2015-08-17 | 2017-10-31
UJJAIN / KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1718001028/AV/4004 — Anganwadi/Other Rural Infrastructure,KALSI | Completed | 195000 | 143123 | 2015-11-30 | 2017-10-31
UJJAIN / KHACHAROD | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718001028/DP/1/जेटोफा व — जेटोफा व़क्षारोपण कलसी 4.25, 92/18-07-2011 | Completed | 425000 | 42954 | 2011-09-01 | 2013-03-07
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001028/DP/22012034242468 — वृक्षारोपण खेलमैदान कलसी | Completed | 335200 | 107217 | 2017-05-22 | 2024-07-10
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001028/DP/22012034242470 — वृक्षारोपण शांतिधाम कलसी | Completed | 335200 | 124237 | 2017-05-22 | 2024-01-21
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718001028/IF/22012034308163 — jasvant singh nadep | Deleted | 1220000000 | 0 | 2016-12-20
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718001028/IF/22012034308175 — shankar/sukhram bpl nadep | Deleted | 1220000000 | 0 | 2016-06-20
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718001028/IF/22012034308180 — rashal kunwar/narayan singh | Deleted | 1220000000 | 0 | 2016-06-20
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1718001028/IF/22012034308194 — avantabai dayaram nadep | Deleted | 1220000000 | 0 | 2016-06-20
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001028/IF/22012034369807 — पोधा रोपण pmरोड साईट | Completed | 335000 | 3045 | 2017-09-20 | 2019-11-04
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718001028/IF/22012034882351 — sokata gadda sohansingh baousingh kalsi | Closed | 2230.76 | 0 | 2021-08-15
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718001028/IF/22012034882354 — sokata gaddam angusingh raysingh gram kalsi | Closed | 2230.76 | 0 | 2021-08-15
UJJAIN / KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1718001028/IF/22012034882359 — sokata gadda sodan singh pitanarayan singh | Closed | 2230.76 | 0 | 2021-08-15
UJJAIN / KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718001028/IF/22012035232880 — Nala traching kal bherav mandir ke pass | New | 0 | 0 | 2024-04-14
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718001028/IF/22012035290290 — Khet talab premsingh narayansingh kalsi | Approved | 0 | 0 | 2024-12-05
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718001028/IF/22012035305642 — Khet talab premsingh narayansingh kalsi 1 | New | 0 | 0 | 2025-01-24
UJJAIN / KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718001028/IF/22012035307221 — Khet Talab Prem singh narayan singh Kalsi | Approved | 0 | 0 | 2025-01-24
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718001028/IF/22012035462474 — JGSA 2023 Khet Talab Prem singh Narayan singh Kalsi | Closed | 147621.16 | 0 | 2025-05-13
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001028/IF/22012035472756 — JGSA kup recharge pit narendra singh kalsi | Completed | 25899.46 | 15660 | 2025-05-07 | 2026-01-07
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001028/IF/22012035472816 — JGSA kup recharge pit tej kunwar | Completed | 25899.46 | 14355 | 2025-05-07 | 2026-01-07
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001028/IF/22012035472894 — JGSA kup recharge pit govind kunwar | Completed | 25899.46 | 15660 | 2025-05-07 | 2026-01-07
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1718001028/IF/22012035472919 — JGSA kup recharge pit maya kunwar | Completed | 25899.46 | 15138 | 2025-05-07 | 2026-01-07
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718001028/IF/22012035472987 — JGSA kup recharge pit lakhan | Completed | 25899.46 | 14877 | 2025-05-09 | 2026-01-07
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718001028/IF/22012035484922 — JGSA recharge pit rup singh | Completed | 25899.46 | 15138 | 2025-05-09 | 2026-01-07
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1718001028/IF/22012035484975 — JGSA recharge pit darbar singh | Completed | 25899.46 | 14877 | 2025-05-10 | 2026-01-07
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718001028/IF/22012035526444 — KHET TALAB NIRMAN KARY PREMSINGH NARAYAN SINGH JI KALSI | Approved | 0 | 0 | 2025-05-10
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1718001028/IF/22012035528100 — JGSA 2025 KHET TALAB NIRMAN PREM SINGH NARAYAN SINGH | Completed | 147621.16 | 111969 | 2025-05-20 | 2026-02-11
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001028/IF/22012035631470 — Ek Bagiya Maa ke Naam shg ganga bai w/o basanti basanti basanti lal uda kalsi | Ongoing | 263511.37 | 126546 | 2025-11-13
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001028/IF/22012035635643 — Ek Bagiya Maa Ke Naam shg maya bai w/o bharat bhagwan uda kalsi | Closed | 263511.37 | 1827 | 2026-01-05
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001028/IF/22012035646439 — Ek Bagiya Maa Ke Naam shg kala bai w/o ratan lal kalsi | Ongoing | 158975.85 | 68289 | 2025-11-29
UJJAIN / KHACHAROD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001028/IF/2कलसी (अलस — कलसी (अलसी) नवीन कुप निर्माण मांगीलाल लुणा जी | Completed | 180000 | 1225 | 2008-09-15 | 2011-08-30
UJJAIN / KHACHAROD | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001028/IF/2कलसी नवीन — कलसी नवीन कुप निर्माण भारत सिह राम सिह | Completed | 180000 | 10891 | 2008-09-22 | 2011-08-30
UJJAIN / KHACHAROD | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001028/IF/2/मि‍श्रील — मि‍श्रीलालभुवान नवीन कुप मि‍श्रीलालभुवान कलसी | Completed | 216100 | 23504 | 2009-06-01 | 2011-08-30
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001028/IF/9926737366 — मायाकुंवरपति मंगुसिंह | Completed | 299000 | 240014.08 | 2014-06-16 | 2016-06-04
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001028/IF/9926737680 — रूखमणी बाई/नरपत नविन कूप निर्माण | Completed | 299000 | 213096 | 2014-06-16 | 2016-06-04
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001028/IF/9993662945 — Pashu shed Ishwar bheru | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001028/IF/9993662951 — pasu shed tej kunwar | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001028/IF/9993663909 — kup nirman sumer singh | Deleted | 0 | 0 | 2014-10-20
UJJAIN / KHACHAROD | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718001028/IF/9993663910 — kup nirman avanti bai | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/9993680407 — seeta bai bapuji IAY | Completed | 14310 | 14216 | 2015-10-12 | 2016-11-03
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001028/IF/9993717020 — ketal sed mohanlal | Deleted | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718001028/IF/9993717021 — ketal sed mohanlal | Deleted | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1004544 — Construction of IAY House -IAY REG. NO. MP1283394 | Completed | 15480 | 14448 | 2017-09-20 | 2018-03-07
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1045729 — Construction of IAY House -IAY REG. NO. MP3388881 | Completed | 15480 | 13488 | 2017-10-25 | 2018-08-01
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1045959 — Construction of IAY House -IAY REG. NO. MP3408470 | Completed | 15480 | 18636 | 2017-08-29 | 2018-05-14
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1046072 — Construction of IAY House -IAY REG. NO. MP3419061 | Completed | 15480 | 15196 | 2017-08-29 | 2018-07-15
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1409792 — Construction of IAY House -IAY REG. NO. MP1675527 | Completed | 15480 | 14790 | 2018-05-10 | 2019-01-23
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1435985 — Construction of IAY House -IAY REG. NO. MP3296508 | Completed | 15480 | 14616 | 2018-04-04 | 2018-08-17
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1437522 — Construction of IAY House -IAY REG. NO. MP3348081 | Completed | 15480 | 15624 | 2018-04-04 | 2018-11-01
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1437523 — Construction of IAY House -IAY REG. NO. MP3348177 | Completed | 15480 | 14616 | 2018-04-19 | 2019-01-23
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1440078 — Construction of IAY House -IAY REG. NO. MP3437135 | Completed | 15480 | 14616 | 2018-04-04 | 2018-09-04
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1538880 — Construction of IAY House -IAY REG. NO. MP3917149 | Completed | 15480 | 14616 | 2018-04-04 | 2018-08-17
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1697723 — Construction of IAY House -IAY REG. NO. MP2132329 | Completed | 15660 | 15660 | 2018-06-06 | 2018-12-05
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1863360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4471333 | Completed | 15660 | 14640 | 2018-07-02 | 2019-08-16
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1863548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4937795 | Completed | 15660 | 14616 | 2018-07-02 | 2019-03-08
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/1863705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5411654 | Completed | 15660 | 14616 | 2018-07-02 | 2018-12-26
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/245802 — Construction of IAY House -IAY REG. NO. MP1715761 | Completed | 15030 | 14986 | 2017-01-25 | 2018-03-07
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/255217 — Construction of IAY House -IAY REG. NO. MP2119551 | Completed | 15030 | 15360 | 2017-01-25 | 2017-12-17
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/256576 — Construction of IAY House -IAY REG. NO. MP2160008 | Completed | 15030 | 15660 | 2018-02-13 | 2018-10-23
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/256685 — Construction of IAY House -IAY REG. NO. MP2162290 | Completed | 15030 | 14844 | 2017-01-25 | 2018-01-18
UJJAIN / KHACHAROD | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/274797 — Construction of IAY House -IAY REG. NO. MP3226438 | Completed | 15030 | 15188 | 2017-01-25 | 2018-01-18
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/276039 — Construction of IAY House -IAY REG. NO. MP3409279 | Completed | 15030 | 15480 | 2017-05-14 | 2018-01-12
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4314804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116693058 | Completed | 18360 | 17952 | 2022-08-30 | 2023-07-14
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4314805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116693150 | Completed | 18360 | 18955 | 2022-09-13 | 2023-12-07
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4320213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126765533 | Completed | 18360 | 17646 | 2022-09-03 | 2023-07-14
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4320801 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125555644 | Completed | 18360 | 18326 | 2022-08-30 | 2023-10-16
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4324618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141155893 | Completed | 18360 | 18122 | 2022-08-30 | 2023-10-16
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4327857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116693249 | Completed | 18360 | 18343 | 2023-01-31 | 2023-07-14
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4331443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121690624 | Completed | 18360 | 18944 | 2022-10-27 | 2023-12-07
UJJAIN / KHACHAROD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4340039 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117486230 | Completed | 18360 | 18811 | 2022-10-27 | 2023-12-12
UJJAIN / KHACHAROD | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4386944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106917042 | Completed | 18360 | 19067 | 2023-09-28 | 2024-08-09
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4696667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117266347 | Completed | 21870 | 13158 | 2024-10-05 | 2025-03-06
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4699604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118036850 | Completed | 21870 | 11705 | 2024-10-05 | 2025-02-19
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4721438 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143819368 | Completed | 23490 | 21048 | 2024-10-05 | 2026-04-02
UJJAIN / KHACHAROD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/4780773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128158117 | Completed | 23490 | 23238 | 2025-02-28 | 2026-05-06
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5252900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106924833 | Completed | 23490 | 22185 | 2025-07-25 | 2026-02-07
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5278435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106931166 | Completed | 23490 | 22968 | 2025-08-26 | 2026-03-27
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5294664 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126764454 | Completed | 23490 | 21141 | 2025-07-25 | 2026-01-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5302663 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141170492 | Completed | 23490 | 20097 | 2026-01-05 | 2026-02-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5306935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118030440 | Completed | 23490 | 21402 | 2026-01-20 | 2026-04-08
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5337049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113885047 | Completed | 23490 | 21924 | 2025-07-25 | 2026-01-03
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5341148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143818982 | Completed | 23490 | 23348 | 2025-07-24 | 2026-03-10
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5367482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118031608 | Completed | 23490 | 22707 | 2025-08-08 | 2026-01-03
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5424870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128564331 | Completed | 23490 | 21924 | 2025-07-25 | 2026-03-14
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5425809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129628666 | Completed | 23490 | 23229 | 2025-07-25 | 2025-12-28
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5426844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143362334 | Completed | 23490 | 22569 | 2025-08-26 | 2026-02-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5428139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123545517 | Completed | 23490 | 22446 | 2025-07-25 | 2026-01-03
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5429528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128159975 | Completed | 23490 | 23229 | 2025-07-25 | 2025-12-28
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5431812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116306386 | Completed | 23490 | 22185 | 2025-07-25 | 2026-01-09
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5432604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120838006 | Completed | 23490 | 21924 | 2025-07-25 | 2026-01-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5459116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118035167 | Completed | 23490 | 22185 | 2025-07-25 | 2026-01-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5459528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106938677 | Completed | 23490 | 23229 | 2025-07-25 | 2026-03-10
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5461468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129629015 | Completed | 23490 | 21924 | 2025-08-26 | 2026-02-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5461580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124795910 | Completed | 23490 | 21663 | 2025-07-25 | 2026-01-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5462447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106906585 | Completed | 23490 | 22707 | 2025-07-25 | 2026-02-03
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5463741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117476348 | Completed | 23490 | 22185 | 2025-08-08 | 2026-02-03
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5474311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130485562 | Completed | 23490 | 20887 | 2025-08-26 | 2026-04-14
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5476237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116631804 | Completed | 23490 | 21141 | 2025-08-26 | 2026-05-13
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5476424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116306361 | Completed | 23490 | 21924 | 2025-07-25 | 2026-01-09
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5480459 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130484635 | Completed | 23490 | 22707 | 2025-08-26 | 2026-01-03
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5481209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130499950 | Ongoing | 23490 | 12279 | 2025-08-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5481407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130493880 | Completed | 23490 | 22968 | 2025-07-25 | 2026-02-07
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5482180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123863551 | Completed | 23490 | 22707 | 2025-07-25 | 2026-01-03
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5626817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106913498 | Completed | 23490 | 20097 | 2025-08-26 | 2026-04-08
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5710890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121697520 | Completed | 23490 | 21924 | 2025-08-26 | 2026-05-06
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5711214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118033604 | Ongoing | 23490 | 19053 | 2025-09-14
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5711402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116708316 | Ongoing | 23490 | 21402 | 2025-08-26
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5711421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128156061 | Completed | 23490 | 22185 | 2025-08-26 | 2026-03-14
UJJAIN / KHACHAROD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/5871065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116300408 | Completed | 23490 | 23229 | 2026-01-06 | 2026-06-06
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/604359 — Construction of IAY House -IAY REG. NO. MP3763981 | Completed | 15030 | 13416 | 2017-05-14 | 2018-01-11
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6111990 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143820636 | Ongoing | 23490 | 16182 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6112495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141170693 | Completed | 23490 | 23229 | 2026-04-21 | 2026-07-07
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6113304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143998532 | Ongoing | 23490 | 22185 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6114118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106932718 | Ongoing | 23490 | 1827 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6114394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116308895 | Ongoing | 23490 | 20880 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6114491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113885065 | Ongoing | 23490 | 21924 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6114768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128113288 | Completed | 23490 | 22968 | 2026-04-21 | 2026-07-07
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6115146 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130480670 | Ongoing | 23490 | 19575 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6115267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143819550 | Ongoing | 23490 | 0 | 2026-05-14
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6115429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106924944 | Ongoing | 23490 | 14616 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6116436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130478374 | Ongoing | 23490 | 19314 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6117240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118504394 | Ongoing | 23490 | 11745 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6117369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126770933 | Ongoing | 23490 | 12006 | 2026-04-21
UJJAIN / KHACHAROD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/6117538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122088504 | Ongoing | 23490 | 21402 | 2026-04-21
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/694850 — Construction of IAY House -IAY REG. NO. MP1357298 | Completed | 15030 | 15072 | 2017-10-24 | 2018-09-20
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/734906 — Construction of IAY House -IAY REG. NO. MP2104436 | Completed | 15030 | 14034 | 2017-08-22 | 2018-12-28
UJJAIN / KHACHAROD | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/769681 — Construction of IAY House -IAY REG. NO. MP3419348 | Completed | 15030 | 15684 | 2018-04-05 | 2019-06-10
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/770066 — Construction of IAY House -IAY REG. NO. MP3437127 | Completed | 15030 | 15528 | 2017-09-20 | 2018-05-14
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/778713 — Construction of IAY House -IAY REG. NO. MP3917124 | Completed | 15030 | 15480 | 2017-08-22 | 2018-04-02
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/778728 — Construction of IAY House -IAY REG. NO. MP3918019 | Completed | 15030 | 14620 | 2017-08-22 | 2018-03-07
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/781990 — Construction of IAY House -IAY REG. NO. MP1275188 | Completed | 15480 | 14496 | 2017-06-03 | 2018-07-15
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/901884 — Construction of IAY House -IAY REG. NO. MP2162283 | Completed | 15480 | 15404 | 2017-10-24 | 2018-08-01
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/915592 — Construction of IAY House -IAY REG. NO. MP2356406 | Completed | 15480 | 15084 | 2017-08-22 | 2018-08-17
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/957647 — Construction of IAY House -IAY REG. NO. MP3230678 | Completed | 15480 | 14532 | 2017-08-29 | 2018-07-08
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/962267 — Construction of IAY House -IAY REG. NO. MP3348066 | Completed | 15480 | 13980 | 2017-10-24 | 2018-07-16
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/973663 — Construction of IAY House -IAY REG. NO. MP2526903 | Completed | 15480 | 14448 | 2017-10-25 | 2018-04-02
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/973763 — Construction of IAY House -IAY REG. NO. MP3237141 | Completed | 15480 | 15576 | 2017-08-22 | 2018-08-01
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/976158 — Construction of IAY House -IAY REG. NO. MP3730168 | Completed | 15480 | 13512 | 2017-08-22 | 2019-01-16
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/977192 — Construction of IAY House -IAY REG. NO. MP3769696 | Completed | 15480 | 15136 | 2017-08-22 | 2018-01-18
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/977781 — Construction of IAY House -IAY REG. NO. MP3792833 | Completed | 17100 | 18394 | 2017-10-25 | 2023-12-12
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/977815 — Construction of IAY House -IAY REG. NO. MP3793765 | Completed | 15480 | 12960 | 2017-10-25 | 2018-07-16
UJJAIN / KHACHAROD | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718001028/IF/IAY/983376 — Construction of IAY House -IAY REG. NO. MP1360004 | Completed | 15480 | 14448 | 2017-10-25 | 2018-04-02
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718001028/LD/22012034224324 — shanti dham kalsi daksin deesa | Completed | 518000 | 329540.4 | 2016-09-10 | 2018-06-29
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Anganwadi Building / Repair and Maintenance of Anganwadi Building for Community | Repair & Maint of Community infrastructure | 1718001028/LD/22012034248639 — shanti dham kalsi uttar deesa | Completed | 518000 | 45779 | 2017-03-08 | 2018-07-18
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718001028/LD/22012034358459 — शांतिधाम ग्राम अलसी | Completed | 180000 | 1032 | 2017-08-25 | 2018-06-25
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1718001028/PG/9425891383 — khel medan | Completed | 320000 | 201059.54 | 2016-12-17 | 2018-08-10
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034188510 — तीसरी किशत मनरेगा पच कानसिह के मकान से श्री ना | Completed | 83000 | 82785.9 | 2013-10-07 | 2014-03-15
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034188545 — मनरेगा पचपरमेश्‍वर चोथी किशत रमेश सेठ के घर से कैल | Completed | 83000 | 82785.9 | 2013-10-14 | 2014-03-15
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034209893 — पांचवीं किस्त भेरू रूपा के घर से भारत देवा जी के | Completed | 126102 | 116160 | 2014-03-11 | 2015-02-02
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034213379 — आंतरिक मार्ग व् नाली निर्माण | Completed | 630000 | 424335.5 | 2014-05-19 | 2016-06-20
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034214855 — दुसरीकिशत मनरेगा भवरकेमकानसेश्रीहनुानजीमदिरकीऔर कल | Completed | 99800 | 96250 | 2014-08-18 | 2015-06-22
UJJAIN / KHACHAROD | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034218541 — गणेश जी मंदिर से निम्बोदिया कांकड़ की ओर | Deleted | 0 | 0 | 2013-08-19
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034218603 — khetsadak yojana किशोरसिहजी के माकन से काला भेरुजी | Completed | 1462000 | 754034 | 2014-06-09 | 2016-11-27
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034227159 — हरिजन मोहल्ले के पप्पू की दुकान से राधा कृष्ण मंद | Completed | 100000 | 93580 | 2014-08-18 | 2015-06-21
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034264132 — khet sadak | Deleted | 1000000 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034264133 — khet sadak | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034264996 — cement kankrit road | Closed | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034264998 — CC ROAD OR NALI NIRMAN | Completed | 100000 | 97108 | 2016-08-20 | 2016-10-23
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034264999 — nali nirman | Closed | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034265723 — Antrik marg | Deleted | 0 | 0 | 2014-10-02
UJJAIN / KHACHAROD | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034291489 — c.c.road balaji mandir se saligram ke ghar ki or | Completed | 100000 | 99843 | 2015-12-18 | 2016-01-26
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034302427 — keat sadak kalsi | Deleted | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034302428 — Manrega pachparmeasvar | Closed | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034302429 — Manrega pachparmeasvar | Closed | 0 | 0 | 2016-04-01
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034302516 — rugga nathu ke ghar se antar singh ji dudhawat ke ghar tak | Completed | 5150 | 4816 | 2017-09-18 | 2017-12-07
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034302517 — mohan ke ghar se rugga nathu ke ghar tak | Completed | 17063 | 16168 | 2017-09-18 | 2017-12-07
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034330359 — cc road nali nirman | Closed | 49500 | 0 | 2017-01-26
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034335055 — cc road alasi/pappu ke ghar se rakesh ke ghar tak | Completed | 123016 | 61404 | 2017-04-11 | 2018-06-19
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034341026 — चेन सिंह जी के घर से भारत के घर तक | Completed | 49500 | 39216 | 2017-06-09 | 2017-12-07
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034347720 — सीमेंट कंक्रीट रोड (मदन पूना के घर से नाग महाराज मंदिर की और | Completed | 4522500000 | 44376 | 2017-08-02 | 2017-12-07
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034348657 — विलम सिह के घर से मंगू सिह के घर तक | Completed | 79650 | 11352 | 2017-08-09 | 2017-12-07
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034364874 — मनसुख के घर से गोकुलसिंह के घर तक | Completed | 39825 | 39216 | 2017-10-26 | 2018-01-15
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034365628 — बगदीराम के घर से लाल माता मन्दिर तक | Completed | 9735 | 8772 | 2017-10-30 | 2018-01-15
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034373985 — सीसी रोड | Closed | 0 | 0 | 2017-10-02
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034373986 — सीसी रोड | Closed | 0 | 0 | 2017-10-02
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034379937 — c.croad ganesh mandir se devilal ke ghar tak | Completed | 59063 | 58824 | 2018-02-08 | 2018-06-21
UJJAIN / KHACHAROD | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034382710 — cc raod rakesh bapu ke ghar se pm road tak | Completed | 25200 | 25112 | 2018-03-07 | 2018-06-21
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034392236 — datar siha ke ghar se kamal puri ke ghar tk | Completed | 24543 | 24360 | 2018-08-23 | 2018-12-07
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034392239 — ram lal ke ghar se deva ke ghar tk | Completed | 28687 | 28536 | 2018-08-31 | 2018-12-07
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034392241 — Rupsingh ke ghar se pyarsingh ke ghar ki our cc road | Completed | 13800 | 13728 | 2019-08-29 | 2020-02-19
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034392242 — mohan seth ke ghar se bheru lal ke ghar tk | Completed | 5738 | 5568 | 2018-09-20 | 2019-01-04
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034392319 — mangu siha ke ghar se madankunwar ke ghar tk | Completed | 10200 | 10092 | 2018-08-23 | 2018-12-07
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034392821 — cc road parmanand ke ghar se dinesh kumar ke ghar tak | Completed | 9563 | 9396 | 2018-09-20 | 2019-01-03
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034397423 — cc road jagdish kumawat ke ghr se mansukh laal ke ghr tk | Completed | 38587 | 38280 | 2018-12-18 | 2019-03-06
UJJAIN / KHACHAROD | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034397430 — cc road pradhanmantri road se omprakash ke ghr tk | Completed | 27540 | 25992 | 2019-01-29 | 2020-02-17
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034441677 — Cc road or nali niarman | Closed | 0 | 0 | 2019-04-25
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034449614 — bheru lal ke ghar se balu lal ke ghar tk | Completed | 15428 | 15200 | 2020-09-06 | 2026-02-28
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034449621 — Balu lal ke ghar se bagdi ram ke ghar | Completed | 8694 | 11616 | 2019-06-06 | 2019-08-06
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034450167 — Goverdhan siha ke ghar se sattar kha ke ghar tk | Completed | 15180 | 15136 | 2019-07-17 | 2020-02-19
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034463356 — Pappu siha ke ghar se vaktavar siha ke ghar tk | Completed | 10557 | 10384 | 2019-07-17 | 2020-02-17
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034463358 — Bagdiram ke ghar se basanti lal ke ghae tk | Completed | 23425 | 23232 | 2019-04-23 | 2019-08-06
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034468533 — vaktar simgh ke ghar se rai singh ji ghar tak cc road | Completed | 6900 | 6864 | 2019-08-03 | 2020-09-22
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034470172 — mangu siha ke ghar se gajraj siha ke ghar tak | Completed | 21735 | 21648 | 2019-11-05 | 2020-02-19
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034470174 — kachru siha ke ghar se kan siha ke ghar tk | Completed | 7245 | 7040 | 2019-11-22 | 2020-02-19
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034470178 — Gajraj siha ke ghar se ram mandir tak | Closed | 9660 | 0 | 2019-07-01
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034470580 — gajraj singh ke ghar se ram mandir tak | Closed | 9660 | 0 | 2019-07-01
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034505145 — vikram singh ke ghar se madan ke ghr tk | Completed | 14007 | 13904 | 2019-12-22 | 2020-09-22
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034507871 — Bhagwandas ke ghar se kamalsingh ke ghar ki our cc road | Completed | 8453 | 8448 | 2020-03-13 | 2020-09-22
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034514054 — Cc road | Closed | 0 | 0 | 2019-04-26
UJJAIN / KHACHAROD | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034519814 — Bhawandas ke ghar se kamal singh ke ghar ki our cc road | Closed | 0 | 0 | 2019-04-01
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034540093 — balaji mandir parisar cc road | Completed | 24863 | 33060 | 2020-09-22 | 2026-02-28
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034542392 — bhanwar lal ke ghr se ratan lal ke ghar tak | Completed | 13950 | 13680 | 2020-10-06 | 2026-02-28
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034544945 — Nandaram ke ghar se sruesh lal ke ghar ki our cc road | Completed | 13950 | 13680 | 2020-10-20 | 2023-07-15
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034544946 — Hanuman mandir se ramprasad ke ghar ki our cc road | Completed | 25500 | 14920 | 2020-10-28 | 2024-01-03
UJJAIN / KHACHAROD | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718001028/RC/22012034555921 — ग्राम कलसी से झांझाखेड़ी खेत सड़क तक ( सुदूर ग्राम संपर्क/खेत सड़क) ग्रेवल रोड ग्राम कलसी | Completed | 2440392.03 | 1332660.2 | 2021-01-25 | 2026-03-04
UJJAIN / KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034583071 — Aaganwadi bhawan se nagda bercha road tak cc road | Completed | 44019 | 38214 | 2021-11-24 | 2024-01-03
UJJAIN / KHACHAROD | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034583072 — Mangusingh ke ghar se Aaganwadi bhawan tak cc road | Completed | 44019 | 25476 | 2021-10-27 | 2026-02-28
UJJAIN / KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034607969 — nai nraman bercha rod se babaji tak | Completed | 35100 | 40392 | 2022-05-18 | 2026-02-28
UJJAIN / KHACHAROD | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034615414 — Ramprasda ke ghar se mangusingh ke ghar ki our | Completed | 38250 | 37944 | 2022-05-25 | 2025-12-20
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034649370 — Nali Nirman Rakesh bapu ke Ghar Se Pappu Set ke Ghar Ki Or | Completed | 45750 | 44863 | 2023-10-03 | 2025-12-20
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034651292 — cc road parmanand prajapat ke ghar ghar se kal bherav mandir ki or | Completed | 39005 | 30498 | 2023-10-03 | 2024-06-19
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034663097 — Nala Nirman kary Shantisham Ke Pass Kalsi | Completed | 41623 | 41327 | 2023-10-06 | 2024-06-19
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034663127 — CC Road main Raod se Shantidham tak Kalsi | Completed | 24909 | 24089 | 2023-10-06 | 2024-06-19
UJJAIN / KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/22012034838478 — RCC Nali Nirman Chen singh ke ghar se Parmandd ke Ghar Tak | Approved | 17044 | 0 | 2024-07-01
UJJAIN / KHACHAROD | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718001028/RC/46/मनरेगा — 1718001028/RC/46/मनरेगा | Completed | 99800 | 81525 | 2012-07-02 | 2014-04-25
UJJAIN / KHACHAROD | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718001028/RS/22012034323733 — हुसेन मिरू शौचलय अलसी | Closed | 9800 | 0 | 2016-10-02
UJJAIN / KHACHAROD | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718001028/RS/22012034697459 — सामुदायिक स्वछता परिसर कलसी | Completed | 47000 | 46852 | 2023-06-30 | 2024-03-04
UJJAIN / KHACHAROD | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1718001028/RS/22012035129875 — nali nirman Chain singh ke ghar se parmanand ke ghar tak | Approved | 17000 | 0 | 2024-07-30
UJJAIN / KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718001028/WC/22012034431061 — nala treching 1 | Completed | 133096 | 110796 | 2019-01-16 | 2020-01-24
UJJAIN / KHACHAROD | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1718001028/WC/22012034431067 — nala treching 2 | Completed | 116931 | 105120 | 2019-01-10 | 2020-01-24
UJJAIN / KHACHAROD | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718001028/WC/22012034507940 — samudayik kup | Completed | 450949.98 | 437736.8 | 2019-12-20 | 2024-12-13
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718001028/WC/22012034530061 — सामुदायिक कूप कलसी 2 | Completed | 450949.98 | 439513.95 | 2020-05-05 | 2025-03-02
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001028/WC/22012034530062 — नाला ट्रेचिंग नई आबादी कलसी | Completed | 144567.72 | 107470 | 2020-05-24 | 2023-07-15
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718001028/WC/22012034549800 — निम्बोदिया मार्ग रिचार्ज पोंड कलसी | Completed | 332572.21 | 241038 | 2020-05-19 | 2025-05-25
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718001028/WC/22012034562910 — richarg pond aanand puri ke khet ke pas | Deleted | 332962.02 | 1330 | 2021-01-09
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001028/WC/22012034583571 — richarj pond gram kalsi aanad puri ke khet ke pas kalsi | Closed | 0 | 0 | 2020-04-02
UJJAIN / KHACHAROD | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001028/WC/22012034583572 — richarg pond gram alsi savaji ji ke khet ke pas kalsi | Completed | 332962.02 | 173828 | 2021-03-12 | 2025-05-28
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718001028/WC/22012034754655 — samudayak kup deva mataji ki said gram alsi | Closed | 0 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1718001028/WC/22012034764150 — Gram panchayat kalsi gram alsi me mataji ki radi me samudaik kup nirman | Closed | 0 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001028/WC/22012034764153 — Gram panchayt kalsi nala treching rod par | Closed | 0 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001028/WC/22012034776512 — Sokhta gadda panchayat bhawan ke paas gram kalsi | Completed | 14467.3 | 13896 | 2021-09-24 | 2022-02-01
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001028/WC/22012034776516 — sokhta gada puliya ke pass gram kalsi | Completed | 14467.3 | 15054 | 2021-10-09 | 2022-02-01
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001028/WC/22012034776520 — shokhta gadda samudaik kup ke pass gram kalsi | Completed | 14467.3 | 13896 | 2021-10-09 | 2022-02-01
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001028/WC/22012034776526 — shokta gadda gav ke nikas nali ke pass gram kalsi | Closed | 14467.3 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001028/WC/22012034776531 — shokhta gadda nala trecheng ke pass gram kalsi | Closed | 14467.3 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001028/WC/22012034776536 — shokhta gadda men nale ke pass gram kalsi | Completed | 14467.3 | 11580 | 2021-11-11 | 2022-02-01
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718001028/WC/22012034776541 — shokhta gadda samidaik kup ke pass gram kalsi | Closed | 14467.3 | 0 | 2021-04-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001028/WC/22012034780369 — gram Kalsi nala treching new aabadi Jane wale rashte ke pas me | Completed | 266999.4 | 241027 | 2021-09-07 | 2025-05-02
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1718001028/WC/22012034906184 — nala trachingh kelash ke khet ke pass kalsi | Completed | 151748.31 | 127525 | 2022-03-22 | 2025-12-25
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Trench for Community | Construction of Trench | 1718001028/WC/22012034906186 — nala trachingh kelash ke khet ke pass kalsi | Closed | 0 | 0 | 2022-01-25
UJJAIN / KHACHAROD | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718001028/WC/22012034923454 — tali pal maramat kalsi | Completed | 39000 | 3606 | 2022-03-10 | 2023-07-07
UJJAIN / KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718001028/WC/22012035209825 — nala trachingh shantidham ke pas kalsi | Approved | 0 | 0 | 2024-06-12
UJJAIN / KHACHAROD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718001028/WC/22012035238986 — Recharge Pond Gram Alsi Dinesh ke khet ke pass | Completed | 307825.06 | 142192 | 2025-03-11 | 2026-03-16
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718001028/WC/22012035297579 — JGSA kup recharge pit samudayik kup | Completed | 25899.46 | 11484 | 2025-05-18 | 2026-01-30
UJJAIN / KHACHAROD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1718001028/WC/22012035297586 — JGSA kup recharge pit nai aabadi kalsi | Completed | 25899.46 | 11223 | 2025-05-22 | 2026-01-30
UJJAIN / KHACHAROD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718001/IF/22012034589770 — MANREGA NIJI KHET ME FALOUDHAN SUMER SINGH NARAYAN SINGH KALSE | Closed | 142545 | 4560 | 2020-07-29