## Work List
Exported on: 2026-10-25 08:36:23
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BIRAMKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN / GHATIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1718003047/AV/22012034399425 — Anganwadi/Other Rural Infrastructure Koyalkedi | Ongoing | 180000 | 0 | 2019-09-17
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1718003047/IC/22012034888258 — samudaik kup sinchai hetu shamshan ke pass | Physically Completed | 588165.42 | 0 | 2025-03-15 | 2026-10-13
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1718003047/IC/22012034888259 — samudaik kup sinchai hetu Kalu singh ke khet ke pass | Physically Completed | 588165.42 | 0 | 2025-03-15 | 2026-10-13
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1718003047/IC/22012034888658 — samudaik kup sinchai hetu shamsha ke pass | New | 0 | 0 | 2025-01-26
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1718003047/IC/22012034888659 — samudaik kup sinchai hetu Kalu singh ke khet ke pass | New | 0 | 0 | 2025-01-26
UJJAIN / GHATIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718003047/IF/22012035206888 — kapildhara koop nirman | New | 0 | 0 | 2023-04-01
UJJAIN / GHATIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718003047/IF/22012035206890 — kapildhara koop nirman | New | 0 | 0 | 2023-04-01
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1718003047/IF/22012035251786 — NIJI KHET PAR PHALODHYAN GENDAKUNVAR/LAKHAN | Approved | 0 | 0 | 2024-06-08
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1718003047/IF/22012035251788 — NIJI KHET PAR PHALODHYAN MAYAKUNVAR/LOKENDRA | Ongoing | 145638.56 | 0 | 2024-09-02
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1718003047/IF/22012035251789 — NIJI KHET PAR PHALODHYAN SHYARKUNWAR/KAMALSINGH | Ongoing | 145638.56 | 0 | 2024-09-02
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1718003047/IF/22012035251790 — NIJI KHET PAR PHALODHYAN RAMKUNWAR/PREMSINGH | Approved | 0 | 0 | 2024-06-08
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1718003047/IF/22012035254539 — NIJI KHET PAR PHALODHYAN MAYAKUNWAR/LOKEDNRA | New | 0 | 0 | 2024-06-08
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1718003047/IF/22012035254542 — NIJI KHET PAR PHALODHYAN SHAYARBAI/KAMAL SINGH | New | 0 | 0 | 2024-06-08
UJJAIN / GHATIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1718003047/IF/22012035391520 — JGSA Recharge structure kapildhara kup nirman Elash kunwar Arjunsingh | Approved | 0 | 0 | 2025-04-07
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1718003047/IF/22012035547222 — kapildhara koop nirman Sohanbai/Mansingh | Ongoing | 291275.44 | 0 | 2025-07-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595768 — EK BAGIYA MAA KE NAAM Sayar bai Kamal singh | Ongoing | 164231.85 | 6096.96 | 2025-09-06
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595801 — EK BAGIYA MAA KE NAAM GENDA KUNWAR Lakhan | Ongoing | 159250.27 | 0 | 2025-09-06
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595812 — EK BAGIYA MAA KE NAAM RAMKUNWAR BAI PREMSINGH | Ongoing | 162180.83 | 0 | 2025-09-06
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595819 — EK BAGIYA MAA KE NAAM KRISHNA KUNWAR SHER SINGH | Ongoing | 159250.27 | 12193.92 | 2025-09-11
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595828 — EK BAGIYA MAA KE NAAM BHURI BAI RAJESH | Ongoing | 159250.27 | 0 | 2025-09-11
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595835 — EK BAGIYA MAA KE NAAM LAD KUNWAR TEJ SINGH | Ongoing | 159250.27 | 0 | 2025-09-11
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595848 — EK BAGIYA MAA KE NAAM SEEMA BAI PAPPU | Ongoing | 159250.27 | 0 | 2025-09-11
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595874 — EK BAGIYA MAA KE NAAM BADU BAI TOFAN SINGH | Ongoing | 161573.72 | 0 | 2025-09-12
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595877 — EK BAGIYA MAA KE NAAM KAILASHBAI RAM SINGH | Ongoing | 159016.14 | 0 | 2025-09-11
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595906 — EK BAGIYA MAA KE NAAM HIRAMANI KUNWAR NATHU SINGH | Ongoing | 159250.27 | 14009.22 | 2025-09-12
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595911 — EK BAGIYA MAA KE NAAM SHANTI BALU | Ongoing | 159250.27 | 12193.92 | 2025-09-11
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035595919 — EK BAGIYA MAA KE NAAM MAMTA BAI KELASH | Ongoing | 159617.14 | 0 | 2025-09-12
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035619995 — EK BAGIYA MAA KE NAAM RADHA BAI VIKRAM | Ongoing | 158169.62 | 0 | 2025-10-03
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035620003 — EK BAGIYA MAA KE NAAM NOJI BAI BAHADUR | Ongoing | 159025.63 | 0 | 2025-10-03
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035622516 — EK BAGIYA MAA KE NAAM MAYAK KUNVAR LOKENDRA | Ongoing | 158169.62 | 0 | 2025-09-21
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035625665 — EK BAGIYA MAA KE NAAM SHYAM KUNWAR TOOFAN | Approved | 269407.26 | 0 | 2025-05-16
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035625667 — EK BAGIYA MAA KE NAAM SHAYAMU BAI MOHAN | Ongoing | 263511.37 | 4500 | 2025-10-29
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035626383 — EK BAGIYA MAA KE NAAM SHYAM KUNWAR TUFAN SINGH | New | 0 | 0 | 2025-08-18
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1718003047/IF/22012035626562 — EK BAGIYA MAA KE NAAM SANTOSHKUNVAR RAJENDRA | Ongoing | 263511.37 | 17625.12 | 2025-10-29
UJJAIN / GHATIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/4231179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124966307 | Ongoing | 27000 | 0 | 2022-09-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5190208 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119308247 | Ongoing | 27000 | 0 | 2025-09-28
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5239587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125519893 | Approved | 27000 | 0 | 2025-02-21
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5263884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125868081 | Ongoing | 27000 | 0 | 2025-05-02
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5287617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124968149 | Approved | 27000 | 0 | 2025-02-21
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5292863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124970282 | Approved | 27000 | 0 | 2025-02-21
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5322434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290954 | Approved | 27000 | 0 | 2025-02-21
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115064006 | Ongoing | 27000 | 15000 | 2026-07-23
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113653872 | Physically Completed | 27000 | 27000 | 2026-08-18 | 2026-10-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119299872 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119305161 | Ongoing | 27000 | 8400 | 2026-08-31
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935967 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119305809 | Ongoing | 27000 | 2100 | 2026-08-31
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119307077 | Ongoing | 27000 | 18600 | 2026-08-07
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119307575 | Ongoing | 27000 | 11100 | 2026-08-07
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5935970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119308646 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5936499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114103904 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5936543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114112731 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5936721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114144706 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5936754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114662779 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5936899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114190798 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5936994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115350156 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118352893 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118354200 | Ongoing | 27000 | 1500 | 2026-10-05
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118354373 | Ongoing | 27000 | 14400 | 2026-08-31
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114154997 | Ongoing | 27000 | 7800 | 2026-08-31
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115780829 | Ongoing | 27000 | 5400 | 2026-08-31
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114096638 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290090 | Ongoing | 27000 | 19200 | 2026-08-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5937843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114933363 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5938677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114106122 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5938735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114137018 | Ongoing | 27000 | 21600 | 2026-08-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5938887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114670985 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5939359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117712216 | Ongoing | 27000 | 11400 | 2026-08-18
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5939360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290848 | Ongoing | 27000 | 5700 | 2026-09-03
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5939361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113754145 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5939362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114098289 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5939363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119301185 | Ongoing | 27000 | 5700 | 2026-09-03
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5939498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121733603 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5940255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114121091 | Ongoing | 27000 | 24000 | 2026-07-23
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5940588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117619405 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5940820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119293431 | Ongoing | 27000 | 0 | 2026-10-05
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5940870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118551982 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5940871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118552271 | Ongoing | 27000 | 25500 | 2026-09-03
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5940872 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118552512 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5940873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118552587 | Ongoing | 27000 | 25986 | 2026-07-16
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114161256 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941120 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125863458 | Ongoing | 27000 | 0 | 2026-07-23
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119307879 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290060 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119292967 | Ongoing | 27000 | 8400 | 2026-09-08
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941542 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119292299 | Physically Completed | 27000 | 11508 | 2026-04-23 | 2026-09-06
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119292577 | Ongoing | 27000 | 11400 | 2026-09-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125817063 | Ongoing | 27000 | 0 | 2026-03-23
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125819563 | Ongoing | 27000 | 16200 | 2026-07-23
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114114253 | Ongoing | 27000 | 0 | 2026-09-08
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5941808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119297536 | Ongoing | 27000 | 11400 | 2026-09-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5942572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113760147 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5942601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119293816 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5942609 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118353401 | Physically Completed | 27000 | 27000 | 2026-07-03 | 2026-10-11
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5942642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118552409 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5942649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114933187 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5943103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115348410 | Ongoing | 27000 | 8400 | 2026-09-08
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5975988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119329225 | Physically Completed | 23490 | 15708 | 2026-06-04 | 2026-08-23
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5976594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125864238 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5976717 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114086387 | Ongoing | 27000 | 7800 | 2026-09-14
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114670787 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114672061 | Ongoing | 27000 | 16800 | 2026-09-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114692858 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977731 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114692890 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114692901 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977846 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114662136 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114662615 | Ongoing | 27000 | 7800 | 2026-07-23
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5977848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114669781 | Ongoing | 27000 | 0 | 2026-04-23
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5978898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125836726 | Ongoing | 27000 | 8400 | 2026-08-07
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5979107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119312828 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5979110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119318609 | Ongoing | 27000 | 13800 | 2026-09-08
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5979111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119320192 | Ongoing | 27000 | 10200 | 2026-08-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5979541 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119284188 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5979579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114671266 | Ongoing | 27000 | 0 | 2026-07-16
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119319708 | Ongoing | 27000 | 3000 | 2026-10-05
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117712136 | Ongoing | 27000 | 6000 | 2026-09-30
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290539 | Ongoing | 27000 | 10800 | 2026-07-23
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290756 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290812 | Ongoing | 27000 | 10800 | 2026-08-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290832 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980164 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290861 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290882 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980166 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290888 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114666219 | Ongoing | 27000 | 7200 | 2026-08-08
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114692924 | Ongoing | 27000 | 18300 | 2026-07-23
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980920 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114692958 | Ongoing | 27000 | 14400 | 2026-08-07
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114836415 | Physically Completed | 27000 | 19908 | 2026-04-23 | 2026-09-27
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114692981 | Ongoing | 27000 | 8400 | 2026-08-07
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114693051 | Ongoing | 27000 | 27000 | 2026-08-08
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5980970 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114693079 | Ongoing | 27000 | 0 | 2026-10-26
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5981402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114668110 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5981522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119286579 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5981781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117710156 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5981829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114668870 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5981980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290014 | Ongoing | 27000 | 3000 | 2026-10-05
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5982220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125533089 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5982225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114671793 | Ongoing | 27000 | 0 | 2026-09-23
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5982615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114928824 | Ongoing | 27000 | 1500 | 2026-10-05
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5982616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114928826 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5982617 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114928830 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5982618 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114928831 | Ongoing | 27000 | 3000 | 2026-10-05
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5983249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125810494 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5983304 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117710793 | Physically Completed | 27000 | 9000 | 2026-04-28 | 2026-10-18
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5983306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117710880 | Ongoing | 27000 | 10800 | 2026-04-28
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5983308 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117711842 | Ongoing | 27000 | 0 | 2026-08-26
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5983761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114083452 | Ongoing | 27000 | 16200 | 2026-07-23
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5983929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117712301 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5984076 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124971444 | Ongoing | 27000 | 10800 | 2026-08-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5984313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124968488 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5984823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114669375 | Ongoing | 27000 | 0 | 2026-10-26
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5985396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119285737 | Ongoing | 27000 | 11100 | 2026-06-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5985399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117710609 | Ongoing | 27000 | 7800 | 2026-04-28
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5985455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125840272 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5985806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127231877 | Ongoing | 27000 | 0 | 2026-09-14
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5985937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125862114 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5986003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117710979 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5986004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117711758 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5986278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114678234 | Ongoing | 27000 | 16800 | 2026-09-08
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5986279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114663458 | Ongoing | 27000 | 18600 | 2026-07-29
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5986280 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114667610 | Ongoing | 27000 | 7200 | 2026-08-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/5986371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125805859 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6101901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126006222 | Ongoing | 27000 | 16800 | 2026-08-07
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6106837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119321827 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6110434 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119306704 | Approved | 27000 | 0 | 2026-03-05
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6256596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119299035 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6262751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124967771 | Approved | 27000 | 0 | 2026-05-18
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6281437 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127965002 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6292578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114190896 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6325613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290584 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6325875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290611 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6326116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125097026 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6326288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125993399 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6326865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116202714 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6343965 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115290561 | Approved | 27000 | 0 | 2026-05-18
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6344269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124967312 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6353320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114669181 | Approved | 27000 | 0 | 2026-02-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6364421 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119306343 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6365287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114663637 | Approved | 27000 | 0 | 2026-02-17
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6366156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115066149 | Approved | 27000 | 0 | 2026-02-10
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718003047/IF/IAY/6381047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118552131 | Approved | 27000 | 0 | 2026-03-05
UJJAIN / GHATIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718003047/RC/22012034580966 — Puliya Nirman GP Biramkhedi | Physically Completed | 317000 | 0 | 2022-05-26 | 2026-10-13
UJJAIN / GHATIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1718003047/RC/22012034821931 — cc road and nali nirman Teju singh ke ghar se Krapal singh ke ghar ki our | Approved | 0 | 0 | 2024-06-08
UJJAIN / GHATIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Gully Plug for Community | Construction of Check Dam/Stop Dam | 1718003047/WC/22012035145585 — nala trancha Ramlal ke khet se Ramchanran ke khet ki our | Ongoing | 201189.55 | 0 | 2024-03-15
UJJAIN / GHATIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1718003047/WC/22012035184953 — nala tranch nirman kishor singh ke khet se mahendra ke khet ki our | Ongoing | 181170.6 | 0 | 2024-03-15
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1718003047/WC/22012035250441 — Percalation Tank nirman PM road ke pass | Approved | 0 | 0 | 2025-01-26
UJJAIN / GHATIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718003047/WC/VB/22012035330248 — Rooftop Rainwater Harvesting Shasakiya Prathmik Vidyalay Atirikt kash | Approved | 30496.65 | 0 | 2026-04-14