## Work List
Exported on: 2026-09-10 04:02:11
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: AMARPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN / GHATIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1718003058/AV/22012034637840 — Shantidham shed nirman majra tola tibba ajja basti suliya | Ongoing | 226381.46 | 0 | 2023-10-06
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718003058/DP/22012034613982 — sankirn pond | New | 0 | 0 | 2024-04-01
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1718003058/IC/22012034887250 — samudaik kup sinchai hetu shamshan ghat par | Approved | 588165.42 | 0 | 2024-10-02
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1718003058/IC/22012034887309 — samudaik kup sinchai hetu Tilvat marg par | Ongoing | 588165.42 | 0 | 2025-03-12
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1718003058/IC/22012034887310 — samudaik kup sinchai hetu Kankar Marg par s | Ongoing | 588165.42 | 0 | 2025-03-05
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1718003058/IC/22012034892264 — samudayik koop sichai hetu nale ke pass | Approved | 605674.76 | 0 | 2025-06-06
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718003058/IF/22012035200932 — kapildhara koop nirman | New | 0 | 0 | 2024-04-01
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1718003058/IF/22012035251773 — NIJI KHET PAR PHALODHYAN SAMPATBAI/KALUSINGH | Approved | 145050.83 | 0 | 2024-06-08
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1718003058/IF/22012035383654 — kapildhara koop nirman Gopalsingh/Bhagvan singh | Approved | 322434.5 | 0 | 2025-04-07
UJJAIN / GHATIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/3928222 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105780417 | Approved | 27000 | 0 | 2022-05-05
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/3939942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105051644 | Ongoing | 27000 | 0 | 2026-06-04
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/4543317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105065521 | Approved | 27000 | 0 | 2024-09-10
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5160259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105782648 | Approved | 27000 | 0 | 2025-03-01
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5163030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103410524 | Approved | 27000 | 0 | 2025-02-28
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5168318 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105063173 | Approved | 27000 | 0 | 2025-03-13
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5198428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105780496 | Ongoing | 27000 | 0 | 2026-06-04
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5211616 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130929648 | Approved | 27000 | 0 | 2025-02-28
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5238020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105778957 | Ongoing | 27000 | 0 | 2026-01-28
UJJAIN / GHATIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5571290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105035712 | Approved | 27000 | 0 | 2025-03-01
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5579281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105784388 | Ongoing | 27000 | 0 | 2026-04-05
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5579345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131267513 | Ongoing | 27000 | 0 | 2025-09-25
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5580907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105778691 | Physically Completed | 23490 | 0 | 2026-06-04 | 2026-08-16
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5735995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105050049 | Ongoing | 27000 | 8100 | 2026-06-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5736199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130627569 | Ongoing | 27000 | 0 | 2025-09-12
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5740709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105779411 | Physically Completed | 23490 | 0 | 2026-05-05 | 2026-08-16
UJJAIN / GHATIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5742122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105779896 | Ongoing | 27000 | 0 | 2026-06-04
UJJAIN / GHATIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718003058/IF/IAY/5805299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105056049 | Approved | 27000 | 0 | 2025-08-29
UJJAIN / GHATIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718003058/RC/22012034678181 — cc road | New | 0 | 0 | 2024-04-01
UJJAIN / GHATIYA | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718003058/RC/22012034845383 — cc road nirman men road se suresh ke ghar ki our | Ongoing | 38000 | 0 | 2026-05-13
UJJAIN / GHATIYA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718003058/RC/22012034853023 — cc road nirman Mukhay marg se Ratan singh ke ghar ki our | Approved | 50000 | 0 | 2025-12-26
UJJAIN / GHATIYA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1718003058/WC/22012035169298 — check dam | New | 0 | 0 | 2024-04-01
UJJAIN / GHATIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718003058/WC/VB/22012035330391 — Rooftop Rainwater Harvesting Samudayik bhavan me | Approved | 0 | 0 | 2026-04-14
UJJAIN / GHATIYA | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1718003058/WC/VB/22012035330392 — Rooftop Rainwater Harvesting Atal Rain basera amarpura | Approved | 0 | 0 | 2026-04-14