## Work List
Exported on: 2026-10-25 07:05:46
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: NARELAKALAN
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1718006065/FR/22012034322880 — Samudayik khet talab bheru ke khet ke pass kalmoda | New | 0 | 0 | 2024-10-02
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1718006065/FR/22012034325587 — Dagout pond nirman prakash ke khet ke pass narelakala 2025 | New | 0 | 0 | 2025-08-15
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1718006065/FR/22012034325588 — Dagout pond nirman eliyas patel ke khet ke pass narelakala 2025 | New | 0 | 0 | 2025-08-16
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1718006065/FR/22012034325678 — samudayek khet talab nirman munshi ke khet ke pass kalmoda 2025 | New | 0 | 0 | 2025-10-02
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1718006065/FR/22012034325721 — samudayek khet talab nirman harisingh ke khet ke pass narelakala 2026 | New | 0 | 0 | 2026-01-26
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Fisheries | Construction of Fisheries Ponds for Community / Construction of Fishery Pond for Community | Construction of Tank | 1718006065/FR/22012034325722 — samudayek khet talab nirman nagusingh ke khet ke pass kalmoda 2026 | New | 0 | 0 | 2026-01-27
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/4575805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118070353 | Approved | 27000 | 0 | 2024-09-13
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/4992262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113521055 | Ongoing | 27000 | 261 | 2025-06-30
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5420460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115266213 | Approved | 27000 | 0 | 2025-02-10
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5420893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118095049 | Approved | 27000 | 0 | 2025-02-10
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5805718 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118189075 | Approved | 27000 | 0 | 2025-02-10
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5806024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118121991 | Approved | 27000 | 0 | 2025-02-10
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5863083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118055727 | Approved | 27000 | 0 | 2025-02-10
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5863089 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114984366 | Ongoing | 27000 | 0 | 2026-02-13
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5863143 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118059000 | Approved | 27000 | 0 | 2025-02-10
UJJAIN / BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/5970568 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118059091 | Completed | 23490 | 0 | 2026-05-09 | 2026-09-23
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/67625 — Construction of IAY House -IAY REG. NO. MP-18-006-065-002/53 | Approved | 27000 | 0 | 2016-01-01
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/67626 — Construction of IAY House -IAY REG. NO. MP-18-006-065-002/54 | Approved | 27000 | 0 | 2016-01-01
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/92671 — Construction of IAY House -IAY REG. NO. MP-18-006-065-003/19 | Approved | 27000 | 0 | 2015-08-26
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1718006065/IF/IAY/93433 — Construction of IAY House -IAY REG. NO. MP-18-006-065-002/04 | Approved | 27000 | 0 | 2015-08-26
UJJAIN / BADNAGAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1718006065/RS/22012035129171 — Nali nirman panda ji ke ghar se gajendra singh ji ke ghar ki or kalmoda | Approved | 0 | 0 | 2024-06-16
UJJAIN / BADNAGAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1718006065/WC/22012035228279 — Dagout pond nirman kakad per kalmoda | Approved | 0 | 0 | 2024-10-02
UJJAIN / BADNAGAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1718006065/WC/22012035287314 — Dag pond nirman prakash ke khet ke paas narelakala | Approved | 0 | 0 | 2025-04-24
UJJAIN / BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718006065/WC/VB/22012035331564 — handpump recharge pit panchayat bhawan ke pass narelakala | Ongoing | 25164.85 | 15600 | 2026-08-09
UJJAIN / BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718006065/WC/VB/22012035331566 — recharge pit school ke pass narelakala | Ongoing | 25164.85 | 15600 | 2026-08-09
UJJAIN / BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718006065/WC/VB/22012035332331 — handpump recharge pit suresh ke ghar ke pass narelakala | Ongoing | 25164.85 | 12600 | 2026-08-09
UJJAIN / BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718006065/WC/VB/22012035332333 — hanpump recharge pit school ke pass kalmoda | Ongoing | 25164.85 | 16800 | 2026-08-09
UJJAIN / BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718006065/WC/VB/22012035332334 — recharge pit school ke pass gulabkhedi | Ongoing | 25164.85 | 16800 | 2026-08-09
UJJAIN / BADNAGAR | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1718006065/WC/VB/22012035332335 — recharge pit rajaram ji ke ghar ke pass narelakala | Ongoing | 25164.85 | 16800 | 2026-08-09