## Work List
Exported on: 2026-09-02 17:46:59
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: KILOLI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
UJJAIN / BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006039/RS/22012034293073 — SAMUDAYIKSOCHALAY - GRAM PANCHAYAT BHAWAN KE PAAS KILOLI | Deleted | 115000 | 0 | 2016-01-05
UJJAIN / BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006042/RC/5 रपट निर् — किलोली मुरमीकरण नामलपुर से रणवा मार्ग भाग-1 | Completed | 480000 | 346150.02 | 2009-06-01 | 2011-07-18
UJJAIN / BADNAGAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1718006099/AV/22012034546439 — Navin goshala nirman kiloli | Ongoing | 3804449.17 | 3308865.06 | 2021-03-02
UJJAIN / BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006099/DP/22012034242486 — ग्राम आबादी से pwd रोड की और(as no 02) | Deleted | 33500000000 | 0 | 2017-04-19
UJJAIN / BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1718006099/DP/नंदन फलोद्यान जगदीश नागु किलोली — नंदन फलोद्यान जगदीश नागु किलोली | Completed | 48200 | 1884 | 2008-09-02 | 2011-07-18
UJJAIN / BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006099/IF/22012034341720 — वृक्ष रोपण ग्राम आबादी से pwd रोड की और(as no 06) | Completed | 335000 | 9964 | 2017-05-22 | 2021-12-14
UJJAIN / BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1718006099/IF/22012034357512 — VARCHHA ROPAN namalpr2 | Completed | 335000 | 6500 | 2017-08-10 | 2019-09-10
UJJAIN / BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/22012034371368 — IAY SUNIL JAGDISH | Completed | 1435000000 | 14128 | 2017-12-06 | 2018-06-04
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006099/IF/22012035227982 — CATTLE SHESD KRISHNA BAI PYARCHANDRA | Closed | 0 | 0 | 2024-01-26
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006099/IF/22012035238292 — CATTLE SHED KRISHNA BAI PYARCHAND KILOLI | Ongoing | 110545.11 | 76411.9 | 2024-09-07
UJJAIN / BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006099/IF/9993649851 — pashu shed jaswant panna(ts-578/30.1.14) | Deleted | 70700 | 0 | 2014-08-12
UJJAIN / BADNAGAR | 2014-2015 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006099/IF/9993649853 — pashu shed ransingh (ts-577/30.1.14) | Deleted | 70700 | 0 | 2014-08-12
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/9993689043 — IAY(hiralal ji) | Completed | 14310 | 5916 | 2015-11-23 | 2017-10-25
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/9993689305 — IAY सायर बाई | Completed | 14310 | 12337.2 | 2015-11-23 | 2017-10-17
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1718006099/IF/9993692952 — KHET SAMTALI KARN ESHVARLAL -RATANLAL | Deleted | 116000 | 0 | 2015-12-06
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1718006099/IF/9993700918 — KETAL SHED BHERULAL NARSINGH (TS-413/11/12/2015 AS-10/13/12/2015) | Deleted | 100000 | 0 | 2015-12-30
UJJAIN / BADNAGAR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/1847978 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5037114 | Completed | 15660 | 15660 | 2018-06-30 | 2018-11-11
UJJAIN / BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/262270 — Construction of IAY House -IAY REG. NO. MP2113210 | Completed | 15030 | 13750 | 2017-01-30 | 2019-08-30
UJJAIN / BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/270068 — Construction of IAY House -IAY REG. NO. MP2478945 | Completed | 15030 | 16392 | 2017-01-30 | 2018-03-13
UJJAIN / BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/270154 — Construction of IAY House -IAY REG. NO. MP2576956 | Completed | 15030 | 14934 | 2017-01-30 | 2018-06-18
UJJAIN / BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/285280 — Construction of IAY House -IAY REG. NO. MP2525380 | Completed | 15030 | 15360 | 2017-01-30 | 2017-12-06
UJJAIN / BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3307147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2347414 | Completed | 17370 | 17340 | 2022-11-23 | 2023-04-15
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3966873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115010662 | Completed | 18360 | 17820 | 2023-06-13 | 2024-07-04
UJJAIN / BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3970975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115303996 | Completed | 18360 | 18088 | 2023-03-03 | 2023-09-15
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3970976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115304040 | Completed | 18360 | 17680 | 2023-08-26 | 2024-07-04
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3971751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114999197 | Completed | 18360 | 19006 | 2023-08-02 | 2024-10-29
UJJAIN / BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3973886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116928936 | Closed | 18360 | 0 | 2022-05-10
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3974402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145616 | Physically Completed | 18360 | 19926 | 2024-09-10 | 2024-11-21
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3974461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168431 | Completed | 18360 | 18283 | 2023-08-03 | 2024-07-04
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3974463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168597 | Physically Completed | 18360 | 16524 | 2024-09-07 | 2024-11-21
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3974464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168678 | Completed | 18360 | 17416 | 2023-12-02 | 2024-07-04
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3974603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117029474 | Completed | 18360 | 17820 | 2023-07-28 | 2024-07-04
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3977961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115337332 | Completed | 18360 | 18332 | 2023-06-13 | 2024-07-09
UJJAIN / BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3977992 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115350824 | Physically Completed | 18360 | 10746 | 2022-09-03 | 2024-11-21
UJJAIN / BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/3998465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145575 | Closed | 18360 | 0 | 2022-05-11
UJJAIN / BADNAGAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4040885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115169037 | Approved | 23490 | 0 | 2022-05-10
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4040886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115169286 | Completed | 18360 | 17479 | 2023-08-05 | 2024-07-04
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4066150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168751 | Completed | 18360 | 17745 | 2023-08-01 | 2024-07-04
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4328841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117033281 | Completed | 18360 | 17220.2 | 2023-07-28 | 2024-07-09
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4368571 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115317835 | Completed | 18360 | 17820 | 2023-07-28 | 2024-07-04
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4397810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116897331 | Closed | 19890 | 0 | 2023-07-08
UJJAIN / BADNAGAR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4398065 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116810841 | Completed | 19890 | 19403 | 2023-08-02 | 2024-07-04
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4698493 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168479 | Ongoing | 23490 | 21717 | 2024-12-08
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4698495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115169120 | Ongoing | 23490 | 21879 | 2024-12-08
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/4751744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116963253 | Completed | 23490 | 22383 | 2025-02-07 | 2025-12-10
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5003483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117406893 | Completed | 23490 | 23229 | 2025-05-17 | 2025-12-10
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5501815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117025698 | Ongoing | 23490 | 22968 | 2025-05-17
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5668894 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145515 | Completed | 23490 | 23490 | 2025-09-19 | 2026-02-21
UJJAIN / BADNAGAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/572143 — Construction of IAY House -IAY REG. NO. MP1017332 | Completed | 15030 | 14959 | 2017-01-30 | 2018-04-02
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115007540 | Physically Completed | 23490 | 10962 | 2025-12-19 | 2026-02-03
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859548 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115340733 | Ongoing | 23490 | 23229 | 2025-12-05
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104895027 | Ongoing | 23490 | 21924 | 2025-12-05
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117414198 | Physically Completed | 23490 | 21924 | 2025-12-05 | 2026-02-03
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116965689 | Physically Completed | 23490 | 22968 | 2025-12-05 | 2026-05-10
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145685 | Physically Completed | 23490 | 14616 | 2025-12-05 | 2026-02-03
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115009469 | Ongoing | 23490 | 22707 | 2025-12-05
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115350886 | Physically Completed | 23490 | 22707 | 2025-12-05 | 2026-04-05
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115303901 | Ongoing | 23490 | 18270 | 2025-12-05
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115009617 | Physically Completed | 23490 | 15660 | 2025-12-05 | 2026-03-06
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115350704 | Ongoing | 23490 | 18270 | 2025-12-05
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115168379 | Approved | 23490 | 0 | 2025-03-02
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859789 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115012067 | Physically Completed | 23490 | 22968 | 2025-12-05 | 2026-06-14
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114999297 | Physically Completed | 23490 | 22968 | 2025-12-05 | 2026-02-03
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145825 | Physically Completed | 23490 | 21924 | 2025-12-05 | 2026-02-03
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115011428 | Physically Completed | 23490 | 22968 | 2025-12-05 | 2026-02-03
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117017962 | Physically Completed | 23490 | 18270 | 2025-12-05 | 2026-03-15
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859895 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115351000 | Ongoing | 23490 | 22968 | 2025-12-05
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859921 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115007264 | Physically Completed | 23490 | 21924 | 2025-12-05 | 2026-06-28
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5859988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114935752 | Ongoing | 23490 | 23229 | 2026-01-07
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5870521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117452466 | Physically Completed | 23490 | 22968 | 2026-01-07 | 2026-05-03
UJJAIN / BADNAGAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5870522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115337280 | Ongoing | 23490 | 23229 | 2026-01-07
UJJAIN / BADNAGAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/5971023 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115145589 | Ongoing | 23490 | 7308 | 2026-05-14
UJJAIN / BADNAGAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/6244655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116965757 | Approved | 23490 | 0 | 2025-02-22
UJJAIN / BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/780939 — Construction of IAY House -IAY REG. NO. MP2103000 | Completed | 15480 | 14792 | 2017-05-16 | 2018-04-11
UJJAIN / BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/781146 — Construction of IAY House -IAY REG. NO. MP3407008 | Completed | 15480 | 15504 | 2017-12-07 | 2018-06-01
UJJAIN / BADNAGAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/781170 — Construction of IAY House -IAY REG. NO. MP3669378 | Completed | 15480 | 15540 | 2017-05-16 | 2018-06-01
UJJAIN / BADNAGAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1718006099/IF/IAY/92684 — Construction of IAY House -IAY REG. NO. MP-18-006-099-001/15 | Approved | 23490 | 0 | 2015-08-26
UJJAIN / BADNAGAR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006099/LD/1वजेसिह — किलोली मेढबंधान कार्य वजेसिह शंकरलाल | Completed | 5632 | 6552 | 2008-12-12 | 2009-03-26
UJJAIN / BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006099/LD/22012034294232 — शांतिधाम समग्र विकाश(रोड़+शेड़+समतलीकरण TS No.141) | Completed | 1318000 | 737624.53 | 2016-12-02 | 2018-08-05
UJJAIN / BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1718006099/LD/22012034298620 — SANTIDHAM NAMLPUR(TS 7258, AS-05) | Completed | 180000 | 179007.85 | 2017-01-23 | 2018-06-27
UJJAIN / BADNAGAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1718006099/LD/3799424229 — KHEL MEDAN GOVT SCHOOL(TS-183/13.9.13) | Completed | 200000 | 167566.9 | 2014-02-02 | 2015-03-31
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034183880 — CC ROAD+NALI PP+M BHUWAN SE JASWANT(TS-135/2.8.13) | Completed | 66750 | 59281 | 2013-09-20 | 2015-06-05
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034183883 — CC ROAD +NALI PP+MRAMESHWAR SE MANDIR(TS-134/02.08 | Completed | 175000 | 147180 | 2013-09-20 | 2015-06-05
UJJAIN / BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/22012034218987 — greval road ramdev ji mandir(ts-44/27.1.14) | Completed | 1387000 | 1206859.9 | 2014-05-25 | 2017-02-23
UJJAIN / BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034220713 — DIWAR AWARODHAK RAJIVGANDHI(TS-58/26.5.14) | Completed | 148333 | 139160.99 | 2014-06-09 | 2015-06-12
UJJAIN / BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034220715 — cc+nali pp+m radheshyam se hendpump(ts-892/3.3.14) | Completed | 150000 | 149241 | 2014-06-09 | 2015-06-12
UJJAIN / BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006099/RC/22012034220719 — GRAVAL ROAD PALIYA MAHARAJ(TS-54/26.5.14) | Completed | 1455000 | 1173280.5 | 2014-06-02 | 2017-02-23
UJJAIN / BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034264232 — cc road +nali nirman pp+m gram abadi kiloli | Closed | 0 | 0 | 2014-10-02
UJJAIN / BADNAGAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034264736 — cc+nali nirman mn+pp2 gram abadi kiloli | Closed | 0 | 0 | 2014-10-02
UJJAIN / BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034301927 — सीसी रोड +नाली निर्माण 14V + M गोरधन के घर से राधेश्याम के घर (TS 7418,AS02) | Completed | 112000 | 34982 | 2017-02-07 | 2019-09-09
UJJAIN / BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034301928 — DPR CC Road+NALI NIRMAN BALVANT KE GHAR SE SARDAR KE GHAR TAK(TS- 7418/26/01/2017 AS-102/2801/2017) | Completed | 27800 | 22242 | 2018-06-07 | 2021-09-10
UJJAIN / BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034302212 — dpr cc road +nali nirman lal mata se sunil v gordhan ke ghar se devalmata tak pp+m | Deleted | 68000 | 0 | 2016-04-01
UJJAIN / BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034302213 — cc road +nali nirman pp+m | Closed | 0 | 0 | 2016-04-01
UJJAIN / BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034323221 — CC ROAD AND NALI NIRMAN | Closed | 0 | 0 | 2017-01-26
UJJAIN / BADNAGAR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034323223 — cc road+nali nirman | Closed | 0 | 0 | 2017-01-26
UJJAIN / BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034371097 — सीसी रोड +नाली | Closed | 0 | 0 | 2018-04-01
UJJAIN / BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034387215 — DPR CC ROD DASHRATH KE GHAR SE HANUMAN MANDIR TAK NAMALPUR | Completed | 26600 | 27666 | 2018-04-11 | 2021-12-24
UJJAIN / BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034440221 — CC ROAD+NALI | Closed | 0 | 0 | 2019-04-14
UJJAIN / BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034440773 — dpr cc rod pm rod se school ke samne tejaji mandir | Completed | 15000 | 18900 | 2019-02-05 | 2019-06-17
UJJAIN / BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034441230 — dpr nali nirman school ke samne pwd rod ke dono or | Closed | 10000 | 0 | 2019-12-09
UJJAIN / BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034443205 — DPR CC ROD repairing NIRMAN CHANDAR KE GHAR SE SUNIL KE GHAR TAK | Completed | 6000 | 5220 | 2019-02-22 | 2021-10-10
UJJAIN / BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034443219 — DPR CC ROD NIRMAN BONDAR JI KE GHAR SE PWD ROD TAK | Completed | 21000 | 21750 | 2019-02-22 | 2019-06-17
UJJAIN / BADNAGAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034448017 — dpr cc rod nali nirman shobharam tolaram ke ghar se antrik mang tak namalpur | Completed | 19000 | 18610 | 2019-11-13 | 2021-10-10
UJJAIN / BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718006099/RC/22012034550208 — ग्रेवलरोडPWD रोड से मुक्तिधाममार्ग नारायण के खेत तक एवंनारायण के खेत से गुर्जरमोहल्ला बद्री के खेततक | Ongoing | 2344233.79 | 1675034.29 | 2021-03-14
UJJAIN / BADNAGAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/22012034833430 — Cement concrete ki nali nirmand govt. School se namlpur k raste gram kiloli | Ongoing | 82000 | 0 | 2026-03-01
UJJAIN / BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/27मुरमीकरण — मुरमीकरण कार्य गंगाजल नाले से अशोक के खेत तक किलोली की ओर | Completed | 500000 | 293396.11 | 2010-06-18 | 2010-07-10
UJJAIN / BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/33सी सी रो — सी सी रोङ व नाली P.P+ M.‍िनमाण मांगीलाल से जगदीश कीलोली(536/14.03.2012) | Completed | 175000 | 54343.19 | 2012-06-04 | 2014-05-28
UJJAIN / BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/34CC ROAD — CC ROAD ABHIKARAN KILOLI(107/22/02/2011) | Completed | 300000 | 191996 | 2012-01-27 | 2013-02-20
UJJAIN / BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/35Reti Ban — Reti Banda manohar se piliya nala ANAM Nayi Abadi KILOLI (113/2.6.12) | Completed | 156000 | 137906 | 2012-06-19 | 2013-02-20
UJJAIN / BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1718006099/RC/35सी सी रो — सी सी रोङ व नाली P.P+ M.‍िनमाण Namalpur m Aja Basti (T/S 43 /08.06.2012) | Completed | 150000 | 136492 | 2013-02-13 | 2013-12-24
UJJAIN / BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/4 मुरमीकरण — मुरमीकरण हरिजन बस्‍ती से बगदीराम के खेत तक भाग-1 | Completed | 500000 | 283068.59 | 2009-05-25 | 2009-06-22
UJJAIN / BADNAGAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/5 किलोली म — किलोली मुरमीकरण अशोक के खेत से काकड तक शेष भाग | Completed | 194000 | 71096.83 | 2009-12-06 | 2009-12-20
UJJAIN / BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/6 किलोली अ — किलोली अर्थवर्क बगदीराम के खेत से अशोक के खेत तक | Completed | 497000 | 249036.34 | 2010-05-05 | 2011-07-18
UJJAIN / BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/6किलोली अर — किलोली अर्थवर्क बगदीराम के खेत से अशोक के खेत तक | Deleted | 496000 | 59789.3 | 2010-06-11
UJJAIN / BADNAGAR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718006099/RC/मुरमीकरण किलोली से काकड तक किलोली — मुरमीकरण किलोली से काकड तक किलोली | Completed | 397200 | 724177.08 | 2008-07-01 | 2010-06-03
UJJAIN / BADNAGAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Soakage Channel/Pit / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1718006099/RS/22012034282259 — SOKHTA GADDHA KILOLI TS-76/12.6.15 UNIT 5 | Completed | 32500 | 20352 | 2015-07-10 | 2016-10-10
UJJAIN / BADNAGAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006099/RS/22012034498530 — SAMUDAYIK SWACHHTA PARISAR GRAM PANCHAYAT BHAWAN KE PAAS KILOLI | Closed | 48000 | 0 | 2020-10-01
UJJAIN / BADNAGAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1718006099/RS/22012034511729 — सामुदायिक स्वछता परिसर किलोलि | Physically Completed | 48000 | 44004 | 2021-04-07 | 2022-01-11
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/29917 — NIRMAL BHARAT NANDKISHORE BHERULAL (AS-100/14.04.2 | Completed | 4312 | 876 | 2013-06-08 | 2015-06-25
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71402 — nirmal bharat jaswant parwat(as-07/5.8.13) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71406 — nirmal bharat govind ramaji(as-08/5.8.12) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71414 — nirmal bharat mohan mangilal(as-9/08.5.13) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71416 — nirmal bharat prakash bai goverdhan(as-10/5.8.13) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71420 — nirmal bharat narayan mulchandra(as-11/5.8.13) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71423 — nirmal bharat mohan punaji(as-12/05.08.13) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71425 — nirmal bharat radheshyam amrudchandra(as-13/5.8.13 | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71427 — nirmal bharat mangilal amrat(tas-14/5.8.13) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71432 — nirmal bharat mukesh bapu(as-15/05.08.2013 | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71444 — nirmal bharat prakash bapu(as-16/05.08.2013) | Completed | 4312 | 4353 | 2013-10-11 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71447 — nirmal bharat ramsingh bhagirath(as-17/5.8.13) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71450 — nirmal bharat shankar sukhram(as-18/05.08.2012) | Completed | 4312 | 4353 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71452 — nirmal bharat vikram bhagirath(as-19/05.08.2013) | Completed | 4312 | 2628 | 2013-10-11 | 2016-10-10
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71454 — nirmal bharat bhagwan bhagirath(as-20/05.08.2013) | Completed | 4312 | 4353 | 2013-12-04 | 2014-04-09
UJJAIN / BADNAGAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1718006099/RS/71455 — nirmal bharat mohanlal ramnarayan(as-29/05.08.2013 | Completed | 4312 | 4313 | 2013-10-10 | 2014-04-09
UJJAIN / BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006099/WC/22012034429397 — MWC संकीर्ण तालाब निर्माण नामालपुर गाँव के पास | Completed | 418000 | 379941.95 | 2019-01-01 | 2019-12-03
UJJAIN / BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034438666 — check dam nirman | Deleted | 1202138.93 | 120 | 2020-06-21
UJJAIN / BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034442853 — CHEK DEM NALA TRECHING WORK GORDHAN KE KHET KI OR | Physically Completed | 1162900 | 754726.92 | 2019-03-08 | 2026-06-23
UJJAIN / BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034443641 — CHEK DEM NALA TRECHING WORK RET GHAT PAR | Closed | 1371776 | 0 | 2019-01-26
UJJAIN / BADNAGAR | 2018-2019 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1718006099/WC/22012034443744 — nala gharikaran work ranva marg par namalpur | Completed | 277900 | 241026 | 2019-03-08 | 2024-07-27
UJJAIN / BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034448889 — CHEK DEM NALA TRECHING RANVA PULIYA KE PAS GAV NAMALPUR KI OR | Closed | 0 | 0 | 2019-01-26
UJJAIN / BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034464783 — chek dem v nala treching gram namalpur ranva marg par | Closed | 0 | 0 | 2019-01-26
UJJAIN / BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034482829 — JAL SANCHYA WORK SCHOOL PARISAR ME HEDPAMP KA | Closed | 10857.75 | 0 | 2019-06-22
UJJAIN / BADNAGAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034482830 — JAL SANCHYA HEDPAMP HARIRAM CHOKIDAR KE GHAR KE SAMNE | Closed | 10857.75 | 0 | 2019-06-22
UJJAIN / BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006099/WC/22012034580276 — Sankirn pond namalpur | Closed | 0 | 0 | 2020-04-26
UJJAIN / BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034580721 — sankiran pond talab ke pas namalpur | Closed | 0 | 0 | 2020-08-15
UJJAIN / BADNAGAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034581012 — sankiran pond namalpur 1 | Closed | 0 | 0 | 2020-08-15
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1718006099/WC/22012034744707 — ctr richarg pit namalpur | Closed | 11979.75 | 0 | 2021-04-14
UJJAIN / BADNAGAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/22012034765640 — Ctr sankirn pond namalpur 1 | Completed | 285355.2 | 112607 | 2023-06-10 | 2025-05-29
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006099/WC/22012034831689 — richarg pit panchayt bhavan ke samne hedpump kiloli | Physically Completed | 14467.3 | 386 | 2021-10-01 | 2022-01-11
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006099/WC/22012034831696 — richarg pit chokidar ke ghar ke samne hedpump kiloli | Closed | 0 | 0 | 2021-08-15
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006099/WC/22012034831700 — richarg pit chokidar ke ghar ke samne hedpump kiloli | Closed | 0 | 0 | 2021-08-15
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006099/WC/22012034831701 — richarg pit chokidar ke ghar ke samne hedpump kiloli | Physically Completed | 14467.3 | 386 | 2021-10-01 | 2022-01-11
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006099/WC/22012034831711 — richarg pit mata ji mandir ke samne hedpump namalpur | Physically Completed | 14467.3 | 386 | 2021-10-01 | 2022-01-11
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1718006099/WC/22012034831717 — richarg pit shala bhavan hedpump namalpur | Physically Completed | 14467.3 | 772 | 2021-10-01 | 2022-01-11
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849271 — CTR Sock Pit Nirman panchayat parisar | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849274 — CTR Sock Pit Nirman shala bhavan | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849277 — CTR Sock Pit Nirman bagri mohala | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849291 — CTR Sock Pit Nirman sitaram parmar ki gali | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849296 — CTR Sock Pit Nirman rajput mohala | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849301 — CTR Sock Pit Nirman samudyik bhavan ke pass | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849305 — CTR Sock Pit Nirman balai mohala | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849311 — CTR Sock Pit Nirman hanuman mandir gali namalpur | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849318 — CTR Sock Pit Nirman pm road ke pass namalpur | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849319 — CTR Sock Pit Nirman bherulala ke ghar ke pass namalpur | Closed | 14467.3 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1718006099/WC/22012034849325 — CTR Sock Pit Nirman shala bhavan | Closed | 0 | 0 | 2021-10-02
UJJAIN / BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/7STOP DAME — STOP DAME Gangajal nale per Kiloli(48/8.6.12) | Completed | 660000 | 568544 | 2012-12-25 | 2014-05-28
UJJAIN / BADNAGAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1718006099/WC/7परकोलेशन — परकोलेशन टैंक Govt. Bhumi KILOLI (107/02.06.12) | Deleted | 126000 | 0 | 2012-05-12
UJJAIN / BADNAGAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006099/WH/19960767 — तालाब जीर्णोद्धार मरम्मत कार्य किलोली(TS-44/19.5.17) | Completed | 313000 | 172820 | 2017-05-24 | 2021-12-14
UJJAIN / BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1718006099/WH/22012034331894 — तालाब जीर्णोद्धार एवम मरम्मत कार्य | Closed | 0 | 0 | 2018-04-14
UJJAIN / BADNAGAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1718006099/WH/22012034438950 — nala gharikaran work ranva marg par namalpur | Closed | 277900 | 0 | 2019-01-26
UJJAIN / BADNAGAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718/RC/22012034154074 — Arthwork Nirman Gram Kiloli Ashok ke Khet To Satwan Mil Kankad | Completed | 500000 | 617403.37 | 2011-08-29 | 2012-04-21
UJJAIN / BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1718/RC/22012034155487 — Gramin Sadak Nirman Kiloli To Kharsod Kakad (Ramchandra ke ket To Jagdish Pujari ke ket tak) | Completed | 1681000 | 857563.16 | 2012-11-03 | 2013-02-27
UJJAIN / BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718/RC/22012034155525 — Gramin Sadak Nirman Kiloli To Kharsod (Bus Stand) (Ashok ke ket To Kharsod Funta) | Completed | 2080000 | 1445560.2 | 2013-01-28 | 2016-07-08
UJJAIN / BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718/RC/22012034195766 — Gravel Road Nirman Namalpur to Ranwa (Orignal | Completed | 1759000 | 144938.6 | 2013-01-19 | 2016-06-22
UJJAIN / BADNAGAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1718/RC/22012034197742 — Gravel Road Nirman Namalpur To Ranwa (Orignal | Deleted | 1759000 | 0 | 2012-04-01
UJJAIN / BADNAGAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1718/RC/8087172नाम — ग्रेवल रोड निर्माण नामलपुर से रणवा | Completed | 3057000 | 378195.94 | 2010-07-30 | 2016-06-22