## Work List
Exported on: 2026-10-22 11:02:38
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MOLYAKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1719002015/IF/22012035378625 — JGSA 2025 डग वेल रिचार्ज पीट प्रभुलाल / रामप्रसाद कूप ग्राम मोल्याखेड़ी | Ongoing | 25899.46 | 0 | 2025-06-16
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719002015/IF/22012035536840 — JGSA खेत तालाब कालुराम / रामचंद्र मोल्याखेड़ी | Approved | 450885.64 | 0 | 2025-04-14
AGAR-MALWA / NALKHEDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4154305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103439770 | Ongoing | 27000 | 0 | 2022-08-27
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4520435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113659141 | Ongoing | 27000 | 0 | 2025-02-04
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4520767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116034878 | Ongoing | 27000 | 0 | 2025-01-21
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4520768 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116035533 | Completed | 23490 | 0 | 2024-11-04 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4520870 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115219247 | Ongoing | 27000 | 0 | 2025-01-21
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4523350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118290141 | Completed | 23490 | 0 | 2024-09-20 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4528959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142990213 | Ongoing | 27000 | 0 | 2024-10-18
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4571499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117332988 | Completed | 27000 | 0 | 2025-01-21 | 2026-10-11
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4578403 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118290487 | Completed | 23490 | 0 | 2025-01-21 | 2026-10-11
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4697708 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117493794 | Ongoing | 27000 | 0 | 2025-01-16
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/4756096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117636457 | Ongoing | 27000 | 0 | 2024-12-16
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5113124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118102344 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5113409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118102645 | Completed | 23490 | 0 | 2025-04-15 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5114167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118102877 | Ongoing | 27000 | 0 | 2025-04-15
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5114242 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118795801 | Ongoing | 27000 | 0 | 2025-08-23
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5114267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124467424 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5114273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124469456 | Physically Completed | 23490 | 0 | 2025-09-17 | 2026-07-12
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5116286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117493704 | Ongoing | 27000 | 0 | 2025-10-29
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5118006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106455843 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5118550 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124470761 | Ongoing | 27000 | 7200 | 2026-01-28
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5118551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124471809 | Physically Completed | 23490 | 0 | 2025-07-17 | 2026-07-12
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5119429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113659391 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5119430 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113659430 | Ongoing | 27000 | 0 | 2025-03-26
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5120073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115219227 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5120074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115219319 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5120075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115219340 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5121361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113659259 | Physically Completed | 23490 | 0 | 2025-07-17 | 2026-08-16
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5121649 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150096116 | Ongoing | 27000 | 0 | 2025-03-26
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5121650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150096154 | Ongoing | 27000 | 0 | 2025-03-26
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5122016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117619124 | Completed | 23490 | 0 | 2025-04-15 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5123271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127171936 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5123484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118256132 | Completed | 23490 | 0 | 2025-07-17 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5129933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117814489 | Ongoing | 27000 | 9000 | 2026-01-28
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5129934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117814503 | Physically Completed | 23490 | 0 | 2025-09-17 | 2026-08-16
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5130564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117332971 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5130565 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117333028 | Ongoing | 27000 | 0 | 2025-08-23
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5131415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127167081 | Ongoing | 27000 | 0 | 2025-03-26
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5133706 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116035605 | Physically Completed | 23490 | 0 | 2025-07-17 | 2026-08-09
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5133941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118256382 | Completed | 23490 | 0 | 2025-08-23 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5239298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115219135 | Ongoing | 27000 | 0 | 2025-07-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5460884 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117814408 | Completed | 23490 | 0 | 2025-07-17 | 2026-08-17
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5545081 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113659337 | Physically Completed | 23490 | 0 | 2025-07-17 | 2026-08-09
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5548396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116288175 | Physically Completed | 23490 | 0 | 2025-07-17 | 2026-08-16
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5682577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117333062 | Ongoing | 27000 | 3600 | 2025-08-23
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5707802 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113659297 | Completed | 27000 | 10800 | 2025-08-23 | 2026-10-11
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5935709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118295611 | Ongoing | 27000 | 10800 | 2026-05-20
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5936003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118256333 | Ongoing | 27000 | 0 | 2026-09-05
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5937205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118333367 | Ongoing | 27000 | 16200 | 2026-07-11
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5937599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113658944 | Ongoing | 27000 | 16200 | 2026-07-11
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5937940 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117618064 | Ongoing | 27000 | 16200 | 2026-07-11
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5940723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118272237 | Ongoing | 27000 | 0 | 2026-09-20
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5940840 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116288278 | Ongoing | 27000 | 0 | 2026-09-05
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5942309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115219100 | Ongoing | 27000 | 0 | 2026-09-05
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5950446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118279264 | Ongoing | 27000 | 0 | 2026-09-20
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5956512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118256315 | Ongoing | 27000 | 0 | 2026-09-05
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5956513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118256357 | Approved | 27000 | 0 | 2026-02-20
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5959163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116288311 | Ongoing | 27000 | 0 | 2026-07-10
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5959491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117494239 | Ongoing | 27000 | 16200 | 2026-07-11
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5962460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117494093 | Ongoing | 27000 | 0 | 2026-09-05
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5966063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123187298 | Ongoing | 27000 | 0 | 2026-07-11
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/5966080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117617466 | Ongoing | 27000 | 16800 | 2026-07-10
AGAR-MALWA / NALKHEDA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/6052968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116035568 | Ongoing | 27000 | 0 | 2026-09-05
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/6335866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117493990 | Approved | 27000 | 0 | 2026-02-18
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002015/IF/IAY/6336159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118256298 | Approved | 27000 | 0 | 2026-02-10
AGAR-MALWA / NALKHEDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719002015/RC/22012034838744 — सीसी रोड निर्माण कार्य बालचंद के घर से हेमराज के घर तक मोल्याखेडी | Approved | 40000 | 0 | 2025-01-26
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1719002015/WC/22012035260455 — JGJS परकोलेशन टेंक निर्मान कार्य शासकिय बल्डे पर मोल्याखेडी | Approved | 199984.05 | 0 | 2025-04-01
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1719002015/WC/22012035260457 — JGJS डाईक निर्माण प्रेमनारायण के खेत के पास मोल्याखेड़ी | Approved | 33496.31 | 0 | 2025-04-01
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1719002015/WC/22012035275295 — JGSA 2025 डग वेल रिचार्ज पीट सार्वजनिक कूप ग्राम मोल्याखेड़ी | Physically Completed | 25899.46 | 0 | 2025-06-16 | 2026-10-08