## Work List
Exported on: 2026-10-07 16:05:21
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: SUIGAON
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
AGAR-MALWA / NALKHEDA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719002026/DP/22012034236894 — शांती धाम निर्माण सुईगांव | Physically Completed | 180000 | 159212 | 2016-12-26 | 2022-01-04
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035361737 — खेत तालाब निर्मान भिमसिंह उंकार सिंह सुईगांव | Physically Completed | 147621.16 | 138508.34 | 2025-04-22 | 2026-04-22
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035361754 — खेत तालाब निर्माण कार्य गोविंद भगवान सिंह सुईगांव | Physically Completed | 147621.16 | 129039.36 | 2025-04-22 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719002026/IF/22012035423737 — JGSA 2025 डग वेल रिचार्ज पीट बालुसिंह शिवसिंह सुईगांव | Physically Completed | 24899.46 | 24575.18 | 2025-05-15 | 2026-04-16
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719002026/IF/22012035516526 — JGSA खेत तालाब निर्माण अशोककुमार रामेश्वर सुईगांव | Physically Completed | 55865.38 | 51715.16 | 2025-06-17 | 2026-09-16
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035520043 — GJSA खेत तालाब निर्माण बाबुलाल करणसिंह यादव सुईगांव | Physically Completed | 55865.38 | 54806.2 | 2025-06-01 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035535703 — JGSA खेत तालाब निर्माण रुख्मा बाई मोतीसिंह सुईगांव | Physically Completed | 55865.38 | 54804.64 | 2025-06-19 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035543239 — JGSA खेत तालाब निर्माण मांगीलाल रतनलाल सुईगांव | Physically Completed | 147621.16 | 118390.44 | 2025-06-16 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035555613 — JGSA खेत तालाब निर्माण भेरूसिंह भंवरजी सुईगांव | Physically Completed | 147621.16 | 138869.58 | 2025-06-07 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035555625 — JGSA खेत तालाब निर्माण प्रहलादसिंह कल्याणसिंहं सुईगांव | Physically Completed | 147621.16 | 137043.42 | 2025-06-08 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035555630 — JGSA खेत तालाब निर्माण कमल नारायणसिंह सुईगांव | Physically Completed | 147621.16 | 138868.68 | 2025-06-07 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035564786 — JGSA खेत तालाब निर्माण जयनारायण कंवरलाल सुईगांव | Physically Completed | 147621.16 | 138869.16 | 2025-06-21 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002026/IF/22012035567348 — JGSA खेत तालाब निर्माण गोकुूलसिंह उमरावसिंह सुईगांव | Physically Completed | 147621.16 | 127908.3 | 2025-06-21 | 2026-04-29
AGAR-MALWA / NALKHEDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/4325411 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106406086 | Physically Completed | 18360 | 204 | 2022-11-18 | 2024-11-21
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4543733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106272453 | Physically Completed | 23490 | 21825 | 2025-01-08 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4548908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106405994 | Physically Completed | 23490 | 22149 | 2025-01-08 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4556677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114030552 | Physically Completed | 23490 | 22473 | 2025-01-25 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4580414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118539533 | Physically Completed | 23490 | 21825 | 2025-02-01 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4597682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122580027 | Physically Completed | 23490 | 21060 | 2025-02-01 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4602841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124219781 | Physically Completed | 23490 | 21933 | 2025-01-08 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4604394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124280530 | Physically Completed | 23490 | 21717 | 2025-02-01 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/4605145 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123601381 | Physically Completed | 23490 | 21060 | 2025-02-01 | 2026-02-06
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/4610147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124543323 | Physically Completed | 23490 | 21060 | 2025-02-01 | 2026-02-06
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4624480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126687400 | Physically Completed | 23490 | 21717 | 2025-02-01 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4666742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151394393 | Physically Completed | 23490 | 22041 | 2025-01-25 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4725739 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149567631 | Physically Completed | 23490 | 22257 | 2025-01-25 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4848033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114031132 | Physically Completed | 23490 | 21825 | 2025-01-25 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4848720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124546883 | Physically Completed | 23490 | 21825 | 2025-01-25 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4850067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125598158 | Physically Completed | 23490 | 22149 | 2025-02-01 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/4865983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124536312 | Physically Completed | 23490 | 21376 | 2025-01-25 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/4940162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114030478 | Physically Completed | 23490 | 19275 | 2025-03-25 | 2026-02-06
AGAR-MALWA / NALKHEDA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/4953791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120078406 | Physically Completed | 23490 | 20007 | 2025-03-25 | 2026-02-13
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5161662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126483729 | Physically Completed | 23490 | 21924 | 2025-04-24 | 2026-02-13
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5175281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126091016 | Physically Completed | 23490 | 21924 | 2025-08-01 | 2026-04-05
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5188635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115823496 | Physically Completed | 23490 | 21924 | 2025-04-24 | 2026-04-19
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5200810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122576102 | Physically Completed | 23490 | 21924 | 2025-04-24 | 2026-04-05
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5201028 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115823373 | Physically Completed | 23490 | 20358 | 2025-04-24 | 2026-02-06
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5206855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124219262 | Physically Completed | 23490 | 20358 | 2025-04-24 | 2026-04-05
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5207650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122575463 | Physically Completed | 23490 | 20358 | 2025-04-24 | 2026-04-19
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/5242250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124298771 | Physically Completed | 23490 | 23229 | 2025-04-24 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/5457724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115823622 | Physically Completed | 23490 | 21924 | 2025-12-02 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5457976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124838925 | Physically Completed | 23490 | 21924 | 2025-08-01 | 2026-02-13
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5463049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114687064 | Physically Completed | 23490 | 20358 | 2025-08-01 | 2026-02-06
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5463442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115822661 | Physically Completed | 23490 | 21924 | 2025-09-18 | 2026-02-06
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5828682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126068333 | Physically Completed | 23490 | 21924 | 2025-10-28 | 2026-04-05
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002026/IF/IAY/5829190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118683382 | Physically Completed | 23490 | 21924 | 2025-10-28 | 2026-04-05
AGAR-MALWA / NALKHEDA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719002026/IF/IAY/5829615 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119891843 | Physically Completed | 23490 | 21924 | 2025-10-28 | 2026-08-20
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719002026/RC/22012034333582 — सुदूर ग्राम सम्‍पर्क, छोटा गोवा, सुईगांव 451 | Physically Completed | 438000 | 427362.75 | 2017-05-08 | 2022-01-04
AGAR-MALWA / NALKHEDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719002026/RC/22012034620104 — सीसी रोड नाली निर्माण केशु सोनी के घर से मांगुसिंह के मकान तक सुईगाव | Physically Completed | 37033 | 36744 | 2024-09-01 | 2026-09-16
AGAR-MALWA / NALKHEDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002026/RC/22012034837650 — सीसी रोड निर्माण कार्य महेश के घर से शमशान तक सुईगांव | Physically Completed | 70000 | 69687 | 2025-04-24 | 2026-06-23
AGAR-MALWA / NALKHEDA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002026/RC/22012034837655 — सीसी रोड निर्माण कार्य मैन रोड से महेश के घर तक सुईगांव | Physically Completed | 35000 | 34452 | 2025-05-08 | 2026-04-16