## Work List
Exported on: 2026-09-14 15:53:39
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BHANDAWAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
AGAR-MALWA / NALKHEDA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1719002044/AV/22012034504383 — खेल मैदान निर्माण गोयल रोड पर गाव के मध्य मे भण्डावद | Closed | 0 | 0 | 2019-04-14
AGAR-MALWA / NALKHEDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1719002044/AV/22012034512104 — गौशाला निर्माण भण्डावद | Closed | 0 | 0 | 2020-04-14
AGAR-MALWA / NALKHEDA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1719002044/AV/22012034514307 — पुलिया निर्माण आदिवासी मोहल्ला शिव मंदिर के पास भण्डावद | Completed | 85315 | 78660 | 2020-07-24 | 2021-05-30
AGAR-MALWA / NALKHEDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Goat Shelter for Community / Construction of Goat Shelter for Community | Goat Shelter | 1719002044/AV/22012034516337 — गौशाला निर्माण भंडावद | Completed | 3784582.21 | 3604924.32 | 2020-09-21 | 2023-06-23
AGAR-MALWA / NALKHEDA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Repair & Maint of Clvert/cross drainage work-Comm / Repair and Maintenance of Culvert / cross drainage structues for Community | Repair & Maint of Community infrastructure | 1719002044/AV/22012034546273 — पुलिया निर्माण छापीहेडा रोड पर पर्वत के खेत के पास भंडावद | Completed | 55000 | 52630 | 2021-01-04 | 2021-08-12
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Eco Restoration of Forest / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/22012034229713 — Shanti Dham Bhandawad | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1719002044/DP/22012034455501 — JSA नवीन सामुदायिक वृक्षारोपण हनुमान मंदिर परिसर भण्डावद | Ongoing | 373989.79 | 110014 | 2019-08-24
AGAR-MALWA / NALKHEDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation-Horticulture - Community / Canal Line Plantation of Horticulture Trees for Community | Plantation | 1719002044/DP/22012034555900 — मा कि बगिया हाई स्कुल शाला भवन परिसर भंडावद | Closed | 13132 | 0 | 2022-04-14
AGAR-MALWA / NALKHEDA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719002044/DP/22012034572968 — सार्वजनिक कुप निर्माण नवीन गौशाला के पास भंडावद | Completed | 482219.91 | 426613 | 2022-12-29 | 2026-05-08
AGAR-MALWA / NALKHEDA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719002044/DP/22012034573698 — सार्वजनिक कूप निर्माण आदिवासी मोहल्ला भंडावद | Completed | 541117.48 | 358220.29 | 2023-04-25 | 2026-05-20
AGAR-MALWA / NALKHEDA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1719002044/DP/22012034599773 — वसुधा वंदन अंतर्गत वृक्षारोपण कार्य हनुमान मंदिर परिसर भंडावद | Ongoing | 55847.4 | 6452 | 2023-09-23
AGAR-MALWA / NALKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/नन्‍दन फलोदयान/नजीम/इबरारशाह भण्‍डाव — नन्‍दन फलोदयान/नजीम/इबरारशाह भण्‍डावद | Completed | 190627 | 20558 | 2008-08-01 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/नन्‍दन फलोदयान/नसीर/युसूफशाह भण्‍डाव — नन्‍दन फलोदयान/नसीर/युसूफशाह भण्‍डावद | Completed | 190627 | 1914 | 2008-08-01 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/नन्‍दन फलोदयान/राधेश्‍याम/प्रभूलाल भ — नन्‍दन फलोदयान/राधेश्‍याम/प्रभूलाल भण्‍डावद | Completed | 190627 | 864 | 2008-08-10 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/नन्‍दन फलोदयान/रामप्रसाद/रायसि‍ह भण् — नन्‍दन फलोदयान/रामप्रसाद/रायसि‍ह भण्‍डावद | Completed | 190627 | 10264 | 2008-08-05 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/नन्‍दन फलोदयान/रोडमल/गुलाब भण्‍डावद — नन्‍दन फलोदयान/रोडमल/गुलाब भण्‍डावद | Completed | 190627 | 864 | 2008-08-07 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/नन्‍दन फलोदयान/र्नि‍भय/अमरसि‍हं भण्‍ — नन्‍दन फलोदयान/र्नि‍भय/अमरसि‍हं भण्‍डावद | Completed | 190627 | 864 | 2008-08-09 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719002044/DP/नन्‍दन फलोदयान/वि‍ष्‍णूप्रसाद/जगन्‍न — नन्‍दन फलोदयान/वि‍ष्‍णूप्रसाद/जगन्‍नाथ भण्‍डावद | Completed | 190627 | 1410 | 2008-08-01 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719002044/DW/185 — Sarvjanik Koop Nirman | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719002044/DW/22012034294103 — सार्वजनिक कूप निर्माण, हनुमान मंदिर के पास, भण्‍डावद 200 | Completed | 463000 | 448548.46 | 2017-01-29 | 2017-07-04
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719002044/DW/22012034294763 — Sarvjanik koop Banshitalai k pas bhamdawad | Closed | 0 | 0 | 2017-01-26
AGAR-MALWA / NALKHEDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Rural Drinking Water | Recharge Pits / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719002044/DW/89 — सार्वजनिक कूप निर्माण | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/1000001817 — कपिलधारा पूरा उदा | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/1000001818 — कपिलधारा कालूराम मांगीलाल | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/1000002469 — Koop-Kaluram-Mangilal | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/1000003004 — Koop-Bhagwansingh-Umraosingh | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719002044/IF/1000018089 — मेढ बधान 64 श्री विष्‍णु पिता कालुराम,भण्‍डावद | Completed | 47200 | 43088.66 | 2013-06-10 | 2013-12-19
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719002044/IF/1000023796 — Medh bandhan of shri Bapulal S/o Kanwarlal | Completed | 44000 | 42052.4 | 2013-07-04 | 2013-12-19
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719002044/IF/1000023800 — Medh Bandhan of Shri Prabhulal S/o ruggaji | Completed | 44000 | 42081.2 | 2013-07-04 | 2013-12-19
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719002044/IF/1000030884 — Med bandhan of shri umrav s/o kaluram | Completed | 41800 | 39532.5 | 2013-08-13 | 2013-12-19
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/1000063503 — Balchand s/o Udaji, Bhandawad (99) | Deleted | 35999 | 0 | 2013-04-14
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/1000063510 — Gyarsibai w/o Bapulal, Bhandawad (84) | Deleted | 36510 | 0 | 2013-04-14
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/1000065768 — Meharban singh s/o Umravsingh, Med Bandhan, Bhanda | Deleted | 0 | 0 | 2013-04-14
AGAR-MALWA / NALKHEDA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/2169 — मेड बंधान शमशादबी लालखां भण्‍डावद | Completed | 345000 | 30652 | 2011-12-21 | 2012-02-24
AGAR-MALWA / NALKHEDA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/2170 — मेड बंधान लालु पुरा भण्‍डावद | Completed | 460000 | 36050 | 2011-12-14 | 2012-01-06
AGAR-MALWA / NALKHEDA | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/2171 — मेड बंधान भगवानसिंह उमरावसिंह भण्‍डावद | Completed | 345000 | 33382 | 2012-01-02 | 2012-02-24
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034316932 — kapildhara koop Mohansingh S/O Dolat Singh | Closed | 0 | 0 | 2017-01-26
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034346224 — कुपनिर्माण सह खेततालाब जीवनसिंह सुनारसिंह भण्डावद | Completed | 230000 | 229496 | 2017-06-13 | 2019-07-02
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1719002044/IF/22012034348375 — व्रक्षारोपण हनुमार मन्दिर परिसर भण्डावद | Completed | 335000 | 76860 | 2017-06-13 | 2020-10-10
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1719002044/IF/22012034358746 — व्रक्षारोपण, हनुमान मन्दिर के पास, भण्डावद, भण्डावद | Completed | 335000 | 1032 | 2017-06-29 | 2020-10-10
AGAR-MALWA / NALKHEDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034411401 — नवीन कपिलधारा कूप निर्माण, कस्‍तुरीबाई-बद्रीलाल, भण्‍डावद | Completed | 210000 | 201460 | 2018-06-15 | 2022-11-29
AGAR-MALWA / NALKHEDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034411406 — नवीन कपिलधारा कूप निर्माण, महेन्‍द्रसिंह-चांदसिंह, भण्‍डावद | Completed | 210000 | 197140 | 2018-06-04 | 2020-07-20
AGAR-MALWA / NALKHEDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034471938 — कुपनिर्माण कालुसिंह भंवरसिंह भण्डावद | Completed | 210000 | 200956 | 2019-03-09 | 2020-12-16
AGAR-MALWA / NALKHEDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034472332 — कुपनिर्माण एलकारसिह रामनाथसिंह भण्डावद | Ongoing | 210000 | 28188 | 2019-03-10
AGAR-MALWA / NALKHEDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034474768 — कपिलधाराकूप- शकुंतलाबाई / शिवनारायण भण्‍डावद | Completed | 210000 | 201364 | 2019-03-10 | 2020-12-16
AGAR-MALWA / NALKHEDA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/22012034492349 — Kapil Dhara Koop Samudayik | Closed | 0 | 0 | 2019-01-26
AGAR-MALWA / NALKHEDA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1719002044/IF/22012034492385 — JSA नवीन सामुदायिक वृक्षारोपण हनुमान मंदिर परिसर भण्डावद | Deleted | 0 | 0 | 2019-04-14
AGAR-MALWA / NALKHEDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034666456 — कुपनिर्माण मोहनसिंह जगन्नाथ भण्डावद | Ongoing | 246126.86 | 129460 | 2021-03-16
AGAR-MALWA / NALKHEDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034666457 — कुपनिर्माण उमराव कालुराम भंडावद | Closed | 0 | 0 | 2020-08-15
AGAR-MALWA / NALKHEDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034666458 — कुपनिर्माण दिलीपसिंह छोटेलाल भण्डावद | Closed | 0 | 0 | 2020-08-15
AGAR-MALWA / NALKHEDA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/22012034666459 — कुपनिर्माण कालुराम बापुलाल भण्डावद | Closed | 0 | 0 | 2020-08-15
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832009 — नाडेप निर्माण रामनाथसिंह विक्रमसिंह भण्डावद | Closed | 22657.48 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832013 — नाडेप निर्माण गिरिराज पिरुलाल पाटीदार भण्डावद | Closed | 22657.48 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832017 — नाडेप निर्मान किशोर रामप्रसाद पाटीदार भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832020 — नाडेप निर्माण जगदिश भंवरलाल भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832022 — नाडेप निर्माण गंगाराम हरलाल भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832027 — नाडेप निर्माण बद्रिलाल हिरालाल भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832028 — नाडेप निर्माण शकुंतलाबाई शिवनारायन भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832032 — नाडेप निर्माण रमेश जगन्नाथ भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832033 — नाडेप निर्माण उदयसिंह मांगीलाल भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832036 — नाडेप निर्मान बल्लभ करणसिंह भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832038 — नाडेप निर्माण दौलतराम रामप्रसाद माली भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832039 — नाडेप निर्माण कैलाश विष्णु पाटीदार भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832043 — नाडेप निर्माण बाबुलाल मांगीलाल भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832045 — नाडेप निर्माण हरिसिंह मोकमसिंह भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832048 — नाडेप निर्माण रामेश्वर पन्नालाल भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832052 — नाडेप निर्माण सुरजसिंह उदयसिंह भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832054 — नाडेप निर्माण देविसिंह हजारीलाल भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832058 — नाडेप निर्माण घीसुलाल पुनालाल भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832061 — नाडेप निर्माण राजेंद्रा दिनेशचंद्र नागर भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832064 — नाडेप निर्माण कैलाश रामगोपाल भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832066 — नाडेप निर्माण रामबाबु प्रेमनारायण भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719002044/IF/22012034832069 — नाडेप निर्मान रोडमल पुनाजी भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719002044/IF/22012035523802 — JGSA डग वेल रिचार्ज पीट रामनाथ सिंह विक्रम सिंह भंडावद | Physically Completed | 25899.46 | 20412 | 2025-05-21 | 2026-05-15
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719002044/IF/22012035523807 — JGSA डग वेल रिचार्ज पीट ज़गदिश पाटिदार भंवरलाल पाटिदार् भण्डावद | Physically Completed | 25899.46 | 23544 | 2025-05-21 | 2026-04-15
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719002044/IF/2308 — निर्मल वाटीका देवकरण हरचन्‍द भण्‍डावद | Completed | 511500 | 4792 | 2012-05-02 | 2012-05-07
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/2318 — मेड बंधान पीरू भेरू भण्‍डावद | Completed | 359000 | 33032 | 2012-05-29 | 2012-05-31
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/2319 — मेड बंधान मानसिंह बापुलाल भण्‍डावद | Completed | 359000 | 33064 | 2012-05-29 | 2012-05-31
AGAR-MALWA / NALKHEDA | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/IF/2320 — मेड बंधान भागीरथ मांगीलाल भण्‍डावद | Completed | 359000 | 33062 | 2012-05-29 | 2012-05-31
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9926699489 — Amarsingh s/o Bhaggaji, Koopnirman, Bhandawad (162 | Completed | 228000 | 156749.57 | 2014-02-17 | 2015-03-25
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9926699503 — Kesarsingh s/o Ramnathsingh, Koopnirman, Bhandawad | Completed | 218000 | 154733.44 | 2014-02-17 | 2015-03-25
AGAR-MALWA / NALKHEDA | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9926699507 — Pura s/o Uda, Koop nirman, Bhandawad (161) | Completed | 228000 | 151054.8 | 2014-02-12 | 2015-03-25
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/9993685716 — IAY/Paribai/kishnlal | Completed | 14310 | 12149 | 2015-11-09 | 2017-05-05
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/9993685718 — IAY/Firojkhan/sharifkhan | Completed | 14310 | 11879 | 2015-11-09 | 2017-05-05
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/9993685721 — IAY/BHagawansingh/Umaravsingh | Completed | 14310 | 14787 | 2015-11-09 | 2017-05-05
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/9993685725 — IAY/vishnuparshad/Ramlal | Completed | 14310 | 11800 | 2015-11-09 | 2017-05-05
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9993699413 — kup nirman Parvatsingh / Bapusingh gram -bhandhwad | Completed | 271000 | 233159.7 | 2015-12-28 | 2017-02-03
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9993699415 — Kup Nirman Mohanlal / Ganpat gram -Bhandawad | Completed | 271000 | 238162.4 | 2015-12-28 | 2017-02-03
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9993699922 — Kup Nirman Gokul / Magngilal | Completed | 271000 | 233953.9 | 2015-12-28 | 2017-02-03
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9993699923 — Kup nirman Harisingh / Rugnathsing gram bhandawad | Completed | 271000 | 265459.3 | 2015-12-28 | 2016-07-27
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9993699926 — Kup Nirman Banesingh / Sujansingh gram - Bhandawad | Completed | 271000 | 258114.6 | 2015-12-28 | 2016-07-25
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/9993699929 — Kup Nirman Amarsingh / Runathsingh gram bhandawad | Completed | 271000 | 255068.5 | 2015-12-28 | 2016-07-25
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719002044/IF/9993725807 — medhbhandhan | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/1105677 — Construction of IAY House -IAY REG. NO. MP1396465 | Completed | 15480 | 15480 | 2017-09-04 | 2018-03-06
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/1124674 — Construction of IAY House -IAY REG. NO. MP2049594 | Completed | 15480 | 15480 | 2017-09-04 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/1145009 — Construction of IAY House -IAY REG. NO. MP1402065 | Completed | 15480 | 15480 | 2017-09-25 | 2018-03-06
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/1163130 — Construction of IAY House -IAY REG. NO. MP3878844 | Completed | 15480 | 15480 | 2017-09-25 | 2018-03-30
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/1163483 — Construction of IAY House -IAY REG. NO. MP3917298 | Completed | 15480 | 15390 | 2017-10-12 | 2018-07-16
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/125260 — Construction of IAY House -IAY REG. NO. MP-19-002-044-001/55 | Approved | 27000 | 0 | 2016-01-30
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/399937 — Construction of IAY House -IAY REG. NO. MP1211051 | Completed | 15030 | 15210 | 2017-02-08 | 2017-11-01
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/400717 — Construction of IAY House -IAY REG. NO. MP1212646 | Completed | 15030 | 13887 | 2017-03-21 | 2018-03-31
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/400935 — Construction of IAY House -IAY REG. NO. MP1213134 | Completed | 15030 | 14913 | 2017-03-21 | 2018-06-07
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/402091 — Construction of IAY House -IAY REG. NO. MP1217904 | Completed | 15030 | 15330 | 2017-03-21 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/407385 — Construction of IAY House -IAY REG. NO. MP1241207 | Completed | 15030 | 15210 | 2017-02-08 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/63095 — Construction of IAY House -IAY REG. NO. MP-19-002-044-001/183 | Approved | 27000 | 0 | 2015-12-28
AGAR-MALWA / NALKHEDA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/63099 — Construction of IAY House -IAY REG. NO. MP-19-002-044-001/257 | Approved | 27000 | 0 | 2015-12-28
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/644387 — Construction of IAY House -IAY REG. NO. MP1288509 | Completed | 15030 | 15450 | 2017-05-22 | 2018-02-17
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/730895 — Construction of IAY House -IAY REG. NO. MP1989112 | Completed | 15030 | 14448 | 2017-09-15 | 2018-03-30
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/732603 — Construction of IAY House -IAY REG. NO. MP2040594 | Completed | 15030 | 15426 | 2017-09-04 | 2018-07-29
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/733353 — Construction of IAY House -IAY REG. NO. MP2059648 | Completed | 15030 | 15480 | 2017-09-24 | 2018-03-06
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/733573 — Construction of IAY House -IAY REG. NO. MP2066006 | Completed | 15030 | 15366 | 2017-09-04 | 2018-07-16
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/752241 — Construction of IAY House -IAY REG. NO. MP2620397 | Completed | 15030 | 15366 | 2017-09-25 | 2018-05-23
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/752429 — Construction of IAY House -IAY REG. NO. MP2627478 | Completed | 15030 | 15480 | 2017-09-25 | 2018-03-06
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/752790 — Construction of IAY House -IAY REG. NO. MP2640480 | Completed | 15030 | 15390 | 2017-09-04 | 2018-11-11
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/752882 — Construction of IAY House -IAY REG. NO. MP2643727 | Completed | 15030 | 15480 | 2017-09-15 | 2018-01-10
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719002044/IF/IAY/817602 — Construction of IAY House -IAY REG. NO. MP2009433 | Completed | 15480 | 15480 | 2017-09-15 | 2018-03-06
AGAR-MALWA / NALKHEDA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/कूप निर्माण अहमदशाह हजरतशाह भण्‍डावद — कूप निर्माण अहमदशाह हजरतशाह भण्‍डावद | Completed | 107464 | 142142.98 | 2009-06-02 | 2010-06-10
AGAR-MALWA / NALKHEDA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/कूप निर्माण देवा बदद्वा भण्‍डावद — कूप निर्माण देवा बदद्वा भण्‍डावद | Completed | 107464 | 94399.22 | 2009-02-08 | 2010-03-31
AGAR-MALWA / NALKHEDA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/कूप निर्माण भवरलाल कालू भण्‍डावद — कूप निर्माण भवरलाल कालू भण्‍डावद | Completed | 107464 | 147023 | 2009-06-02 | 2010-06-10
AGAR-MALWA / NALKHEDA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/कूप निर्माण माधु उदा भण्‍डावद — कूप निर्माण माधु उदा भण्‍डावद | Completed | 107464 | 123680 | 2009-06-02 | 2010-11-25
AGAR-MALWA / NALKHEDA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/कूप निर्माण मानसिहं बापू भण्‍डावद — कूप निर्माण मानसिहं बापू भण्‍डावद | Completed | 107464 | 216443.72 | 2009-01-29 | 2010-04-14
AGAR-MALWA / NALKHEDA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/नवीन कुप निर्माण कार्य /गिरधारी /जग् — नवीन कुप निर्माण कार्य /गिरधारी /जग्‍गा भण्‍डावद | Completed | 107427.2 | 125661 | 2009-06-02 | 2011-03-22
AGAR-MALWA / NALKHEDA | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/नवीन कुप निर्माण कार्य /गिरधारी/ जग् — नवीन कुप निर्माण कार्य /गिरधारी/ जग्‍गा भण्‍डावद | Deleted | 0 | 0 | 2009-02-01
AGAR-MALWA / NALKHEDA | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719002044/IF/नवीन कुप निर्माण कार्य /पीरू/भेरू जी — नवीन कुप निर्माण कार्य /पीरू/भेरू जी /भण्‍डावद | Completed | 107427.2 | 115413 | 2009-06-02 | 2011-01-24
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034265770 — med bandhan antar bai goverdhan singh | Deleted | 0 | 0 | 2016-01-26
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034265772 — med bandhan prahalad singh kalyan singh | Deleted | 0 | 0 | 2016-01-26
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034265773 — Medhbandhan prhlad singh kalyan singh | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034265774 — Medhbandhan Narayan singh Dhulsiingh | Deleted | 0 | 0 | 2016-01-26
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034268088 — Medhbandhan Gopal Laxminarayan | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034268486 — Medbhandhan Ramkishan Gangaram | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034268487 — Medbhandhan Lal Singh Rugnath | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034268488 — Medbhandhan Ratanlal S/O Bapulal | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034268489 — Med BHandhan Rugnathbadera Devisingh | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034268490 — Medbandhan Ramchandra Badrilal Prajapati | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1719002044/LD/22012034268491 — Medbandhan Ratanlal So Hiralal Rathore | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719002044/LD/22012034525572 — चारागाह निर्माण गौशाला के पास भण्डावद | Ongoing | 1463732.51 | 27495 | 2020-12-14
AGAR-MALWA / NALKHEDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719002044/LD/237 — सामुदायिक शांतिधाम भण्‍डावद | Completed | 277000 | 207378 | 2012-09-01 | 2013-11-07
AGAR-MALWA / NALKHEDA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719002044/LD/245 — सामुदायिक खैल मैदान, 3104, भण्‍डावद | Completed | 393000 | 234564 | 2013-01-01 | 2014-01-09
AGAR-MALWA / NALKHEDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/107 — सामुदायिक सीसी रोड एवं नाली निर्माण, 1130, मनरेगा/पंच, भण्‍डावद | Completed | 158000 | 85436 | 2013-01-01 | 2013-03-29
AGAR-MALWA / NALKHEDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034155454 — CC Road | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034155455 — CC Road 2 | Deleted | 0 | 0 | 2012-12-17
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034185342 — CC Road | Completed | 95600 | 82200.34 | 2013-09-28 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034185346 — CC Road | Completed | 38000 | 33261.78 | 2013-09-27 | 2014-02-07
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034198717 — Cement Concrete Road, Bhandawad (273) | Completed | 109000 | 107222 | 2014-01-16 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034209487 — Khet Sadak, Bhandawad (284) | Completed | 1222300 | 1024852.06 | 2014-02-28 | 2017-05-05
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034222038 — CC Road | Deleted | 0 | 0 | 2014-04-01
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034222039 — CC Road | Deleted | 0 | 0 | 2014-04-01
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034228662 — Cement Concrete Road, PP, Bhandawad (38) | Completed | 103000 | 98279 | 2014-09-15 | 2015-07-16
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034267645 — सीसी रोड एवं नाली निर्माण, शासकीय ग्राम आबादी, गोयल 68 | Deleted | 0 | 0 | 2015-04-14
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034282772 — सीसी रोड, पीरूलाल राजपूत से प्रभुलाल के मकान तक, भण्‍डावद 67 | Completed | 102100 | 102030 | 2015-09-07 | 2016-06-12
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034297153 — CC Road Niali Nirman | Completed | 102000 | 102010 | 2016-01-25 | 2016-05-26
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034297154 — CC road nail nirman Vidhayak Nidhi | Completed | 15000 | 14310 | 2016-01-25 | 2016-05-12
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034304569 — CC ROAD | Deleted | 0 | 0 | 2015-10-02
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034304588 — CC ROAD | Deleted | 0 | 0 | 2016-01-26
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034306700 — CC Road Bhandawd | Deleted | 0 | 0 | 2016-01-21
AGAR-MALWA / NALKHEDA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034320711 — सीसी रोड धारासिंह के मकान से सुखराम के मकान तक | Completed | 114000 | 112836 | 2017-02-20 | 2019-08-16
AGAR-MALWA / NALKHEDA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719002044/RC/22012034332189 — सुदुर सम्पर्क सडक शेष कार्य ग्राम भण्डावद | Completed | 201000 | 199236.68 | 2017-03-21 | 2018-07-07
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034339274 — सीसी रोड नाली निर्माण जगदिश प्रजापती के मकान से राम किशन लोहार के मकान तक भंडावद | Completed | 56383 | 54696 | 2017-05-29 | 2019-09-13
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719002044/RC/22012034340233 — सुदुर सम्पर्क सडक भण्डावद जोड से बेरछाखेडी कांकड तक | Completed | 997465 | 929075.25 | 2017-06-05 | 2018-07-29
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034348670 — सीसी रोड नाली निर्माण बद्रीलाल राठौर के घर से याकुब खान के घर तक भण्डावद | Completed | 315135 | 294744 | 2017-08-10 | 2019-09-14
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034371592 — सीसी रोड नागर मोहल्ले से सुतार मोहल्ले तक भण्डावद | Closed | 0 | 0 | 2017-04-14
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034371593 — सीसी रोड बडी सेरी से रमेश प्रजापति के घर तक भण्डावद | Closed | 0 | 0 | 2017-04-14
AGAR-MALWA / NALKHEDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034437595 — CC ROAD NALI NIRMAN | Closed | 0 | 0 | 2018-12-20
AGAR-MALWA / NALKHEDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034449923 — सीसी रोड हनुमान मंदिर से सामुदायिक भवन तक | Completed | 74970 | 72318 | 2019-03-09 | 2020-07-16
AGAR-MALWA / NALKHEDA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034470562 — सीसी रोड नलखेडा छापीहेडा मार्ग से हनुमान मंदिर तक | Completed | 90015 | 88704 | 2019-07-22 | 2020-07-16
AGAR-MALWA / NALKHEDA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034471058 — CC Road | Closed | 0 | 0 | 2019-01-26
AGAR-MALWA / NALKHEDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719002044/RC/22012034521251 — खेत सड़क गोयल रोड से लेकर पनाली काकड़ तक | Completed | 1048728.61 | 1021629.6 | 2020-07-10 | 2022-08-22
AGAR-MALWA / NALKHEDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719002044/RC/22012034542701 — खेत सड़क लाल जी सेन के खेत से गोविंद सिंह के खेत | Closed | 0 | 0 | 2020-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034559223 — CC ROAD, GRAM BHANDAWAD | Closed | 0 | 0 | 2021-04-15
AGAR-MALWA / NALKHEDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719002044/RC/22012034560630 — खेत सडक निर्माण देविसिंह भिल के खेत से गोकलसिंह के खेत तक भण्डावद | Completed | 1095912.13 | 1072826.32 | 2021-03-10 | 2022-08-18
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034576409 — सीसी रोड निर्माण शिव मंदिर से बाबुसिंह के घर तक भण्डावद | Completed | 55995 | 63840 | 2021-07-05 | 2021-12-15
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034588564 — सीसी रोड निर्माण कालु चौकीदार के मकान से रामप्रसाद भिल के मकान तक भण्डावद | Completed | 32805 | 31920 | 2021-10-25 | 2021-12-15
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034589906 — नाली निर्माण vss के सामने भण्डावद | Closed | 24600 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034606049 — CC ROAD BHANDAWAD | Closed | 0 | 0 | 2022-04-15
AGAR-MALWA / NALKHEDA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034610455 — नाली निर्माण नई आबादी भण्डावद | Completed | 67000 | 47808 | 2022-11-09 | 2022-12-19
AGAR-MALWA / NALKHEDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034660257 — सीसी रोड नाली निर्माण मांगीलाल रामलाल के मकान से गोविन्द सिंह हरिसिह के मकान तक भण्डावद | Completed | 101000 | 98566 | 2024-02-07 | 2024-11-06
AGAR-MALWA / NALKHEDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034660260 — नाली निर्माण कमलसिंह सुनारसिंह के मकान से नाला तक भण्डावद | Closed | 35400 | 0 | 2023-04-14
AGAR-MALWA / NALKHEDA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034661339 — नाली निर्माण कमल सिंह सुनार सिंह के मकान से मैन नाला तक भण्डावद | Completed | 43000 | 42432 | 2024-02-07 | 2024-11-06
AGAR-MALWA / NALKHEDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034827407 — सीसी रोड निर्माण कार्य सामुदायिक भवन परिसर भण्डावद | Approved | 24000 | 0 | 2024-08-14
AGAR-MALWA / NALKHEDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034827413 — सीसी रोड निर्माण कार्य नई आबादि शमशान परिसर भण्डावद | Completed | 91000 | 87235 | 2024-11-08 | 2026-02-05
AGAR-MALWA / NALKHEDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034827992 — सीसी रोड निर्माण कार्य नई आबादी शमशान परिसर भण्डावद | Completed | 24000 | 21868.04 | 2024-11-08 | 2026-02-05
AGAR-MALWA / NALKHEDA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/22012034836381 — सीसी रोड निर्माण कार्य राधेश्याम के मकान से श्याम गिरधारी के मकान तक भण्डावद | Approved | 124000 | 0 | 2025-02-07
AGAR-MALWA / NALKHEDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719002044/RC/48 — सीसी रोड एवं नाली निर्माण टीएस 88 भण्‍डावद | Completed | 54000 | 52096 | 2012-12-10 | 2013-01-08
AGAR-MALWA / NALKHEDA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719002044/RC/64 — सामुदायिक सीसी रोड एवं नाली निर्माण, 313 पंच/मनरेगा, भण्‍डावद | Completed | 144000 | 141320 | 2013-01-01 | 2013-02-18
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034184680 — Maryada Lal khan s/o hasan khan | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034191597 — Giriraj s/o Pirulal, Bhandawad (379/08) | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034193854 — Babulal s/o Mangilal 379 Bandawad | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034193864 — Laluram s/o pura Bhandawad | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034194332 — Sobhgsingh s/o Bhanwarsingh Jab kard 60 Bandawad | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034194347 — उसमानश्ााह /आयुब शाह भण्‍डावद जॉबकार्ड 44 भण्‍डावद | Deleted | 0 | 0 | 2013-04-14
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034194560 — Gopal s/o Laxminarayan, Bhandawad (379) | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034194564 — Jahedshah s/o Sultanshah, Bhandawad (379/1) | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034194569 — Jeevansingh s/o Sunarsingh, Bhandawad (379/2) | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034195142 — Usman Shah s/o Ayub Shah, Bhandawad (379/5) | Completed | 4400 | 4378 | 2014-01-27 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034195197 — Govindsingh s/o Goverdhansingh, Bhandawad (379/7) | Completed | 4400 | 4378 | 2014-02-03 | 2014-03-26
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034214659 — maryadha Manohar / Rugnath Bandhawadh OBC | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215167 — Maryada Jyotish s/o APL Bhandhawad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215171 — Maryadha Radheshyam s/o Motilal Bandawad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215189 — Maryada Yusufh s/o Jarin khan Bhandawad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215197 — Maryada Mohansingh s/o Dulsesingh Bhandawad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215200 — Maryada Nasir s/o Yusufshah Bhandavad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215203 — Maryada Kailash s/o Shivnarayan Bhandavad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215205 — Marayda Manohar s/o Govrdhansinngh | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215210 — Maraydah Narendrasingh s/o Motilal Bhandavad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034215212 — Maryada Kailash s/o Ratanlal Bhandavad | Completed | 4400 | 4378 | 2014-03-10 | 2014-03-31
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034254786 — Maryada,Rajendar,Dineshchand,bhandawad,215/01 | Completed | 5400 | 5393 | 2014-09-18 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034254792 — Maryada,mohansingh,bhanwarsingh,215/02 | Completed | 5400 | 5393 | 2014-09-12 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034254795 — maryada,chandsingh,bhanwarsingh,215/03 | Completed | 5400 | 5393 | 2014-09-12 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034254801 — Maryada,Giriraj,Ramnarayan,215/04 | Completed | 5400 | 5393 | 2014-09-12 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034254805 — Maryada,Ghansyam,Rughnath,215/05 | Completed | 5400 | 5393 | 2014-09-12 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034254809 — Maryada,Babulal,Ramlal,215,05 | Completed | 5400 | 5393 | 2014-09-12 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034259426 — Maryada, Saleem shah s/o Ahmad shah, Bhandawad (29 | Completed | 5400 | 5393 | 2014-09-18 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034259431 — Maryada, Jagdish s/o Ramchandra, Bhandawad (215) | Completed | 5400 | 5393 | 2014-09-12 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034259433 — Maryada, Ibrarshah s/o Hajratshah, Bhandawad (215) | Completed | 5400 | 5393 | 2014-09-18 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034259439 — Maryada, Yaakub khan s/o Jaleel khan, Bhandawad (2 | Completed | 5400 | 5393 | 2014-09-18 | 2015-03-13
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288257 — SBM, Bhawarlal s/o Jagga, Bhandawad 682 | Completed | 3120 | 954 | 2015-10-19 | 2016-07-27
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288268 — SBM Bhandawad Mohanlal S/O Mangu 682 | Completed | 3120 | 954 | 2015-10-19 | 2016-07-25
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288272 — SBM Badrilal S/O Motilal 682 Bha | Completed | 3120 | 954 | 2015-10-19 | 2016-07-25
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288277 — SBM Bhagirath S/O Mangilal | Deleted | 3120 | 0 | 2015-10-10
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288450 — Shouchalay Nirman Champalal / Shankarlal Gram Bhandawad ts 682 | Completed | 3120 | 954 | 2015-10-19 | 2016-07-27
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288455 — shouchalay Nirman Vishnu / Jagnnath Gram - Bhandawad Ts 682 | Completed | 3120 | 954 | 2015-10-19 | 2016-07-25
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288691 — shouchalay Nirman Motilal / Mangilal Gram Bhandvad ts 682 | Deleted | 3120 | 0 | 2015-10-10
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288694 — shouchalay Nirman Kaluram / Motilal Gram - Bhandavad | Completed | 3120 | 1908 | 2015-10-19 | 2016-07-27
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034288696 — shouchalay Niraman Amarsingh / Gangaram | Deleted | 3120 | 0 | 2015-10-10
AGAR-MALWA / NALKHEDA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034289626 — Shouchala Nirman Nagga s/o Mangilal Gram Bhandawad | Deleted | 3120 | 0 | 2015-10-19
AGAR-MALWA / NALKHEDA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034334257 — शौचालय निर्माण कमल बाबुलाल | Completed | 7400 | 7036 | 2017-03-21 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358123 — शौचालय निर्मान रामेशर पन्नालाल | Completed | 12000 | 10432 | 2017-07-12 | 2018-04-29
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358124 — शौचालय निर्मान अर्जुन कालुसिंघ् | Completed | 12000 | 11464 | 2017-07-12 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358125 — शौचालय निर्माण कैलाश रामलाल | Completed | 12000 | 11464 | 2017-07-12 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358126 — शौचालय निर्मान रामलाल सेवा | Completed | 12000 | 10432 | 2017-07-12 | 2018-04-29
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358269 — शौचालय निर्मान नारायन पर्वत | Completed | 12000 | 11464 | 2017-07-12 | 2019-06-05
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358270 — शौचालय निर्माण रामकन्या मोहन | Completed | 12000 | 10432 | 2017-08-28 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358271 — शौचालय निर्माण पिरुसिंह रुपसिंह | Completed | 12000 | 10432 | 2017-08-28 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358272 — शौचालय निर्मान कैलाश रामगोपाल | Completed | 12000 | 12496 | 2017-07-12 | 2017-11-25
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358274 — शौचालय निर्माण बापुलाल कंवरलाल | Completed | 12000 | 2064 | 2017-07-12 | 2020-08-06
AGAR-MALWA / NALKHEDA | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719002044/RS/22012034358276 — शौचालय निर्माण रामप्रसाद देविराम | Completed | 12000 | 10432 | 2017-07-12 | 2021-03-14
AGAR-MALWA / NALKHEDA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1719002044/RS/22012034501694 — सामुदायिक स्वच्छ्ता परिसर निर्माण भण्डावद | Completed | 45000 | 37620 | 2020-12-04 | 2021-12-15
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1719002044/RS/22012034534938 — सामुदायिक नाडेप सामुदायिक भवन के पास भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1719002044/RS/22012034534940 — सामुदायिक नाडेप गौशाला के पास भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1719002044/RS/22012034534941 — सामुदायिक नाडेप गौशाला के पास भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1719002044/RS/22012034534943 — सोखता गडडा शाला भवन हैण्डपम्प के पास भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1719002044/RS/22012034534944 — सोखता गडडा शाला भवन हैण्डपम्प के पास भण्डावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1719002044/RS/22012034540392 — सामुदायिक स्वच्छ्ता परिसर निर्माण नई आबादी भण्डावद | Completed | 45000 | 41040 | 2021-07-12 | 2022-02-28
AGAR-MALWA / NALKHEDA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719002044/WC/22012034357685 — बोरी बन्धान निर्मान गाव के पास नाला | Completed | 39360 | 5160 | 2017-10-24 | 2019-03-30
AGAR-MALWA / NALKHEDA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719002044/WC/22012034426908 — डग आउट पोण्ड निर्माण हनुमान मन्दिर के पास बल्डी पर भन्डावद | Completed | 297500 | 286056 | 2019-01-12 | 2019-09-14
AGAR-MALWA / NALKHEDA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719002044/WC/22012034545229 — डग पोंड पनाली कांकड़ के पास भण्डावद | Completed | 164629.38 | 142500 | 2020-05-13 | 2021-03-29
AGAR-MALWA / NALKHEDA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719002044/WC/22012034840962 — सोखता गड्डा हनुमान मन्दिर के हैंण्डपम्प के पास भंडावद | Closed | 0 | 0 | 2021-04-14
AGAR-MALWA / NALKHEDA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719002044/WC/22012034954253 — सोखता गड्डा हनुमान मंदिर टंकी के हैण्डपम्प के पास भण्डावद | Closed | 0 | 0 | 2022-04-14
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719002044/WC/22012035271139 — JGSA 2025 डग वेल रिचार्ज पीट सार्वजनिक कूप गौशाला के पास भंडावद | Physically Completed | 25899.46 | 22810.5 | 2025-05-02 | 2026-04-22
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719002044/WC/22012035271147 — JGSA 2025 डग वेल रिचार्ज पीट सार्वजनिक कूप भील मोहल्ला भंडावद | Physically Completed | 25899.46 | 14197.5 | 2025-05-02 | 2026-04-22
AGAR-MALWA / NALKHEDA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1719002044/WC/9993647639 — Samudayik Koop nirman, Bhandawad (171) | Completed | 426000 | 421431.6 | 2014-02-28 | 2016-07-25
AGAR-MALWA / NALKHEDA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719002044/WH/19962205 — बडा तालाब गोयल रोड जिर्णोद्वार भण्डावद | Completed | 807000 | 788322 | 2017-05-29 | 2019-09-14
AGAR-MALWA / NALKHEDA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719002044/WH/19962206 — छोटा तालाब गोयल रोड जिर्णोद्वार भण्डावद | Completed | 254000 | 235994 | 2017-05-29 | 2019-08-16
AGAR-MALWA / NALKHEDA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719002044/WH/22012034943420 — बड़ा तालाब जीर्णोद्धार भंडावद | Ongoing | 398029.6 | 210231 | 2025-05-02