## Work List
Exported on: 2026-09-10 20:33:23
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KUNKADI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHAJAPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719005005/AV/22012034562651 — Aangwadi Bhawan Boundarywall + Handpump Nirman gram Umriyataj | Ongoing | 180000 | 0 | 2021-03-19
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of distributary Canal for Community / Construction of distributary Canal for Community | Construction of Canal | 1719005005/IC/22012034891662 — c c road nirman men road se samsan tak | New | 0 | 0 | 2025-04-14
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035593955 — Ek Bagiya Maa ke Naam LEELA BAI | Approved | 270842.86 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035593958 — Ek Bagiya Maa ke Naam SOHAN BAI | Ongoing | 273087.53 | 0 | 2025-09-16
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035595464 — Ek Bagiya Maa ke Naam LEELA BAI GURJAR | Approved | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598267 — ek bagiya maa k naam KRISNA BAI GURJAR | Approved | 263510.03 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598276 — ek bagiya maa k naam JODKUNVAR BAI RAJPUT | Ongoing | 263510.03 | 0 | 2025-09-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598278 — ek bagiya maa k naam JAIKUNWAR BAI | Ongoing | 263510.03 | 300 | 2025-09-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598290 — ek bagiya maa k naam MAN KUNVAR BAI RAJPUT | Ongoing | 263510.03 | 12600 | 2025-09-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598295 — ek bagiya maa k naam TEJKUNWAR BAI RAJPUT | Ongoing | 263510.03 | 5400 | 2025-09-16
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598298 — ek bagiya maa k naam RUKHMA BAI | Ongoing | 263510.03 | 0 | 2025-09-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598304 — ek bagiya maa k naam BALI BAI | Approved | 263510.03 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598316 — ek bagiya maa k naam SUNITA BAI | Ongoing | 263510.03 | 0 | 2025-09-27
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598321 — ek bagiya maa k naam PEPU BAI RAJPOOT | Ongoing | 263510.03 | 0 | 2025-09-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598326 — ek bagiya maa k naam GYANU BAI | Ongoing | 263510.03 | 0 | 2025-09-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035598329 — ek bagiya maa k naam SONA BAI | Approved | 263510.03 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035617179 — EK BAGIYA MA KE NAAM REEN KUWAR | Ongoing | 266577.25 | 300 | 2025-09-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035620352 — EK BAGIYA MA KE NAAM JAIKUWAR BAI KUMER SINGH | Ongoing | 266577.25 | 0 | 2025-09-16
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035622064 — EK BAGIYA MAA KE NAM RINA BAI | New | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035635143 — Ek Bagiya Maa ke Naam Prembai/Bhawarsingh Kukdeshwar | Ongoing | 266578.64 | 1800 | 2025-10-28
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035635153 — Ek Bagiya Maa ke Naam Shyamubai/Narayansingh Kukdeshwar | Ongoing | 266578.64 | 0 | 2025-10-28
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035635162 — Ek Bagiya Maa ke Naam Bebubai/Gopalsingh Kunkadi | Ongoing | 266578.64 | 0 | 2025-10-28
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035635219 — Ek Bagiya Maa ke Naam Mamtabai/Radheshyam Umriyataj | Ongoing | 257158.61 | 0 | 2025-10-31
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035635226 — Ek Bagiya Maa ke Naam Baleebai/Kamalsingh Umriyataj | Approved | 263511.37 | 0 | 2025-10-02
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035635232 — Ek Bagiya Maa ke Naam Rinabai/Dinesh Malviya Kunkadi | Ongoing | 266578.64 | 0 | 2025-10-28
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005005/IF/22012035637157 — Ek Bagiya Maa ke Naam Gendubai Kukdeshwar | Ongoing | 263511.37 | 0 | 2025-10-31
SHAJAPUR / SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/3811839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118525302 | Approved | 27000 | 0 | 2022-05-02
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/4587149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119896236 | Physically Completed | 23490 | 0 | 2024-09-28 | 2026-07-19
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/4758585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119601855 | Physically Completed | 23490 | 0 | 2024-12-25 | 2026-08-09
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/4774929 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125824721 | Approved | 27000 | 0 | 2024-09-21
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/4807903 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145296549 | Completed | 23490 | 0 | 2024-12-11 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5412962 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119878854 | Ongoing | 27000 | 1827 | 2025-05-13
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5413112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125551170 | Ongoing | 27000 | 0 | 2025-08-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5413247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145293692 | Ongoing | 27000 | 0 | 2025-08-28
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5413395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121493301 | Ongoing | 27000 | 0 | 2025-09-26
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5413396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121493324 | Physically Completed | 23490 | 0 | 2025-06-20 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5413486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125861060 | Completed | 23490 | 0 | 2025-10-09 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5413688 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122011399 | Completed | 23490 | 0 | 2025-08-01 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5414058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125796593 | Physically Completed | 23490 | 0 | 2025-08-12 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5414060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125809627 | Physically Completed | 23490 | 0 | 2025-08-01 | 2026-08-23
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5414226 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126278671 | Completed | 23490 | 0 | 2025-08-01 | 2026-08-12
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5414777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125811812 | Physically Completed | 23490 | 0 | 2025-06-20 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5414889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122498386 | Ongoing | 27000 | 2100 | 2025-06-20
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5414947 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145295372 | Ongoing | 27000 | 0 | 2025-08-28
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5414948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145295630 | Completed | 23490 | 0 | 2025-10-20 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5415148 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125809180 | Physically Completed | 23490 | 0 | 2025-08-01 | 2026-07-26
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5415163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145261189 | Physically Completed | 23490 | 0 | 2025-08-01 | 2026-07-26
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5415299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119611881 | Completed | 23490 | 0 | 2025-09-11 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5415423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122012906 | Completed | 23490 | 0 | 2025-07-01 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5415424 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122014711 | Physically Completed | 23490 | 0 | 2025-06-20 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5415471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126252721 | Physically Completed | 23490 | 0 | 2025-08-01 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5416025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122497146 | Physically Completed | 23490 | 0 | 2025-09-26 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5416117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118553862 | Ongoing | 27000 | 0 | 2025-08-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5416461 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127465207 | Completed | 23490 | 0 | 2025-09-05 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5577447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125546035 | Physically Completed | 23490 | 0 | 2025-08-26 | 2026-08-23
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5631425 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145293198 | Physically Completed | 23490 | 0 | 2025-08-01 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5632057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119915661 | Physically Completed | 23490 | 0 | 2025-08-26 | 2026-08-09
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5692492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145295730 | Physically Completed | 23490 | 0 | 2025-09-26 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5692596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122497839 | Physically Completed | 23490 | 0 | 2026-05-12 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5692691 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120567492 | Ongoing | 27000 | 0 | 2025-09-26
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5692745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126662080 | Completed | 23490 | 0 | 2025-10-03 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5692780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113681477 | Physically Completed | 23490 | 0 | 2026-01-09 | 2026-08-09
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5712393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125546845 | Physically Completed | 23490 | 0 | 2026-02-12 | 2026-07-26
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5712579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126248781 | Ongoing | 27000 | 0 | 2026-05-22
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/5712780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121368823 | Completed | 23490 | 0 | 2025-09-26 | 2026-08-25
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005005/IF/IAY/70507 — Construction of IAY House -IAY REG. NO. MP-19-005-005-001/08 | Approved | 27000 | 0 | 2016-01-04
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719005005/LD/22012034954569 — c c road nirman men road se samsan tak | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005005/RC/22012034843371 — c c road nirman men road se samsan tak | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005005/WC/22012034549695 — Watar harveting pond kunkdi | Ongoing | 770165.35 | 0 | 2020-05-20
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005005/WC/22012035305058 — Amrit Sarovar Gram Umriyataj GP Kunkadi | Ongoing | 1601500.67 | 0 | 2025-05-30
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005005/WH/22012034939055 — talab jirnodhar nirman | New | 0 | 0 | 2023-04-14