## Work List
Exported on: 2026-09-05 09:37:04
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: BHADONI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHAJAPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Goat Shelter for Community / Construction of Goat Shelter for Community | Goat Shelter | 1719005020/AV/22012034516471 — Go shala nirman karya bhadoni | Closed | 0 | 0 | 2020-01-26
SHAJAPUR / SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719005020/DP/22012034440744 — samudyik kup nirman | Closed | 0 | 0 | 2019-01-26
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1719005020/DP/22012034541656 — Maa ki bagiya Middile school, Bhadoni | Closed | 8863.57 | 193 | 2022-02-03
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719005020/DP/22012034550503 — Maa ki bagiya School Jadmi, gp. bhadoni | Closed | 8863.57 | 1379 | 2022-03-25
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719005020/DP/22012034550504 — Maa ki bagiya School Jadmi, gp. bhadoni | Closed | 0 | 0 | 2022-01-16
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1719005020/DP/22012034587601 — Vasudha Vandan- Amrit Vatika (75) Gram Panchayat Bhadoni | Ongoing | 55847.4 | 3564 | 2023-12-15
SHAJAPUR / SHAJAPUR | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719005020/DP/2नंदनफलोदय — नंदनफलोदयान कार्य सोनार सिंह रतन सिंह | Deleted | 268000 | 2800 | 2009-05-18
SHAJAPUR / SHAJAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719005020/DP/3नंदनफलोदय — नंदनफलोदयान कार्य रामा जी पिता भेरा जी | Completed | 268000 | 7259 | 2008-08-10 | 2015-03-17
SHAJAPUR / SHAJAPUR | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719005020/DP/नंदन फलोधान बलदेव कालू भदोनी — नंदन फलोधान बलदेव कालू भदोनी | Deleted | 268500 | 0 | 2015-03-12
SHAJAPUR / SHAJAPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719005020/DP/नंदन फलोधान सोदानसिह रतनसिह भदोनी — नंदन फलोधान सोदानसिह रतनसिह भदोनी | Deleted | 268500 | 1664 | 2010-04-03
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719005020/DW/9993658730 — sarvjanik kup nirman jadmi | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719005020/DW/9993658731 — sarvajanik kup nirman jadmi | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719005020/DW/9993658733 — sarvjanik kup nirman jadmi | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719005020/DW/9993658734 — hitgrahi mulak kup nirman bhagwan singh jadmi | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/22012034310101 — Khet Talab + kup nirman Mangilal/kalu ji | Completed | 230000 | 248195 | 2017-01-06 | 2018-05-10
SHAJAPUR / SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/22012034364273 — वृक्षा रोपण सड़क किनारे- ग्राम जादमी(ब्लडी) | Completed | 335000 | 31295 | 2017-07-14 | 2023-09-16
SHAJAPUR / SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/22012034369674 — vraksharopan jadmi | Deleted | 335000 | 0 | 2017-04-14
SHAJAPUR / SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/22012034382211 — Kapildhara sah khet talab | Closed | 0 | 0 | 2018-04-01
SHAJAPUR / SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/22012034437256 — kapil dhara kup recharge pith ramchandra s/o/ sidhu ji | Closed | 210000 | 0 | 2018-08-15
SHAJAPUR / SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/22012034437596 — kapi dhara kup nirman kailash s/o gangaram bhadoni | Completed | 210000 | 114299 | 2018-10-06 | 2024-02-22
SHAJAPUR / SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/22012034456941 — Kup Nirman | Closed | 0 | 0 | 2019-01-26
SHAJAPUR / SHAJAPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/22012034531719 — kapildhara kup nirman | Closed | 0 | 0 | 2020-01-26
SHAJAPUR / SHAJAPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005020/IF/22012034557428 — Kup nirman karya jitendra s/o Nandram bhadoni | Completed | 242453.87 | 173542.52 | 2020-10-23 | 2024-02-22
SHAJAPUR / SHAJAPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719005020/IF/22012034560362 — ketal shed nirman karya dev bai /ramesh | Completed | 101273.16 | 94340.16 | 2020-09-18 | 2024-08-09
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005020/IF/22012035477454 — Dugwell Recharge pit jitendra / nandram | Approved | 0 | 0 | 2025-04-01
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005020/IF/22012035477504 — Dugwell Recharge pit onkar singh / rama ji | Approved | 0 | 0 | 2025-04-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005020/IF/22012035506691 — Khet talab nirman karya ramprashad / amra ji | Approved | 0 | 0 | 2025-04-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719005020/IF/22012035506745 — Khet talab nirman karya Teju lal / sidhu ji | Approved | 0 | 0 | 2025-04-01
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005020/IF/22012035506798 — Dugwell Recharge pit kup ke pass Arjun singh / Sodan singh bhadoni | Approved | 0 | 0 | 2025-04-01
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719005020/IF/22012035598192 — Ek Bagiya Maa Ke Naam BABLI BERAGI | Approved | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668238 — नंदन फलोउदान रामेश्‍वर पिता हरलाल | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668263 — नंदन फलोउदान प्रभुलाल पिता उमरावसिंह | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668265 — नंदन फलोउदान सिदुसिंह पिता भैरवसिंह | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668266 — नंदन फलोउदान हिरालाल पिता मोडसिंह | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668267 — नंदन फलोउदान दुलेसिंह पिता भंवरसिंह | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668269 — नंदन फलोउदान नारायणसिंह पिता उमरावसिंह | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668422 — नंदन फलोउदान भगवानदाश जानकदाश | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668423 — नंदन फलोउदान लोकेन्‍द्रदास नारायणदास | Deleted | 134800 | 0 | 2015-06-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668428 — नंदन फलोउदान रमेशलाल पिता मोतीलाल | Deleted | 134800 | 0 | 2015-06-29
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993668429 — नंदन फलोउदान विष्‍णुप्रसाद पिता हरलाल | Deleted | 134800 | 0 | 2015-06-29
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993679295 — nandan paloudhayan ramesh lal /motilal | Deleted | 0 | 0 | 2015-06-26
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005020/IF/9993679461 — nandan faloudiyan lokendra das /narayan das | Deleted | 0 | 0 | 2015-06-26
SHAJAPUR / SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/9993745779 — खातून बी/चाँद शाह इंद्राआवाश | Completed | 14310 | 11142 | 2016-06-10 | 2018-04-15
SHAJAPUR / SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/9993746376 — santosh s/o hajari lal indra awash nirman | Completed | 14310 | 14255 | 2016-06-10 | 2018-04-15
SHAJAPUR / SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/9993746379 — इंदिरा आवास निर्माण जुम्मे शाह पिता करिम शाह | Completed | 14310 | 14696 | 2016-07-01 | 2017-08-01
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/113390 — Construction of IAY House -IAY REG. NO. MP-19-005-020-002/016 | Closed | 14310 | 0 | 2016-01-15
SHAJAPUR / SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/1934000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4805453 | Completed | 15660 | 15660 | 2018-09-21 | 2019-01-17
SHAJAPUR / SHAJAPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/1934004 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4835705 | Completed | 15660 | 15660 | 2018-09-21 | 2019-01-17
SHAJAPUR / SHAJAPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/2133094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4838623 | Completed | 15840 | 15784 | 2019-07-25 | 2019-12-02
SHAJAPUR / SHAJAPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/2160557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5528651 | Completed | 15840 | 15840 | 2019-08-07 | 2019-11-05
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/36233 — Construction of IAY House -IAY REG. NO. MP-19-005-020-001/28 | Approved | 27000 | 0 | 2015-11-17
SHAJAPUR / SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/3796957 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107036905 | Completed | 18360 | 18360 | 2022-05-27 | 2023-09-27
SHAJAPUR / SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/3809758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117948387 | Completed | 18360 | 18360 | 2022-07-12 | 2022-11-21
SHAJAPUR / SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4061596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113702833 | Completed | 18360 | 18360 | 2022-05-27 | 2022-08-29
SHAJAPUR / SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4108573 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149141084 | Completed | 18360 | 18360 | 2022-07-23 | 2023-09-27
SHAJAPUR / SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4163399 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107075475 | Completed | 18360 | 18360 | 2022-07-23 | 2022-09-27
SHAJAPUR / SHAJAPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4226048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117948875 | Completed | 18360 | 17680 | 2022-07-11 | 2024-01-19
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4552732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113729753 | Completed | 23490 | 21519 | 2024-10-02 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4552741 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113730406 | Ongoing | 27000 | 20412 | 2024-10-11
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4569864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117064986 | Completed | 23490 | 21627 | 2024-10-18 | 2025-07-27
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4659470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149141138 | Completed | 21870 | 21627 | 2024-10-25 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/4742809 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113729211 | Ongoing | 27000 | 17010 | 2024-12-07
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5149865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125382852 | Completed | 23490 | 23490 | 2025-09-11 | 2025-11-17
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5156471 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113739160 | Ongoing | 27000 | 21924 | 2025-06-18
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5160435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147648931 | Completed | 23490 | 21924 | 2025-12-08 | 2026-06-13
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5165169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149141052 | Ongoing | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5168607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119312086 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5170792 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119310657 | Completed | 23490 | 22968 | 2025-06-18 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5170943 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125378855 | Physically Completed | 23490 | 14616 | 2025-12-08 | 2026-02-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5171813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143705474 | Completed | 23490 | 22185 | 2025-09-11 | 2026-06-13
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5172041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117948286 | Approved | 27000 | 0 | 2025-03-20
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5178363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117948144 | Completed | 23490 | 21924 | 2025-12-08 | 2026-06-13
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5184555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119311632 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5185473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113705530 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5188040 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119311382 | Completed | 23490 | 23229 | 2025-06-03 | 2025-11-27
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5189419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148225344 | Physically Completed | 23490 | 21402 | 2025-12-08 | 2026-02-03
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5191102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147648994 | Physically Completed | 23490 | 21924 | 2025-12-08 | 2026-01-23
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5192231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143705627 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5192361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106976138 | Completed | 23490 | 19836 | 2025-05-12 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5194021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119652683 | Ongoing | 27000 | 21402 | 2025-05-12
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5194297 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117949100 | Completed | 23490 | 23490 | 2025-08-27 | 2025-11-17
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5196344 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119310846 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5197524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117949167 | Ongoing | 27000 | 21402 | 2025-12-08
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5198020 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149141291 | Completed | 23490 | 21924 | 2025-05-12 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5202313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149141121 | Completed | 23490 | 23229 | 2025-04-28 | 2025-07-27
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5208085 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125378190 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5208944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118382211 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5217579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117948545 | Completed | 23490 | 23229 | 2025-04-28 | 2025-07-27
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5219272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125370904 | Completed | 23490 | 21663 | 2025-09-29 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5222168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118863942 | Physically Completed | 23490 | 18009 | 2025-12-08 | 2026-03-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5226019 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107072797 | Completed | 23490 | 22968 | 2025-06-18 | 2026-08-05
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5243492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143705452 | Physically Completed | 23490 | 18009 | 2025-10-08 | 2025-12-18
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5243955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113738418 | Completed | 23490 | 22968 | 2025-08-03 | 2026-06-13
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5244443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119312349 | Physically Completed | 23490 | 21924 | 2026-01-18 | 2026-03-22
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5254852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117949252 | Ongoing | 27000 | 0 | 2025-03-26
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5257952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119310416 | Ongoing | 27000 | 0 | 2025-03-20
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5266428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125367028 | Completed | 23490 | 21924 | 2025-06-03 | 2025-07-27
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5304359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113463810 | Completed | 23490 | 23229 | 2025-06-03 | 2025-11-27
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5341271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149141157 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5342099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149141166 | Approved | 27000 | 0 | 2025-03-17
SHAJAPUR / SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/541744 — Construction of IAY House -IAY REG. NO. MP3116230 | Completed | 15030 | 15384 | 2017-02-03 | 2018-06-14
SHAJAPUR / SHAJAPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/545096 — Construction of IAY House -IAY REG. NO. MP3215752 | Completed | 15030 | 14692 | 2017-02-03 | 2018-06-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5522619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143705432 | Ongoing | 27000 | 21924 | 2025-06-03
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5657335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117064997 | Physically Completed | 23490 | 21402 | 2025-07-19 | 2026-03-15
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5658621 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119311098 | Approved | 27000 | 0 | 2025-03-26
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5658623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119311885 | Ongoing | 27000 | 17226 | 2025-07-19
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5679366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113738894 | Approved | 27000 | 0 | 2025-06-05
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5712749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113744776 | Physically Completed | 23490 | 20370 | 2026-06-14 | 2026-08-09
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/5795274 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117948804 | Physically Completed | 23490 | 21924 | 2025-10-08 | 2026-03-22
SHAJAPUR / SHAJAPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/70519 — Construction of IAY House -IAY REG. NO. MP-19-005-020-002/71 | Approved | 27000 | 0 | 2016-01-04
SHAJAPUR / SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/782781 — Construction of IAY House -IAY REG. NO. MP1335552 | Completed | 15480 | 14976 | 2018-01-05 | 2018-07-02
SHAJAPUR / SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/782831 — Construction of IAY House -IAY REG. NO. MP1339002 | Completed | 15480 | 15088 | 2018-01-05 | 2018-06-27
SHAJAPUR / SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005020/IF/IAY/805261 — Construction of IAY House -IAY REG. NO. MP3400953 | Completed | 15480 | 15480 | 2017-11-17 | 2018-02-06
SHAJAPUR / SHAJAPUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/कपिलधारा कुप निर्माण कन्‍हैया शिवलाल — कपिलधारा कुप निर्माण कन्‍हैया शिवलाल भादोनी | Completed | 105200 | 118524.52 | 2008-05-05 | 2010-03-31
SHAJAPUR / SHAJAPUR | 2007-2008 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/कपिलधारा कुप निर्माण रमेश भागीरथ भदो — कपिलधारा कुप निर्माण रमेश भागीरथ भदोनी | Deleted | 0 | 0 | 2008-02-29
SHAJAPUR / SHAJAPUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/कपिलधारा कुप निर्माण लालाजी अमराजी भ — कपिलधारा कुप निर्माण लालाजी अमराजी भदोनी | Completed | 106000 | 96845 | 2008-05-19 | 2010-03-31
SHAJAPUR / SHAJAPUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719005020/IF/कपिलधारा कुप निर्माण शेर सिह नाथु सि — कपिलधारा कुप निर्माण शेर सिह नाथु सिह भदोनी | Completed | 106000 | 18620 | 2008-05-19 | 2016-03-19
SHAJAPUR / SHAJAPUR | 2008-2009 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005020/IF/कुप निर्माण रमेश भागीरथ भदोनी — कुप निर्माण रमेश भागीरथ भदोनी | Deleted | 23000 | 0 | 2008-04-01
SHAJAPUR / SHAJAPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005020/LD/22012034316427 — शांति धाम (समशान सेड) निर्माण कार्य जादमी | Completed | 183600 | 156186.67 | 2017-10-27 | 2018-07-19
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719005020/LD/22012034316428 — शांति धाम (समशान सेड) निर्माण कार्य भदौनी | Completed | 183600 | 182316.67 | 2017-09-08 | 2018-07-05
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719005020/LD/22012034951864 — C.C Road V holi vale bade se bheru maharaj ke tabutre Tak | Approved | 83602 | 0 | 2025-01-26
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719005020/LD/22012034951875 — C.C Road Nirman meharban ki ata chaki se bheru maharaj ke chabutare Tak | Approved | 132027 | 0 | 2025-01-26
SHAJAPUR / SHAJAPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005020/LD/नंदनफलोउदयान रामा भेरा भदोनी — नंदनफलोउदयान रामा भेरा भदोनी | Completed | 268000 | 1664 | 2010-04-03 | 2015-03-12
SHAJAPUR / SHAJAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005020/LD/भूमि सुधार मेढबंधान कार्य रमेश भागीर — भूमि सुधार मेढबंधान कार्य रमेश भागीरथ भदोनी | Completed | 23300 | 21657 | 2008-05-26 | 2010-12-20
SHAJAPUR / SHAJAPUR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005020/LD/मेढबंधान कार्य रमेश भागीरथ भदोनी — मेढबंधान कार्य रमेश भागीरथ भदोनी | Deleted | 0 | 0 | 2008-03-05
SHAJAPUR / SHAJAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719005020/LD/मेढबंधान भदोनी मानसिंह चम्‍पाजी — मेढबंधान भदोनी मानसिंह चम्‍पाजी | Completed | 31000 | 20934 | 2008-05-05 | 2010-12-20
SHAJAPUR / SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1719005020/PG/9425888182 — khel medan bhadoni | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1719005020/RC/13जीएसबी र — जीएसबी रोड निर्माण करेडी रोड से जादमी ग्राम तक भदोनी | Completed | 802000 | 772621.2 | 2008-08-04 | 2011-02-24
SHAJAPUR / SHAJAPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034172821 — पंच परमेश्‍वर एवं सीसी रोड एवं नाली निर्माण ग्राम | Completed | 98500 | 56940 | 2013-06-26 | 2013-08-15
SHAJAPUR / SHAJAPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034174812 — पंचपरमेश्‍वर सीसी रेाड एवं नाली निर्माण मस्जिद से | Completed | 168800 | 108950.1 | 2013-09-13 | 2014-03-13
SHAJAPUR / SHAJAPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034201696 — पंचपरमेश्‍वर सीसी मस्जिद से स्‍कूल तक जादमी | Deleted | 168800 | 0 | 2012-10-15
SHAJAPUR / SHAJAPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719005020/RC/22012034209444 — सुदुर ग्राम संपर्क बिहारी गुर्ज के खेत से बनु मसाब | Completed | 1170000 | 21024 | 2014-02-28 | 2016-11-30
SHAJAPUR / SHAJAPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034219530 — vishnu kemakan se sardar ke makan tak cc road avm | Deleted | 60200 | 0 | 2014-05-30
SHAJAPUR / SHAJAPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034219635 — ayyob khan ke makan se vakilsap kemakan takcc road | Deleted | 120500 | 0 | 2014-05-30
SHAJAPUR / SHAJAPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034221712 — CC ROAD BHADONI | Deleted | 0 | 0 | 2014-01-26
SHAJAPUR / SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034266308 — sitla mata mandir se laxminarayan ke makan tak ccroad nirman | Completed | 156000 | 153675 | 2015-06-15 | 2016-06-08
SHAJAPUR / SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034294143 — c.c road kalu ke makan se bhagwan ke makan tak | Completed | 86400 | 84064 | 2015-12-30 | 2017-12-11
SHAJAPUR / SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034304152 — c.c road nirman barwa | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034304155 — c.c road+Nali nirman Gani ke ghar se amra ke ghar tak | Ongoing | 173629 | 55451 | 2020-01-19
SHAJAPUR / SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034304165 — c.c. road ninman bloc jadmi | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034304168 — c.c. road nirman rashid kha ke makan se bakil shab ke makan tak | Deleted | 0 | 0 | 2015-10-02
SHAJAPUR / SHAJAPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034304171 — c.c. road nirman rashid kha ke makan se bakil shab ke makan tak | Completed | 58500 | 57210 | 2016-10-07 | 2017-08-31
SHAJAPUR / SHAJAPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034304246 — cc road nirman | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHAJAPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034439155 — cc roads nirman | Closed | 0 | 0 | 2019-01-26
SHAJAPUR / SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034658380 — C C Road Aur Nali Nirman Nirbhay Singh Ke Makan Se Rasid Khan Ke Makan Tak | Completed | 67063 | 42874 | 2023-10-06 | 2025-10-09
SHAJAPUR / SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034659141 — C C Road , Nali Nirman Dayaram Ke Makan Se Bhagirath Ke Makan Tak | Completed | 91682 | 83452 | 2023-10-06 | 2024-08-09
SHAJAPUR / SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034659161 — C C Road Aur Nali Nirman Yakub Ke Makan Se ishaq Ke Makan Tak | Completed | 32386 | 21540 | 2024-03-11 | 2025-10-09
SHAJAPUR / SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034681549 — C.C Road V Nali Nirman Gulab Singh Malviya Ke Makan Se Shakir Shah Ke Makan Tak Gram Jadmi | Ongoing | 93286 | 48206 | 2024-03-11
SHAJAPUR / SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034845858 — C.C Road Nirman meharban1 ki ata chaki se bheru maharaj ke chabutare Tak | Ongoing | 132027 | 8091 | 2025-08-03
SHAJAPUR / SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034845864 — C.C Road V holi vale bade1 se bheru maharaj ke tabutre Tak | Ongoing | 83602 | 0 | 2025-09-29
SHAJAPUR / SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005020/RC/22012034851371 — C.C Road Nirman Karya Lalakhedi Road Se Bhadoni Shamshan ghat ki or | Approved | 105987 | 0 | 2025-10-02
SHAJAPUR / SHAJAPUR | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719005020/RC/करेडी से गांव तक रोड निर्माण भदोनी — करेडी से गांव तक रोड निर्माण भदोनी | Deleted | 803000 | 0 | 2008-08-02
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034353787 — शौचालय की मरम्मत कार्य सोदान सिंह जादमी | Completed | 11600 | 10648 | 2017-07-28 | 2018-09-04
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034358869 — sochalay maram mat kary sitaram bhadoni | Completed | 11600 | 11480 | 2017-07-14 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034358960 — souchalay maramat nirman karya mod singh s/o piru ji gram bhadoni | Completed | 11600 | 11480 | 2017-07-14 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034358962 — suochalay maramat karya mojam khan jadmi | Completed | 11600 | 11480 | 2017-07-14 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034358965 — suochalay maramat karya hasina bi W/o naggu khan jadmi | Completed | 11600 | 10648 | 2017-07-21 | 2018-09-04
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034358970 — suochalay maramat karya ram lal s/o pura lal bhadoni | Completed | 11600 | 11480 | 2017-07-14 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360302 — शौचालय मरम्मत कार्य कमल पिता रामलाल भदोनी | Completed | 11600 | 11480 | 2017-07-21 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360303 — शौचालय मरम्मत कार्य राजेंद्र दास पिता मोहन दास भदोनी | Completed | 11600 | 11480 | 2017-07-21 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360304 — शौचालय मरम्मत कार्य रमेश पिता भगीरथ भदोनी | Completed | 11600 | 11480 | 2017-07-21 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360305 — शौचालय मरम्मत कार्य गोविंद दास पिता बलराम दास भदोनी | Completed | 11600 | 11480 | 2017-07-21 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360306 — शौचालय मरम्मत कार्य जलील खा पिता रशीद खा जादामी | Completed | 11600 | 11480 | 2017-07-21 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360307 — शौचालय मरम्मत कार्य अमर सिंह जादमी | Completed | 11600 | 10964 | 2017-07-21 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360308 — शौचालय मरम्मत कार्य बंशी लाल पिता गंगाराम जादमी | Completed | 11600 | 10964 | 2017-08-18 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034360517 — toilet repair work aishan shah s/o mangu shah gram- jadmi | Completed | 11600 | 11480 | 2017-07-21 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034361999 — souchalay marammat karya ghishu lal bhadoni | Completed | 11600 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362000 — शौचालय की मरम्मत काम कालुराम भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362001 — शौचालय की मरम्मत के काम भागवान दास भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362002 — शौचालय मरम्मत कार्य अंतर सिंह भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362003 — शौचालय की मरम्मत कार्य कैलाश पिता गंगाराम भदोनी | Completed | 11600 | 10964 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1719005020/RS/22012034362004 — शौचालय मरम्मत कार्य नारायण सिंह भदोनी | Completed | 11600 | 10648 | 2017-07-28 | 2019-01-10
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362005 — शौचालय की मरम्मत कार्य बाबू दास पिता बलराम दास भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362006 — शौचालय की मरम्मत का काम सरदार शाह पिता मोहम्मद शाह जादमी | Completed | 11600 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362007 — शौचालय की मरम्मत कार्य मेहबूब शाह पिता मोहम्मद शाह जादमी | Closed | 11500 | 0 | 2017-06-01
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362008 — शौचालय की मरम्मत कार्य जयराम पिता रामलाल जादमी | Completed | 11600 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362009 — शौचालय की मरम्मत कार्य कैलाश चौधरी पिता रामचंद्र जादमी | Completed | 11500 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362010 — शौचालय की मरम्मत कार्य मगु सिंह पिता भंवर सिंह जादमी | Completed | 11600 | 11480 | 2017-07-28 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362069 — शौचालय की मरम्मत कार्य पिता विक्रम सिंह पिता नारायण सिंह भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362070 — शौचालय की मरम्मत कार्य अंतर सिंह पिता करण सिंह भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362071 — शौचालय की मरम्मत कार्य हुकुम सिंह पिता नारायण सिंह भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Compost Pit for Individual / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1719005020/RS/22012034362072 — शौचालय की मरम्मत कार्य कैलाश दास पिता रामचंद्र दास | Completed | 11600 | 10648 | 2017-07-28 | 2019-01-10
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362073 — शौचालय की मरम्मत कार्य कमल पिता प्रहलाद भदोनी | Closed | 11500 | 0 | 2017-05-18
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362074 — शौचालय मरम्मत कार्य भगवान सिंह पिता बालाराम सिंह बारवा | Completed | 11600 | 11480 | 2017-07-28 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362080 — शौचालय की मरम्मत कार्य मान सिंह /गंगाराम भदोनी | Completed | 11600 | 11480 | 2017-07-28 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362081 — शौचालय की मरम्मत कार्य लाखनसिंह /गोपालसिंह भदोनी | Completed | 11600 | 10964 | 2017-08-18 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362082 — शौचालय की मरम्मत कार्य प्रेम सिंह /देवीसिंह भदोनी | Completed | 11600 | 10964 | 2017-07-28 | 2018-02-06
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034362083 — शौचालय मरम्मत कार्य भदोनी सोनारसिंह/पर्वत सिंह भदोनी | Closed | 11500 | 0 | 2017-05-18
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034363729 — शौचालय की मरम्मत कार्य - बेबी बी / अल्लाउद्दीन जादमी | Completed | 11600 | 9100 | 2017-08-18 | 2018-09-04
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034363730 — शौचालय की मरम्मत कार्य- दुलेसिंह / पुरालाल भदोनी | Completed | 11600 | 11480 | 2017-08-18 | 2018-01-27
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034363731 — शौचालय की मरम्मत कार्य-लाखन / समंदर -भदोनी | Completed | 11600 | 10964 | 2017-08-18 | 2018-02-06
SHAJAPUR / SHAJAPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719005020/RS/22012034363732 — शौचालय की मरम्मत कार्य- जगदीश चौधरी / गंगा राम जादमी | Completed | 11600 | 10964 | 2017-08-18 | 2017-12-07
SHAJAPUR / SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soakage Channel for Community / Construction of Soakage Channel for Community | Solid and Liquid Waste Management | 1719005020/RS/22012035113913 — Nali nirman Ramesh chandra prajapati se government nale tak | Ongoing | 19649 | 663 | 2023-10-06
SHAJAPUR / SHAJAPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719005020/WC/22012034423931 — talab nirman karya -kundal ka nala gram bhadoni | Completed | 534000 | 386019.9 | 2018-10-01 | 2021-11-20
SHAJAPUR / SHAJAPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034575596 — Talab nirman karya malakho gram bhadoni | Closed | 0 | 0 | 2020-01-26
SHAJAPUR / SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034579797 — Sokhta Gadda Nirmana Karya school ke pas Bhadoni | Completed | 14283.77 | 8909 | 2020-09-04 | 2024-03-05
SHAJAPUR / SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034579798 — Sokhta Gadda Nirmana Karya school ke pas Jadmi | Completed | 14283.77 | 6023 | 2020-09-04 | 2023-07-25
SHAJAPUR / SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034579799 — Sokhta Gadda Nirmana Karya Headpump ke pas Barwa | Completed | 14283.77 | 12413 | 2020-09-14 | 2021-12-31
SHAJAPUR / SHAJAPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/22012034598468 — chek dam nirman karya jhari ghata bhadoni | Closed | 0 | 0 | 2020-10-02
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722797 — Roof rain water harvesting primary school bhadoni | Closed | 0 | 0 | 2021-04-01
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722805 — Roof rain water harvesting middle school bhadoni | Completed | 32656.33 | 13124 | 2021-09-24 | 2024-01-23
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722806 — Roof rain water harvesting middle school bhadoni | Closed | 32116.99 | 0 | 2021-04-01
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722821 — Roof rain water harvesting panchayat bhavan bhadoni | Closed | 33555.23 | 0 | 2021-04-01
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722827 — Roof rain water harvesting anganwadi bhavan bhadoni | Completed | 32116.99 | 6799 | 2021-09-24 | 2024-01-23
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722833 — Roof rain water harvesting anganwadi bhavan jadmi | Completed | 32476.55 | 10393 | 2021-09-24 | 2024-03-05
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722834 — Roof rain water harvesting anganwadi bhavan jadmi | Closed | 0 | 0 | 2021-04-01
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719005020/WC/22012034722837 — Roof rain water harvesting primary school bhavan jadmi | Completed | 31757.45 | 12373 | 2021-09-24 | 2024-01-23
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/22012034804714 — chek dam nirman karya bhadoni | Completed | 57000 | 44882 | 2021-12-03 | 2024-03-05
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone contour Bund for Community / Construction of Stone contour Bund for Community | Construction of Bund | 1719005020/WC/22012034879647 — Talai nirman karya malakho bhadoni | Closed | 0 | 0 | 2021-10-02
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/22012034879669 — chek dam nirman karya jhari ghata 2 bhadoni | Closed | 0 | 0 | 2021-10-02
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/22012034880671 — chek dam nirman karya bhadoni nale par | Completed | 77565 | 62259 | 2021-12-05 | 2024-02-16
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034936975 — Head pump recharge pit nirmar dev mandir ke pas jadmi | Closed | 15140.3 | 0 | 2021-04-01
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034937155 — head pump richarge pit bhadoni | Closed | 15140.3 | 0 | 2021-04-01
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034937156 — head pump richarge pit bhadoni | Closed | 0 | 0 | 2021-04-01
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034937167 — richarge pit nirmankup par chandar bai gram barwa | Closed | 0 | 0 | 2022-04-01
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012034937170 — head pump richarge pit nirman dev mandir ke pas jadmi | Closed | 0 | 0 | 2022-04-01
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1719005020/WC/22012034995598 — Subsurface Dyke BARWA 1 GP BHADONI GWIMP | Closed | 0 | 0 | 2022-08-15
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1719005020/WC/22012034995602 — Subsurface Dyke 2 GP BHADONI GWIMP | Closed | 0 | 0 | 2022-08-15
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1719005020/WC/22012034995603 — Subsurface Dyke 2 GP BHADONI GWIMP | Closed | 0 | 0 | 2022-08-15
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/22012035192867 — Check dam nirman barwa karya raste par | Closed | 0 | 0 | 2024-01-26
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012035276980 — Dugwell Recharge pit kup ke pass jadmi | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012035277008 — Dugwell Recharge pit kup ke pass bhadoni | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719005020/WC/22012035277021 — Dugwell Recharge pit kup ke pass barwa | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHAJAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/32मदन सिंह — मदन सिंह पिता मोती सिंह कुप निर्माण कार्य ग्राम पंचायत भदोनी | Completed | 159000 | 100224.64 | 2009-03-07 | 2010-12-20
SHAJAPUR / SHAJAPUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/42गनीमो — कुप निर्माण कार्य गनीमो पिता अजमेरी भदोनी पंचायत भदोनी | Completed | 198000 | 190515.72 | 2011-05-21 | 2012-03-31
SHAJAPUR / SHAJAPUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/43गोपाल — कुप निर्माण कार्य गोपाल पिता कालुसिह भदोनी पंचायत भदोनी | Completed | 198000 | 187556.58 | 2011-05-21 | 2013-05-27
SHAJAPUR / SHAJAPUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Artificial Recharge of Well Through Sand Filter / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719005020/WC/44रामाजी — कुप निर्माण कार्य रामाजी पिता भेराजी भदोनी पंचायत | Completed | 198000 | 77032.6 | 2011-05-21 | 2016-11-30
SHAJAPUR / SHAJAPUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/45सोदानसिह — कुप निर्माण कार्य सोदानसिह पिता मोतीसिह भदोनी पंचायत भदोनी | Completed | 198000 | 202207 | 2011-05-23 | 2013-03-15
SHAJAPUR / SHAJAPUR | 2011-2012 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719005020/WC/48प्रहलाद — कुप निर्माण कार्य प्रहलाद पिता पुनमचन्‍द्र भदोनी प | Completed | 198000 | 112872.6 | 2011-11-14 | 2015-07-06
SHAJAPUR / SHAJAPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005020/WC/सार्वजनीक कुप निर्माण जादमी भदोनी — सार्वजनीक कुप निर्माण जादमी भदोनी | Completed | 315000 | 345563.76 | 2008-04-29 | 2015-07-06
SHAJAPUR / SHAJAPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719005020/WH/22012034908373 — Talab jirnodhar/ marammat kherkhedi road ke pass Gp Bhadoni | Ongoing | 463456.67 | 134833 | 2022-03-21
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1719005/WC/22012035169559 — Construction of Gully plug gram Bhadoni | New | 0 | 0 | 2024-01-26