## Work List
Exported on: 2026-10-13 11:13:05
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: LODIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1719005096/AV/22012034637733 — puliya nirman londiya motilal ke khet ke pas | Closed | 0 | 0 | 2023-04-14
SHAJAPUR / SHAJAPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Cyclone shelter for Community / Construction of Cyclone shelter for Community | Construction of Other Community Building/Assets | 1719005096/AV/22012034645276 — shamshan sed nirman pandukhora | Ongoing | 219266.88 | 663 | 2023-10-06
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1719005096/DP/22012034589045 — Vasudha Vandan- Amrit Vatika (75) Gram Panchayat Lodiya | Physically Completed | 55847.4 | 28537 | 2023-09-03 | 2026-06-17
SHAJAPUR / SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719005096/DP/22012034610032 — Samudayik kup nirman londiya | Ongoing | 649990.87 | 663 | 2023-10-06
SHAJAPUR / SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005096/IF/22012035122405 — kup nirman geebai | Closed | 274429.96 | 0 | 2023-10-06
SHAJAPUR / SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005096/IF/22012035122409 — kup nirman dakhibai bihari | Ongoing | 274429.96 | 1547 | 2024-03-13
SHAJAPUR / SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005096/IF/22012035122414 — kup nirman sabubai kelash | Closed | 274704.19 | 0 | 2023-04-14
SHAJAPUR / SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719005096/IF/22012035122416 — kup nirman dulesingh | Closed | 274429.96 | 0 | 2023-04-14
SHAJAPUR / SHAJAPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719005096/IF/22012035217199 — Cattle shed se Nirman Sundar Bhai Kailash Chand | Closed | 0 | 0 | 2024-01-26
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005096/IF/22012035372377 — jgsa2025 construction of recharge structure dhapubai | Physically Completed | 24099.46 | 18858.98 | 2025-05-07 | 2026-04-15
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005096/IF/22012035372433 — jgsa2025 construction of recharge structure ramesh | Physically Completed | 24099.46 | 19119.98 | 2025-05-06 | 2026-04-15
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005096/IF/22012035372477 — jgsa2025 construction of recharge structure kamlabai | Approved | 24099.46 | 0 | 2025-04-14
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005096/IF/22012035372520 — jgsa2025 construction of recharge structure harisingh | Physically Completed | 24099.46 | 19119.98 | 2025-05-06 | 2026-04-15
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719005096/IF/22012035372598 — jgsa2025 construction of recharge structure karan | Physically Completed | 24099.46 | 20685.98 | 2025-05-07 | 2026-04-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005096/IF/22012035593968 — Ek Bagiya Maa ke Naam DEV BAI JAT | New | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005096/IF/22012035593972 — Ek Bagiya Maa ke Naam SEEMA BAI GIRI | New | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005096/IF/22012035594854 — ek bagiya maa k naam dev bai jat | New | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005096/IF/22012035594855 — ek bagiya maa k naam dev bai jat | New | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005096/IF/22012035632612 — EK BAGIYA MA KE NAAM DEV BAI JAT | Approved | 263511.37 | 0 | 2025-10-02
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719005096/IF/22012035632615 — EK BAGIYA MA KE NAAM SEEMA BAI GIRI | Approved | 263511.37 | 0 | 2025-10-02
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4559946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115385977 | Ongoing | 23490 | 22356 | 2025-03-11
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4564974 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116406144 | Completed | 23490 | 21870 | 2024-12-03 | 2025-07-27
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4592064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121694945 | Completed | 23490 | 21870 | 2024-12-17 | 2026-04-15
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4699958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113926808 | Completed | 23490 | 21870 | 2024-12-03 | 2026-04-15
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4701906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106311885 | Completed | 23490 | 21870 | 2024-12-03 | 2026-04-15
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4710387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123372641 | Ongoing | 23490 | 23229 | 2026-01-24
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4739150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106311679 | Completed | 23490 | 21870 | 2024-11-23 | 2025-10-24
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4743585 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113926592 | Ongoing | 21870 | 21870 | 2024-12-03
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4744030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106349083 | Ongoing | 23490 | 21888 | 2024-12-06
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4847018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106311834 | Ongoing | 23490 | 21870 | 2025-01-03
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/4850259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123401963 | Completed | 23490 | 21870 | 2024-12-03 | 2025-07-27
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5823153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123370347 | Physically Completed | 23490 | 23490 | 2025-10-07 | 2026-01-16
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5823594 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130365786 | Completed | 23490 | 23490 | 2025-10-07 | 2026-02-03
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5823828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123369561 | Ongoing | 23490 | 23490 | 2025-10-07
SHAJAPUR / SHAJAPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5826357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113924968 | Approved | 23490 | 0 | 2025-03-04
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5828118 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106311791 | Physically Completed | 23490 | 23490 | 2025-10-07 | 2026-05-10
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5828211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106312022 | Physically Completed | 23490 | 23490 | 2025-10-07 | 2026-05-10
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5828371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123371705 | Physically Completed | 23490 | 21924 | 2025-10-07 | 2026-03-22
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5843589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123399905 | Physically Completed | 23490 | 21924 | 2025-11-04 | 2026-03-22
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5843600 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116669889 | Physically Completed | 23490 | 23490 | 2025-11-05 | 2026-05-10
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5844321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117633398 | Physically Completed | 23490 | 21924 | 2025-11-04 | 2026-03-22
SHAJAPUR / SHAJAPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/5845462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106444291 | Ongoing | 23490 | 23490 | 2025-11-04
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/6243313 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106444336 | Approved | 23490 | 0 | 2026-04-28
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/6243314 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106444370 | Approved | 23490 | 0 | 2026-04-28
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/6243315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106444405 | Approved | 23490 | 0 | 2026-04-28
SHAJAPUR / SHAJAPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719005096/IF/IAY/6245418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113926071 | Approved | 23490 | 0 | 2026-04-28
SHAJAPUR / SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005096/RC/22012034845055 — CC Road Sah Nali Nirman jagdish k amkan se Prabhu k Makan Tak | Approved | 99800 | 0 | 2025-04-01
SHAJAPUR / SHAJAPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719005096/RC/22012034845099 — CC Road Sah Nali Nirman ratanlal k mkan se sanju giri ke badetak | Ongoing | 100000 | 99963 | 2025-11-12
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005096/WC/22012035002687 — AMRIT SAROVAR TALAB NIRMAAN SIDHARTH FACTORY KE PASS | Closed | 0 | 0 | 2022-08-15
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005096/WC/22012035002690 — AMRIT SAROVAR TALAB NIRMAAN 2 PODBALL JI KE BAGICHE KE PASS | Closed | 0 | 0 | 2022-08-15
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005096/WC/22012035012104 — Amrit sarowar talag nirman siddharth factory ke pass gram londiya | Closed | 0 | 0 | 2022-10-02
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005096/WC/22012035012107 — amrit sarowar dug out pond akya road ke pass londiya | Completed | 962559.94 | 834154.66 | 2022-12-02 | 2024-08-02
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005096/WC/22012035014274 — Amrit sarovar Dug out pond Siddharth factroy ke pass gram Londiya | Completed | 1117105.82 | 975872.29 | 2022-11-25 | 2024-08-02
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005096/WC/22012035014275 — Amrit sarovar Dug out pond Siddharth factroy ke pass gram Londiya | Closed | 0 | 0 | 2022-10-02
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005096/WC/22012035028461 — chek dam nirman pandukhora | Closed | 0 | 0 | 2022-09-02
SHAJAPUR / SHAJAPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005096/WC/22012035028462 — chek dam nirman pandukhora | Closed | 0 | 0 | 2022-09-02
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005096/WC/22012035087289 — chek dam nirman pandukhora | Deleted | 1194733.44 | 221 | 2024-03-10
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719005096/WC/22012035113958 — Talab Nirman billi Vali bhid ke paas | Physically Completed | 1017296.33 | 751481.56 | 2023-10-05 | 2026-05-04
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005096/WC/22012035113961 — Chek dam nirman vijaysingh ki mashin ke paas | Closed | 0 | 0 | 2023-08-16
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005096/WC/22012035113963 — Chek dam nirman vinod guru ki bhumi ke paas | Deleted | 1149287.61 | 221 | 2024-03-10
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719005096/WC/22012035113965 — Contur trench nirman Siddharth fekti ke paas | Completed | 810754.21 | 703419 | 2023-10-06 | 2026-05-04
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005096/WC/22012035113966 — Gabion nirman londiya | Completed | 150165.62 | 111616.72 | 2023-10-05 | 2025-07-19
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1719005096/WC/22012035135963 — Contour nirman londiya | Closed | 0 | 0 | 2023-10-02
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005096/WC/22012035173195 — Gebiyan nirman sidharth factory ke pass | Completed | 347816.67 | 289762.48 | 2024-05-31 | 2025-05-13
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005096/WC/22012035173208 — Gebiyan nirman londiya | Completed | 364563.07 | 295611.3 | 2024-08-05 | 2025-05-13
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1719005096/WC/22012035183719 — Check dem uanda dhoj magara ki bhid ke pash | Closed | 0 | 0 | 2024-01-25
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005096/WC/22012035217495 — Gebiyan nirman Jojansingh ki bhumi ke pas londiya | New | 0 | 0 | 2024-06-08
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005096/WC/22012035217498 — Gebiyan nirman Jojansingh ki bhumi ke pas londiya | Approved | 0 | 0 | 2024-06-08
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005096/WC/22012035217500 — Gebiyan nirman mangilal ki bhumi ke pas londiya | Approved | 0 | 0 | 2024-06-08
SHAJAPUR / SHAJAPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719005096/WC/22012035217501 — Gebiyan nirman boriya ki bhumi ke pas londiya | Approved | 0 | 0 | 2024-06-08
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1719005096/WC/22012035319380 — Construction of Gully plug Londiya pahadi par 1 | Approved | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1719005096/WC/22012035319381 — Construction of Gully plug Londiya Pahadi par 2 | Approved | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1719005096/WC/22012035319382 — Construction of Gully plug Londiya Pahadi par 3 | Approved | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1719005096/WC/22012035319383 — Construction of Gully plug Londiya pahadi par 4 Londiya | Approved | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1719005096/WC/22012035319384 — Construction of Gully plug Londiya pahadi par 5 Gram Londiya | Approved | 0 | 0 | 2025-08-15
SHAJAPUR / SHAJAPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1719005/WC/22012035169587 — Construction of Gully plug gram Londiya | New | 0 | 0 | 2024-01-26