## Work List
Exported on: 2026-09-26 10:33:48
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: SHADIPURA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1719006034/AV/22012034465889 — Goshala nirman rijavta GP shadipura | Completed | 2771628.29 | 2720821.28 | 2019-08-05 | 2020-10-13
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719006034/AV/22012034541518 — Samudayik swachata parisar school ke pass panchayat bhawan parisar shadipura | Closed | 44000 | 0 | 2020-08-15
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1719006034/AV/22012034616970 — Stopdam kam puliya gp shadipura | Completed | 261000 | 166630.89 | 2022-06-10 | 2025-05-13
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719006034/AV/22012034617093 — Aangnwadi bhawan nirman sadankhedi gp shadipura | Completed | 180000 | 100080 | 2022-04-10 | 2025-05-13
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1719006034/AV/22012034626979 — Puliya nirman kary panchayat bhawan ke samne wale raste par shadipura | Ongoing | 84500 | 23784.28 | 2025-03-02
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1719006034/AV/22012034658188 — puliya nirman karya panchayat bhavan ke samne vale raste par shadipura | Approved | 84500 | 0 | 2024-06-08
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006034/DP/22012034242569 — samudayik vriksharopan shantidham rijawata | Completed | 335000 | 25256 | 2017-07-29 | 2024-02-05
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006034/DP/22012034242585 — SAMUDAYIK VRIKSHAROPAN SHANTIDHAM SHADANKHEDI | Completed | 335000 | 25256 | 2017-07-14 | 2024-02-05
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006034/DP/22012034242587 — SAMUDAYIK VRIKSHAROPAN SHANTIDHAM SHADIPURA | Completed | 335000 | 29432 | 2017-07-29 | 2024-02-05
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719006034/DP/22012034432817 — Samudayik kup niraman Shadipura | Deleted | 535000 | 0 | 2018-10-08
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1719006034/DP/22012034544991 — Ma ki bagiya ekkrit higher school shadipura | Closed | 8863.57 | 0 | 2021-04-14
SHAJAPUR / MOMAN BADODIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719006034/DP/22012034602477 — Vashuda vandan amrit vatika 75 gp shadipura | Closed | 0 | 0 | 2023-04-14
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719006034/DW/9993656514 — Samudayik kup shantidham parisar shadipura | Completed | 789500 | 573453.6 | 2015-12-14 | 2017-05-03
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719006034/DW/9993656515 — Samudayik kup nirman shantidham prangan rijawta | Completed | 497500 | 358993.6 | 2015-12-14 | 2017-11-20
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719006034/IF/22012034354868 — Khet talab badrilal shankarlal shadipura | Closed | 76000 | 0 | 2017-04-01
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719006034/IF/22012034354869 — Nadef nirman harlal raisingh shadipura | Closed | 20798 | 0 | 2017-04-01
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1719006034/IF/22012034354871 — Nadef nirman kantilal mansingh shadipura | Closed | 20798 | 0 | 2017-04-01
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006034/IF/22012034437335 — Kapildhara Kup nirman Pirulal Kaluram rijawta GP Shadipura sc 2018 | Deleted | 210000 | 0 | 2018-10-08
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006034/IF/22012034536499 — Kapildhara kup nirman pirulal kaluram rijawta GP shadipura | Completed | 234458.57 | 233631.27 | 2020-05-01 | 2020-12-03
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719006034/IF/22012034604663 — Nandan falodyan aatmaram amrsingh gurjar rijawta | Ongoing | 149041.99 | 25188 | 2020-10-21
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1719006034/IF/22012034604664 — Nandan falodhyan amarsingh mayaram rijawta | Ongoing | 149041.99 | 24048 | 2020-10-21
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006034/IF/22012034675941 — Kapildhara kup nirman roop singh gurjar | Ongoing | 247839.67 | 206777.26 | 2021-05-17
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006034/IF/22012034675946 — Kapildhar kup nirman bharat singh dariyav singh gurjar | Closed | 247839.67 | 0 | 2020-10-02
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006034/IF/22012034675982 — Kapildhara kup nirman ramprsad devisingh gurjar | Ongoing | 247839.67 | 208701.26 | 2021-05-17
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006034/IF/22012034735666 — Kapildhara kup nirman mansingh ranjit shadipura | Closed | 247839.67 | 0 | 2021-04-01
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006034/IF/22012034735671 — Kapildhara kup nirman tolaram bhawarlal rijavta | Completed | 247839.67 | 225976.26 | 2021-05-17 | 2025-03-10
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006034/IF/9993668696 — Nandan Falodyan Ramesh-Dhulji Shadipura | Completed | 36600 | 7752 | 2015-07-04 | 2018-04-25
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006034/IF/9993668697 — Nandan Falodyan Durgaprsad-ranjit Shadipura | Completed | 36600 | 7752 | 2015-07-04 | 2018-04-25
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1234258 — Construction of IAY House -IAY REG. NO. MP2949765 | Completed | 15480 | 15660 | 2018-05-28 | 2018-08-11
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1480682 — Construction of IAY House -IAY REG. NO. MP2535855 | Completed | 15480 | 15660 | 2018-06-04 | 2019-01-29
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1484736 — Construction of IAY House -IAY REG. NO. MP2953121 | Completed | 15480 | 15660 | 2018-08-20 | 2019-01-08
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1926123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4103138 | Deleted | 15660 | 0 | 2018-09-10
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1926124 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4103157 | Completed | 15660 | 15672 | 2018-09-10 | 2019-06-10
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1926204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4369546 | Completed | 15660 | 15672 | 2018-09-10 | 2019-06-10
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1930525 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4120901 | Completed | 15660 | 15672 | 2018-09-03 | 2019-06-10
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1930603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4703206 | Completed | 15660 | 15660 | 2018-09-03 | 2019-01-29
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1935824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4390774 | Completed | 15660 | 15672 | 2018-10-08 | 2019-06-10
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/1936328 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4085161 | Completed | 15660 | 15696 | 2018-10-08 | 2019-06-10
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/2112252 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4370048 | Completed | 15840 | 15840 | 2019-07-30 | 2019-12-31
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/2129369 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4717737 | Completed | 15840 | 15840 | 2019-07-30 | 2019-12-31
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/2129531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4728388 | Completed | 15840 | 15840 | 2019-07-30 | 2019-12-06
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/2129734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4756997 | Completed | 15840 | 15840 | 2019-07-30 | 2019-12-06
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/2258358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2298293 | Completed | 15840 | 15840 | 2019-07-30 | 2019-12-06
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3968850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607634 | Completed | 18360 | 17136 | 2022-07-25 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3969225 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113927983 | Completed | 18360 | 18150 | 2022-07-09 | 2023-09-30
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3969227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928093 | Completed | 18360 | 18156 | 2022-08-19 | 2023-07-16
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928209 | Completed | 18360 | 18156 | 2022-07-25 | 2023-07-16
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928749 | Completed | 18360 | 17544 | 2022-09-19 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928796 | Completed | 18360 | 18156 | 2022-11-22 | 2024-10-02
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971010 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928936 | Completed | 18360 | 18360 | 2022-07-25 | 2022-12-24
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929053 | Completed | 18360 | 18360 | 2022-07-25 | 2023-03-25
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929184 | Completed | 18360 | 17136 | 2022-07-25 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929346 | Completed | 18360 | 17136 | 2022-07-25 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971018 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929395 | Completed | 18360 | 18217 | 2022-08-19 | 2024-05-01
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113930938 | Completed | 18360 | 17136 | 2022-07-25 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931544 | Completed | 18360 | 17748 | 2022-08-19 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931708 | Completed | 18360 | 17298 | 2022-08-19 | 2024-06-04
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931895 | Completed | 18360 | 18360 | 2022-07-09 | 2023-05-02
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113932930 | Completed | 18360 | 18258 | 2022-08-19 | 2023-07-16
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3971047 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933407 | Completed | 18360 | 18240 | 2022-10-28 | 2023-09-17
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3973183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118043903 | Completed | 18360 | 18360 | 2022-08-19 | 2023-05-02
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978258 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119503713 | Completed | 18360 | 17561 | 2022-08-19 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507312 | Completed | 18360 | 18246 | 2022-09-19 | 2024-06-04
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507822 | Completed | 18360 | 17748 | 2022-08-19 | 2024-02-29
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508013 | Completed | 18360 | 17802 | 2022-12-13 | 2024-07-09
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508273 | Completed | 18360 | 18102 | 2023-01-12 | 2024-06-27
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978268 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508443 | Closed | 18360 | 0 | 2022-05-10
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509573 | Completed | 18360 | 18156 | 2022-08-19 | 2023-07-16
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510081 | Completed | 18360 | 17969 | 2022-08-19 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510685 | Completed | 18360 | 17748 | 2022-08-19 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978272 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510710 | Completed | 18360 | 17748 | 2022-08-19 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3978273 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511495 | Completed | 18360 | 18325 | 2022-11-22 | 2024-05-01
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3979086 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117858903 | Completed | 18360 | 18156 | 2022-08-19 | 2023-07-16
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3984958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117966420 | Completed | 18360 | 18360 | 2022-07-09 | 2023-05-17
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/3984969 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117971165 | Completed | 18360 | 17646 | 2022-11-22 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4073714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117859221 | Completed | 18360 | 14136 | 2022-12-13 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4074505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509370 | Completed | 18360 | 17969 | 2022-12-13 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4074506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509486 | Completed | 18360 | 18044 | 2023-01-13 | 2024-06-04
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4074510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511023 | Completed | 18360 | 17520 | 2023-01-13 | 2024-07-09
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4114715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928605 | Completed | 18360 | 17646 | 2022-11-22 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4114724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931617 | Completed | 18360 | 15942 | 2023-01-12 | 2024-10-02
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4118732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117858104 | Closed | 18360 | 0 | 2022-05-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4119213 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509416 | Completed | 18360 | 18144 | 2023-01-12 | 2024-06-04
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4119214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510421 | Completed | 18360 | 17340 | 2022-08-19 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4284248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510453 | Completed | 18360 | 18060 | 2022-12-13 | 2024-07-09
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4284250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511588 | Completed | 18360 | 17340 | 2022-10-28 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4285757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118464845 | Completed | 18360 | 17544 | 2022-10-28 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4286281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117968126 | Closed | 18360 | 0 | 2022-07-16
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4300008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931851 | Completed | 18360 | 18322 | 2023-03-02 | 2024-07-02
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4300009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931951 | Completed | 18360 | 17867 | 2022-10-28 | 2024-02-22
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4743612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929917 | Completed | 23490 | 21510 | 2024-11-30 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4745209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607727 | Completed | 23490 | 21510 | 2024-11-30 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4745210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607774 | Completed | 23490 | 16533 | 2025-01-28 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4754391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117969224 | Completed | 23490 | 20187 | 2024-11-30 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4756611 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118464906 | Completed | 23490 | 21510 | 2024-11-30 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4757742 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507120 | Completed | 23490 | 21510 | 2024-11-30 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4793485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141598690 | Completed | 23490 | 21393 | 2024-11-30 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4800009 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150269530 | Completed | 23490 | 22176 | 2024-11-30 | 2026-05-20
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4858806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509956 | Ongoing | 27000 | 22041 | 2025-02-18
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4858808 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511521 | Ongoing | 27000 | 15777 | 2025-02-18
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4858968 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150276186 | Completed | 23490 | 22563 | 2025-02-18 | 2026-05-20
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4859030 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118044689 | Completed | 23490 | 16292 | 2025-02-18 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4863413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507261 | Completed | 23490 | 15777 | 2025-02-18 | 2026-08-04
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4863556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933800 | Completed | 23490 | 8991 | 2025-02-18 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4870522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113934059 | Ongoing | 27000 | 10917 | 2025-03-02
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4940392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607672 | Ongoing | 27000 | 21402 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4943777 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928455 | Physically Completed | 23490 | 7308 | 2025-09-12 | 2026-04-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4943781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929253 | Completed | 23490 | 21924 | 2025-05-31 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4943785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113930327 | Physically Completed | 27000 | 7308 | 2025-09-12 | 2026-08-30
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4943798 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933057 | Ongoing | 27000 | 21402 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4943804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113935119 | Completed | 23490 | 21672 | 2025-05-31 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4949993 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117829221 | Ongoing | 27000 | 21276 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/4953000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511641 | Completed | 27000 | 22707 | 2025-05-31 | 2026-09-01
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5253405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511760 | Completed | 23490 | 21672 | 2025-05-31 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5258832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113586525 | Ongoing | 27000 | 21241 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5273892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141598538 | Ongoing | 27000 | 14094 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5280779 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118464941 | Completed | 23490 | 23229 | 2025-05-31 | 2026-03-11
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5281167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928543 | Physically Completed | 23490 | 18294 | 2025-09-12 | 2026-08-02
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5287206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113934748 | Physically Completed | 23490 | 17615 | 2025-05-31 | 2026-08-09
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5334595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933932 | Completed | 23490 | 14094 | 2025-09-12 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5341046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507089 | Completed | 23490 | 21388 | 2025-05-31 | 2026-08-04
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/535587 — Construction of IAY House -IAY REG. NO. MP2944782 | Completed | 15030 | 15520 | 2017-10-02 | 2018-08-11
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5385125 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507144 | Ongoing | 27000 | 21262 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5396025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928679 | Completed | 23490 | 21395 | 2025-05-31 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5460455 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933344 | Approved | 27000 | 0 | 2024-11-20
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5495645 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931873 | Ongoing | 27000 | 22441 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5496497 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118043997 | Ongoing | 27000 | 21388 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5496498 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118044477 | Ongoing | 27000 | 21770 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5496794 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113935486 | Completed | 23490 | 23215 | 2025-05-31 | 2026-03-11
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5496837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928288 | Physically Completed | 23490 | 21262 | 2025-05-31 | 2026-08-02
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5556851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113934936 | Completed | 23490 | 17734 | 2025-05-31 | 2026-08-10
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5558295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607425 | Completed | 23490 | 23215 | 2025-05-31 | 2026-03-11
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5561229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931922 | Physically Completed | 27000 | 17734 | 2025-05-31 | 2026-08-30
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5561230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931995 | Physically Completed | 23490 | 21658 | 2025-05-31 | 2026-08-02
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5563578 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126419741 | Ongoing | 27000 | 21910 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5563860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929521 | Ongoing | 27000 | 8613 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5566211 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141598472 | Ongoing | 27000 | 21658 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5566212 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141598557 | Ongoing | 27000 | 21910 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5566958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126740166 | Completed | 23490 | 21658 | 2025-05-31 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5576281 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113935928 | Ongoing | 27000 | 12775 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5577250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607744 | Completed | 23490 | 21262 | 2025-05-31 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5577786 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511632 | Physically Completed | 23490 | 21262 | 2025-05-31 | 2026-08-09
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5591215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511620 | Ongoing | 27000 | 21402 | 2025-05-31
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672427 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113927892 | Completed | 23490 | 14094 | 2025-09-12 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672475 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607068 | Physically Completed | 23490 | 7308 | 2025-09-12 | 2026-04-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141598396 | Ongoing | 27000 | 1566 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931972 | Ongoing | 27000 | 13608 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607701 | Ongoing | 27000 | 20394 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113928862 | Ongoing | 27000 | 12267 | 2025-09-19
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929471 | Ongoing | 27000 | 20394 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672935 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113934150 | Physically Completed | 27000 | 14094 | 2025-09-12 | 2026-08-30
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5672956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113929752 | Physically Completed | 27000 | 14094 | 2025-09-12 | 2026-08-30
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5687275 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113580677 | Physically Completed | 27000 | 1827 | 2025-09-12 | 2026-08-30
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5698650 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118043780 | Ongoing | 27000 | 7308 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5698833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511576 | Ongoing | 27000 | 7308 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5699952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118464929 | Physically Completed | 27000 | 1827 | 2025-09-12 | 2026-08-30
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5700685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113607762 | Physically Completed | 27000 | 20394 | 2025-09-12 | 2026-08-30
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5708644 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118464870 | Ongoing | 27000 | 1827 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5718443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507307 | Ongoing | 27000 | 14094 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5718639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511564 | Ongoing | 27000 | 7308 | 2025-09-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5723366 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150284998 | Ongoing | 27000 | 11781 | 2025-09-19
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/586077 — Construction of IAY House -IAY REG. NO. MP2300419 | Completed | 15030 | 15504 | 2017-10-02 | 2019-12-06
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/5870824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113933551 | Approved | 27000 | 0 | 2025-03-08
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/59323 — Construction of IAY House -IAY REG. NO. MP-19-006-034-001/0113 | Approved | 27000 | 0 | 2015-12-22
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/59324 — Construction of IAY House -IAY REG. NO. MP-19-006-034-002/023 | Approved | 27000 | 0 | 2015-12-22
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/61108 — Construction of IAY House -IAY REG. NO. MP-19-006-034-001/82 | Approved | 27000 | 0 | 2015-12-27
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/61109 — Construction of IAY House -IAY REG. NO. MP-19-006-034-002/00176 | Approved | 27000 | 0 | 2015-12-27
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/616064 — Construction of IAY House -IAY REG. NO. MP2300587 | Completed | 15030 | 15480 | 2017-07-17 | 2017-10-16
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/623816 — Construction of IAY House -IAY REG. NO. MP1251202 | Completed | 15030 | 15480 | 2017-07-31 | 2017-10-16
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/781662 — Construction of IAY House -IAY REG. NO. MP1240765 | Completed | 15480 | 15480 | 2017-10-02 | 2018-01-29
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/781675 — Construction of IAY House -IAY REG. NO. MP1242795 | Completed | 15480 | 15480 | 2017-10-02 | 2018-01-29
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/810237 — Construction of IAY House -IAY REG. NO. MP1423421 | Completed | 15480 | 15492 | 2017-10-02 | 2018-06-20
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/820304 — Construction of IAY House -IAY REG. NO. MP2250865 | Completed | 15480 | 15480 | 2017-07-10 | 2018-01-29
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/821048 — Construction of IAY House -IAY REG. NO. MP2322009 | Completed | 15480 | 16512 | 2017-10-02 | 2018-06-04
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/825170 — Construction of IAY House -IAY REG. NO. MP2944892 | Completed | 15480 | 15480 | 2017-07-31 | 2018-02-09
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/825260 — Construction of IAY House -IAY REG. NO. MP2962293 | Completed | 15480 | 15824 | 2017-07-10 | 2018-05-10
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/825261 — Construction of IAY House -IAY REG. NO. MP2962458 | Completed | 15480 | 14448 | 2017-07-17 | 2017-10-16
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/825554 — Construction of IAY House -IAY REG. NO. MP3020981 | Completed | 15480 | 16512 | 2017-10-02 | 2017-11-20
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006034/IF/IAY/825573 — Construction of IAY House -IAY REG. NO. MP3025632 | Completed | 15480 | 15480 | 2017-10-02 | 2018-01-29
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719006034/LD/22012034226487 — Shantidham gova me rijavta gp shadipura | Deleted | 0 | 0 | 2015-04-24
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719006034/LD/22012034226489 — Shantidham gowa me rijavta gp shadipura | Completed | 430000 | 377645.41 | 2015-06-17 | 2016-03-18
SHAJAPUR / MOMAN BADODIYA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719006034/LD/22012034297086 — Shantidham sadan khedi sadipura | Completed | 181600 | 154650.09 | 2017-01-09 | 2017-08-16
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719006034/LD/22012034309830 — Shantidham gram rijawta shadipura | Completed | 180000 | 151458.73 | 2017-06-05 | 2017-11-15
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719006034/LD/22012034310151 — Shantidham nirman rijawta shadipura | Completed | 180000 | 151507.29 | 2017-06-05 | 2017-11-15
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1719006034/LD/22012034369483 — Dabri nirman GP shadipura | Deleted | 288000 | 0 | 2018-10-08
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Dev of Silvipasture Grassslands for Community / Development of Silvipasture Grassslands for Community | Grass Land Development | 1719006034/LD/22012034467726 — Chragah nirman gram rijavta GP shadipura | Completed | 750924.38 | 56832 | 2020-01-26 | 2026-06-02
SHAJAPUR / MOMAN BADODIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Constr of Earthen contour Bund for Community / Construction of Earthen contour Bund for Community | Construction of Bund | 1719006034/LD/22012034600643 — khrt talab | New | 0 | 0 | 2024-01-26
SHAJAPUR / MOMAN BADODIYA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719006034/LD/3799398086 — santidham shadipura | Completed | 339000 | 306900.53 | 2013-06-28 | 2015-04-30
SHAJAPUR / MOMAN BADODIYA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034156250 — पंच पर्मेश्वर | Deleted | 0 | 0 | 2012-12-31
SHAJAPUR / MOMAN BADODIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034176204 — cc pp sadan khedi ambaram to hend pump | Completed | 70200 | 72705.76 | 2013-07-26 | 2014-06-04
SHAJAPUR / MOMAN BADODIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034181274 — cc road panch parmesvar III sadankhedi amarsing to | Completed | 142500 | 142261.74 | 2014-01-13 | 2014-06-11
SHAJAPUR / MOMAN BADODIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034222113 — ccroad panchparmeswar | Deleted | 0 | 0 | 2013-08-15
SHAJAPUR / MOMAN BADODIYA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034223220 — cc road pp nrega mandir chok to road shadipura | Completed | 104300 | 99714.73 | 2014-06-30 | 2015-04-30
SHAJAPUR / MOMAN BADODIYA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034224089 — cc road pp nrega kaluram to nanuram shadipura | Completed | 127400 | 121536.7 | 2014-07-21 | 2015-04-30
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034304089 — c.c.raoad ramash to mohan ke makan tak shadepura | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / MOMAN BADODIYA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034304137 — c.c.raod rupkumar to rajandra shadepura | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / MOMAN BADODIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034311560 — CC road pp nrega Syamsingh ke makan se shri ramdev manditr or road se ps shala rijawta | Completed | 170000 | 152917.91 | 2017-03-06 | 2017-11-20
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034311561 — CC road pp nrega main road se shri hanumanmandir rijawta | Completed | 142200 | 123686 | 2017-04-03 | 2017-11-20
SHAJAPUR / MOMAN BADODIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034320593 — c.c.road & nalinerman Shadipura | Closed | 0 | 0 | 2016-08-15
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034342519 — CC road nali nirman shukhlal ke makan se goverdhan ambemata mandir chowk shadipura | Closed | 83985 | 0 | 2017-04-01
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034345146 — CC road anarsingh ke makan se main road ps school shadipura | Closed | 302850 | 0 | 2017-04-01
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034393399 — CC road nali nirman colony sadankhedi aagar road se hendpump tak | Completed | 64740 | 64536 | 2018-10-08 | 2020-06-04
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034397001 — CC road nali nirman bapulal ke makan se jagdish ke makan tak rizavta shadipura | Closed | 9039000000 | 0 | 2018-10-02
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034397004 — CC road nali nirman ramsingh ke makan se mandir road rizavta shadipura | Closed | 78600 | 0 | 2018-04-14
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034439597 — CC road nirman | Closed | 0 | 0 | 2018-08-15
SHAJAPUR / MOMAN BADODIYA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034514091 — cc rod nirman | Closed | 0 | 0 | 2019-10-02
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719006034/RC/22012034526171 — Graval sadak nirman aanganwadi bhawan se narayan bharti ke makan tak rijawta GP shadipura | Completed | 1494117.76 | 546805.57 | 2020-06-29 | 2025-10-28
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034531858 — CC road nali nirman Ghisulal ke makan se rajesh ke makan tak any gali rijawta Shadipura | Physically Completed | 177000 | 176700 | 2020-12-07 | 2021-09-15
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034544562 — CC road pirulal ke makan se bhagirath ke makan tak rijawta GP shadipura | Physically Completed | 58500 | 61750 | 2020-12-07 | 2021-09-15
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034558174 — cc road | Closed | 0 | 0 | 2020-10-02
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034628495 — C C ROAD | Closed | 0 | 0 | 2022-11-30
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/22012034838234 — cc road nali nirman pirmalik se puri bai tak road se mandir chok v babulal tak aya galiya shadipura | Approved | 81600 | 0 | 2025-01-20
SHAJAPUR / MOMAN BADODIYA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1719006034/RC/50 — मिटटी क्रत सडक मुख्‍य मार्ग रिजावता से शमशान ग्राम रिजावता तक | Completed | 484200 | 452128 | 2011-05-08 | 2011-11-25
SHAJAPUR / MOMAN BADODIYA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/88 — सी,सी,रोड सादनखेडी पंच- परमेश्‍वर+मनरेगा | Completed | 69200 | 69273.74 | 2013-01-16 | 2014-06-04
SHAJAPUR / MOMAN BADODIYA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006034/RC/89 — सी,सी,रोड विधायकनिधि+मनरेगा सादनखेडी | Completed | 61100 | 58091.86 | 2013-01-16 | 2014-06-04
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1719006034/RS/22012034500916 — Samudayik swachhta parisar school ke pass panchayat bhawan parisar shadipura | Physically Completed | 44000 | 40560 | 2020-12-07 | 2021-10-30
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719006034/RS/22012034679975 — Nali nirman bhagirath ke makan se jan suvidha kendra ke aage tak shadipura | Closed | 0 | 0 | 2022-08-15
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719006034/RS/22012034679976 — Nali nirman bhagirath ke makan se jan suvidha kendra ke aage tak shadipura | Closed | 25300 | 0 | 2022-08-15
SHAJAPUR / MOMAN BADODIYA | 2016-2017 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719006034/SK/9993648836 — Bharat Nirman Rajeev Gandhi Sewa Kendra,SHADIPURA | Completed | 1285000 | 507860.07 | 2016-12-26 | 2018-06-25
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719006034/WC/22012034379476 — chak dam | Closed | 0 | 0 | 2017-11-21
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Stop Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719006034/WC/22012034379488 — chek dem | Closed | 0 | 0 | 2017-11-21
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1719006034/WC/22012034562033 — Dabri nirman Goshala parisar rijawata GP shadipura | Completed | 203175.24 | 172582 | 2020-06-29 | 2022-04-28
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719006034/WC/22012034701897 — Samudayik kup PHE ke pass recharg pit nirman shadipura | Closed | 21072.25 | 0 | 2021-04-14
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719006034/WC/22012034701900 — Samudayik kup PHE ke pass recharge pit nirman rijawta gp shadipura | Closed | 21386.45 | 0 | 2021-04-14
SHAJAPUR / MOMAN BADODIYA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719006034/WC/5 — डबरी निर्माण | Completed | 60000 | 57937 | 2008-05-28 | 2010-05-08
SHAJAPUR / MOMAN BADODIYA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719006034/WH/19954774 — Talab maramat gahrikaran rijawta | Completed | 74000 | 44255 | 2016-05-02 | 2016-08-31
SHAJAPUR / MOMAN BADODIYA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719006034/WH/19954775 — Talab maramat gahrikaran shadipura | Completed | 51000 | 37408 | 2016-05-02 | 2016-08-31
SHAJAPUR / MOMAN BADODIYA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719006034/WH/19960699 — Talab jirnoddhar rizawta | Completed | 350000 | 249008.79 | 2017-06-05 | 2018-09-03
SHAJAPUR / MOMAN BADODIYA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Village Drain / Construction of Open / Covered Grey Water/Storm Drain for Community | Construction of Road and Culvert | 1719/RC/22012034176485 — cc road drainhume pipe shadipura shadipura | Completed | 347200 | 183773.91 | 2013-06-14 | 2014-07-21