## Work List
Exported on: 2026-09-08 12:12:50
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MAKHAWAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / MOMAN BADODIYA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1719006073/AV/22012034533934 — Goshala nirman karya gram panchayat makhawad me | Physically Completed | 3804449.17 | 0 | 2020-11-18 | 2026-08-16
SHAJAPUR / MOMAN BADODIYA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719006073/DP/22012034407390 — Samudayik vriksharopan patada nala ki pal simrol shu raste par makahavad 2018 | Ongoing | 544000 | 0 | 2018-08-03
SHAJAPUR / MOMAN BADODIYA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1719006073/DP/22012034613274 — khet talab | New | 0 | 0 | 2024-01-26
SHAJAPUR / MOMAN BADODIYA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719006073/IF/22012034758427 — khet talab nirman manohar-lochan kanjar makhawad | Ongoing | 337715.44 | 0 | 2021-06-10
SHAJAPUR / MOMAN BADODIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006073/IF/22012035109637 — Kapildhara kup nirman karya kalu s/o hukma sc makhawad | Ongoing | 282417.57 | 0 | 2023-06-16
SHAJAPUR / MOMAN BADODIYA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006073/IF/22012035116979 — Kapildhara kup nirman karya gokal s/o shankarlal sc makhawad | Ongoing | 282417.57 | 0 | 2023-06-19
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719006073/IF/22012035527213 — JGSA2025 DUGWELL RICHARGE PIT MANISH-KACHRULAL MAKHAWAD | Approved | 25899.46 | 0 | 2025-05-12
SHAJAPUR / MOMAN BADODIYA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/3981153 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122541264 | Ongoing | 27000 | 0 | 2022-08-24
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/4696074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113919560 | Ongoing | 27000 | 0 | 2024-12-14
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5396577 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115217056 | Ongoing | 27000 | 0 | 2025-04-29
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5399482 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113920633 | Ongoing | 27000 | 0 | 2025-05-13
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5399495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113945935 | Ongoing | 27000 | 0 | 2025-05-20
SHAJAPUR / MOMAN BADODIYA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5399942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114865253 | Approved | 27000 | 0 | 2025-03-26
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5405233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115226262 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5459263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113919200 | Physically Completed | 23490 | 0 | 2025-05-13 | 2026-08-16
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5561193 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113919582 | Ongoing | 27000 | 0 | 2025-08-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5566890 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142757590 | Physically Completed | 23490 | 0 | 2025-07-24 | 2026-07-26
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5659317 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115226621 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5672359 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114184253 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5672360 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114184419 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5672405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114791118 | Completed | 23490 | 0 | 2025-07-24 | 2026-08-05
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5672422 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115217182 | Ongoing | 27000 | 0 | 2025-09-03
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5672936 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114127291 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5684799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114125407 | Ongoing | 27000 | 0 | 2025-09-03
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5689232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113935894 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5698036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113919538 | Ongoing | 27000 | 0 | 2025-08-12
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5698763 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115215405 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5700880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130765593 | Ongoing | 27000 | 0 | 2025-07-28
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5708667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115226679 | Ongoing | 27000 | 0 | 2025-07-24
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5734632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113920345 | Ongoing | 27000 | 0 | 2025-08-16
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5857737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130765517 | Completed | 23490 | 0 | 2026-01-22 | 2026-08-05
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5878396 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113936127 | Ongoing | 27000 | 0 | 2026-05-26
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/5878442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113919266 | Ongoing | 27000 | 0 | 2026-08-11
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6102900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142492522 | Ongoing | 27000 | 0 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6102901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142492571 | Approved | 27000 | 0 | 2026-03-18
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6105227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116899470 | Approved | 27000 | 0 | 2026-03-18
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6105732 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114865702 | Ongoing | 27000 | 0 | 2026-08-11
SHAJAPUR / MOMAN BADODIYA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6106684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115232402 | Approved | 27000 | 0 | 2026-03-18
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6106867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115216042 | Ongoing | 27000 | 0 | 2026-05-26
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6110041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113936001 | Ongoing | 27000 | 0 | 2026-05-26
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6110619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114791147 | Ongoing | 27000 | 0 | 2026-05-26
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6110623 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116898978 | Ongoing | 27000 | 0 | 2026-05-26
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6110624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116899027 | Ongoing | 27000 | 0 | 2026-07-25
SHAJAPUR / MOMAN BADODIYA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006073/IF/IAY/6330162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116899287 | Approved | 27000 | 0 | 2026-07-02
SHAJAPUR / MOMAN BADODIYA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006073/RC/22012034675163 — cc road | New | 0 | 0 | 2024-01-26