## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1719006087/AV/22012034648911 — Pipe culvert nirman baliya ghat naya choma | Completed | 835000 | 808453.58 | 2024-01-29 - 2025-10-24
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719006087/AV/22012034657080 — shanti daam nirman bijnakhedi | New | 0 | 0 | 2024-06-08 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719006087/AV/22012034658584 — shantidhaam nirman bijna khedi | Physically Completed | 199933.33 | 186925.61 | 2024-08-22 - 2026-06-04
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play field for Community | Construction of Play field | 1719006087/AV/22012034659403 — khel medhan nirman gram bijnakhedi | Physically Completed | 476879.26 | 312070.6 | 2024-11-12 - 2026-06-04
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719006087/DP/22012034590658 — amrat vatika navin talab ke paas naya choma | Closed | 55847.4 | 600 | 2023-10-06 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Canal Line Plantation of Forestry-Community / Canal Line Plantation of Forestry Trees for Community | Plantation | 1719006087/DP/22012034613262 — khet talab | New | 0 | 0 | 2024-01-26 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719006087/IC/22012034891265 — samudayik kup nirman samsan ke paas naya choma | New | 0 | 0 | 2025-04-20 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719006087/IC/22012034891356 — Samudayik kup nirman naya choma samsan ke paas | Approved | 605674.76 | 0 | 2025-04-20 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719006087/IF/22012035445190 — JGSA DUGWELL RECHARGE PIT KAPILDHARA KOOP AMARSINGH/CHHITULAL NAYACHOUMA | New | 0 | 0 | 2025-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719006087/IF/22012035459733 — KHET TALAB NIRMAN KARY KANHAYALAL/KANIRAM NAYACHOUMA | New | 0 | 0 | 2025-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719006087/IF/22012035483190 — JGSA DUGWELL RECHARGE PIT NIJI KOOP KALURAM/GORELAL NAYACHOUMA | Physically Completed | 23899.46 | 14730.74 | 2025-05-11 - 2026-04-14
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719006087/IF/22012035483238 — JGSA DUGWELL RECHARGE PIT NIJI KOOP GORDAN/NARAYAN NAYACHOUMA | Physically Completed | 23899.46 | 14730.74 | 2025-05-11 - 2026-04-14
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719006087/IF/22012035548632 — KHET TALAB NIRMAN KARYA GORILAL / MOTILAL GP NAYACHOUMA | Closed | 106874.88 | 780.08 | 2025-05-28 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719006087/IF/22012035575124 — JGSA DUGWELL RECHARGE PIT NIJI KOOP RADHESHYAM /GANGARAM BIJNAKHEDI GP NAYACHOUMA | Physically Completed | 23899.46 | 19830.86 | 2025-08-22 - 2026-04-14
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006087/IF/22012035609868 — EK BAGIYA MAA KE NAAM DEV BAI SONDHIYA SARDAR SINGH GRAM NAYA CHOUMA GRAM BIJNAKHEDI | New | 0 | 0 | 2025-08-15 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006087/IF/22012035609882 — EK BAGIYA MAA KE NAAM DEV BAI SONDHIYA SARDAR SINGH GRAM NAYA CHOUMA GRAM BIJNAKHEDI | New | 0 | 0 | 2025-08-15 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006087/IF/22012035620643 — ak bagiya ma ke naam dev bai pati sardar singh bijnakhedi | New | 0 | 0 | 2025-09-10 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Sericulture in fields-Individuals / Block Plantation of Sericulture Trees in fields for Individuals | Plantation | 1719006087/IF/22012035620655 — ak bagiya ma ke naam dev bai pati sardar singh bijnakhedi | New | 0 | 0 | 2025-09-10 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006087/IF/22012035621423 — EK BAGIYA MAA KE NAAM DEV BAI SONDHIYA SARDAR SINGH GRAM NAYA CHOUMA GRAM BIJNAKHEDI | Closed | 263510.03 | 1212 | 2025-09-22 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719006087/IF/22012035621427 — EK BAGIYA MAA KE NAAM MUNNA BAI SONDHIYA HOKAM SINGH GP NAYA CHOUMA GRAM BIJNAKHEDI | Closed | 263510.03 | 1212 | 2025-09-22 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/4753333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117125268 | Completed | 23490 | 21627 | 2025-02-08 - 2025-11-07
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5821419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126826884 | Completed | 23490 | 22160 | 2025-10-30 - 2026-07-30
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5821876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116622400 | Approved | 23490 | 0 | 2025-02-27 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5821985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117393064 | Completed | 23490 | 21894 | 2025-10-30 - 2026-05-17
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5823098 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121596881 | Ongoing | 23490 | 18732 | 2026-06-13 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5823783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115151868 | Completed | 23490 | 21894 | 2025-10-28 - 2026-05-17
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5823958 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118525014 | Completed | 23490 | 21894 | 2025-10-30 - 2026-07-30
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5823959 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118525109 | Completed | 23490 | 22426 | 2025-10-30 - 2026-05-17
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5823960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118525201 | Completed | 23490 | 21096 | 2026-02-24 - 2026-07-30
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5827064 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119835961 | Approved | 23490 | 0 | 2025-02-27 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5827847 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115325530 | Ongoing | 23490 | 10676 | 2026-04-17 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5827951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126912105 | Completed | 23490 | 21514 | 2025-10-28 - 2026-07-30
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5828073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116212350 | Completed | 23490 | 22578 | 2025-10-30 - 2026-05-17
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5843776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114136731 | Ongoing | 23490 | 21367 | 2025-10-28 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5844604 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117125461 | Completed | 23490 | 22920 | 2025-10-28 - 2026-07-30
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5905433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116256825 | Approved | 23490 | 0 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5908682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116224151 | Approved | 23490 | 0 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5923805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122395748 | Approved | 23490 | 0 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5928646 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118525151 | Approved | 23490 | 0 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5928764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117570639 | Approved | 23490 | 0 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006087/IF/IAY/5929183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121575266 | Approved | 23490 | 0 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719006087/LD/22012034943724 — samudayik vraksha ropan radha savami parisar ke paas bijnakhedi | Ongoing | 145449.02 | 34206.88 | 2024-11-12 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034628440 — cc rod nirman | Closed | 0 | 0 | 2022-11-30 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719006087/RC/22012034654632 — Antrik marg karya cc hetu | Closed | 0 | 0 | 2023-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034657288 — cc rod avm nali nirman radesyam ke gar se badrilal ke gar tak | Completed | 95000 | 92639 | 2023-10-06 - 2024-08-06
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034661305 — CC road av nali nirman kary vishnu patidar ke ghar se ailkar ke ghar tak | Completed | 34849 | 24845 | 2023-10-06 - 2024-08-06
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034661308 — cc road av nali nirman kary prabhulal ke makan se rajendra singh ke makan tak naya choma | Completed | 55371 | 50536 | 2023-10-06 - 2024-08-06
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034662625 — CC road nirman prem narayan ke makan se hanuman mandir tak bijna khedi | Completed | 34887 | 30276 | 2025-09-12 - 2026-06-05
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719006087/RC/22012034663296 — puliya Nirman kary | Completed | 1004338.15 | 986484.49 | 2023-10-06 - 2024-10-15
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034675175 — CC road nali nirman kailas khati ke makan se hajarilal ke makan tak avm rajesh ke makan se shamshan | Completed | 92000 | 76734 | 2025-08-22 - 2026-06-05
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034842811 — cc road nali nirman kailash khati ke makan se rajesh ke makan tak naya choma | Approved | 92000 | 0 | 2025-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719006087/RC/22012034842813 — cc road nirman premnarayan ke makan se hanuman mandir tak bijnakhedi | Approved | 35000 | 0 | 2025-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034851696 — cc road nali nirman main road se p s va babula se amar singh | Closed | 80000 | 0 | 2026-03-21 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006087/RC/22012034851698 — cc rod avmam nali nirman karya rajendra singh ke makan se navin panchyat bhavan tak naya choma | Closed | 51628 | 0 | 2026-03-21 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719006087/RS/22012034700964 — nali nirman karya kelash ke gar se p s school tak | Completed | 42000 | 24889 | 2023-10-06 - 2024-08-06
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719006087/RS/22012034701605 — cc rod nali nirman prapbhulal ke gar se rajendra singh ke makan tak | Closed | 56000 | 0 | 2023-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719006087/RS/22012034705117 — cc rod nali nirman vishnu ke gar se alkar ke gar tak | Closed | 35000 | 0 | 2023-09-29 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1719006087/WC/22012035009220 — gully plak nirman talab ke paas gram panchayat naya choma | Completed | 101316.26 | 89066.75 | 2022-11-26 - 2024-05-03
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719006087/WC/22012035016335 — Naveen talab nirman Naya choma | Completed | 939366.52 | 933968.65 | 2022-12-20 - 2024-03-21
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719006087/WC/22012035078206 — percolation tank nirman naya choma | Completed | 377884.39 | 319992.72 | 2023-08-25 - 2024-08-06
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1719006087/WC/22012035131535 — gully plak nirman nirman bijnakhedi | Closed | 114992.97 | 0 | 2023-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719006087/WC/22012035131536 — chek dem nirman juna pani ka nala | Closed | 816262.31 | 0 | 2023-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719006087/WC/22012035131537 — chek dem nirman bijna khedi | Closed | 0 | 0 | 2023-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719006087/WC/22012035171142 — gabion structure nirman kary bijna khedi nale par | Completed | 112274.02 | 80005.32 | 2024-03-15 - 2025-03-13
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719006087/WC/22012035180729 — gabion structure nirman kary shamsan ke paas bijnakhedi | Completed | 112269.73 | 80005.72 | 2024-03-15 - 2025-03-13
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1719006087/WC/22012035180736 — gabion structure nirman kary talab ke paas bijnakhedi | Completed | 112269.73 | 80035.36 | 2024-03-15 - 2025-03-13
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719006087/WC/22012035233220 — Samudayik Talab nirman bijnakhedi | Approved | 1345209 | 0 | 2024-11-26 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719006087/WC/22012035289768 — JGSA DUGWELL RECHARGE PIT SAMUDAYIK KOOP NAYACHOUMA | Physically Completed | 23899.46 | 20473.78 | 2025-05-03 - 2026-04-14
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719006087/WC/22012035289777 — JGSA DUGWELL RECHARGEPIT SARVJANIK KUNDI NAYACHOUMA | Physically Completed | 23899.46 | 20473.78 | 2025-05-03 - 2026-04-14
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719006087/WC/22012035289782 — JGSA DUGWELL RECHARGE PIT SAMUDAYIK KOOP BIJNAKHEDI | Physically Completed | 23899.46 | 18907.78 | 2025-05-03 - 2026-05-02
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719006087/WC/22012035304489 — Dugout pond bijnakhedi gp naya choma | Approved | 0 | 0 | 2025-04-14 -
SHAJAPUR / MOMAN BADODIYA / NAYA CHOMA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719006087/WH/22012034937086 — percolation tank jirnodhar naya choma | Closed | 0 | 0 | 2023-04-01 -