## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719006093/DP/22012034602481 — Vashuda vandan amrit vatika 75 rijawata | Closed | 0 | 0 | 2023-04-14 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719006093/DP/22012034613251 — khet talab | New | 0 | 0 | 2024-01-26 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006093/IF/22012035056967 — kapildhara kup nirman bane singh bhawarlal | Closed | 0 | 0 | 2022-10-02 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006093/IF/22012035056975 — kapildhara kup nirman radhesayam girdharilala | Closed | 0 | 0 | 2022-10-02 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719006093/IF/22012035056984 — kapildhara kup nirman hindu singh girdharilal | Closed | 0 | 0 | 2022-10-02 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4384880 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509643 | Closed | 0 | 0 | 2022-11-15 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4387956 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510255 | Closed | 18360 | 0 | 2022-12-06 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757740 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119504743 | Completed | 23490 | 21789 | 2024-12-13 - 2025-06-24
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507693 | Completed | 23490 | 22032 | 2024-12-13 - 2025-06-24
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508052 | Completed | 23490 | 22032 | 2024-12-13 - 2025-06-24
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508933 | Approved | 23490 | 0 | 2024-10-01 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509214 | Completed | 23490 | 22032 | 2024-12-13 - 2025-06-24
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757750 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509529 | Completed | 23490 | 22032 | 2024-12-13 - 2025-06-24
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509816 | Completed | 23490 | 22336 | 2025-01-27 - 2025-09-12
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511084 | Completed | 23490 | 22032 | 2024-12-13 - 2025-06-24
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4757759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511349 | Completed | 23490 | 22131 | 2024-12-13 - 2025-10-27
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4858807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510157 | Completed | 23490 | 22536 | 2025-01-27 - 2025-09-12
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4863414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508063 | Completed | 23490 | 22410 | 2025-01-28 - 2025-09-12
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4863415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510240 | Completed | 23490 | 22275 | 2025-01-28 - 2025-09-12
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4863418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511227 | Completed | 23490 | 18612 | 2025-01-28 - 2025-10-27
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4863551 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931028 | Ongoing | 23490 | 22048 | 2025-02-18 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4863552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931226 | Ongoing | 23490 | 21312 | 2025-01-28 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4863559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113935648 | Completed | 23490 | 22266 | 2025-01-28 - 2025-09-12
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/4864507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117827021 | Completed | 23490 | 11952 | 2025-01-28 - 2025-10-27
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5822224 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117829792 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5822348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931381 | Ongoing | 23490 | 7047 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5822349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931404 | Ongoing | 23490 | 14094 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5822351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931805 | Approved | 23490 | 0 | 2025-02-27 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5822758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117859902 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823407 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510781 | Ongoing | 23490 | 13572 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510789 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510835 | Approved | 23490 | 0 | 2025-08-22 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510867 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823412 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510962 | Approved | 23490 | 0 | 2025-03-08 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823413 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510967 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823414 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511135 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823655 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119503303 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823656 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119504710 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507684 | Approved | 23490 | 0 | 2025-06-17 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5823658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507699 | Approved | 23490 | 0 | 2025-04-29 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508493 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508575 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508626 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508689 | Ongoing | 23490 | 4698 | 2026-03-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508697 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508751 | Approved | 23490 | 0 | 2025-07-10 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824823 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508757 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824824 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508766 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824825 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509253 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509336 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509385 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509458 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824829 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509517 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509625 | Ongoing | 23490 | 5220 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510365 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510498 | Ongoing | 23490 | 7047 | 2026-02-04 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510553 | Ongoing | 23490 | 4698 | 2026-03-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824834 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510610 | Approved | 23490 | 0 | 2025-02-27 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824836 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510673 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511273 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824838 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511369 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5824839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119511385 | Physically Completed | 23490 | 6525 | 2026-02-24 - 2026-03-03
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931661 | Approved | 23490 | 0 | 2025-03-08 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931775 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113931350 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508845 | Ongoing | 23490 | 6264 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825710 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508854 | Approved | 23490 | 0 | 2025-07-10 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508868 | Approved | 23490 | 0 | 2025-02-27 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825712 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509030 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509049 | Ongoing | 23490 | 4698 | 2026-03-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509080 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825715 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509171 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509203 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825998 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509670 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5825999 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509884 | Approved | 23490 | 0 | 2025-08-04 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510197 | Physically Completed | 23490 | 0 | 2025-03-08 - 2026-03-15
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510250 | Approved | 23490 | 0 | 2025-03-08 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507339 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826007 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507343 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117859685 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826860 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119507929 | Ongoing | 23490 | 7047 | 2026-02-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508104 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508118 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508188 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508198 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5826865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508268 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5845675 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510061 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5846057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119508708 | Approved | 23490 | 0 | 2025-06-03 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5846058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509341 | Ongoing | 23490 | 6525 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5846059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510662 | Approved | 23490 | 0 | 2025-04-16 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5846144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119509002 | Ongoing | 23490 | 13050 | 2026-02-24 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719006093/IF/IAY/5878353 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119510604 | Approved | 23490 | 0 | 2024-10-22 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006093/RC/22012034622883 — CC road nali nirman mohanlal sharma ke makan se pani ki tanki rijavta | Ongoing | 26200 | 25636.8 | 2023-08-17 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006093/RC/22012034628412 — cc rod nirman | Closed | 0 | 0 | 2022-11-30 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006093/RC/22012034650058 — CC road nirman devnarayan parisar rijawata | Ongoing | 92800 | 92773.45 | 2023-09-04 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719006093/RC/22012034827141 — CC road nirman karay rauji ke makan se premnarayan Tak mandir chock se Anya galiya rijawta | Approved | 64600 | 0 | 2024-08-19 -
SHAJAPUR / MOMAN BADODIYA / RIJAAWTA | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719006093/RS/22012035129032 — nali nirman karay babulal ke makn se narayan singh ke makan ke age tak | Approved | 48150 | 0 | 2024-07-05 -