## Work List
Exported on: 2026-10-11 05:10:03
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: CHITOUNI
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719007034/AV/22012034373634 — SHANTIDHAM SHED NIRMAN SHAMSHAN PARISAR ME | Completed | 180000 | 179886.91 | 2018-07-11 | 2019-10-12
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1719007034/DP/22012034543599 — Ma ki bagiya prathmik School shyampur | Completed | 9619.45 | 8883.61 | 2022-02-07 | 2022-12-01
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Road side line plantation of Forestry Trees for Community | Plantation | 1719007034/DP/22012034543604 — Ma ki bagiya Middle school chitoni | Completed | 9619.45 | 9031 | 2022-02-01 | 2022-12-01
SHAJAPUR / SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1719007034/DP/22012034575388 — सार्वजनिक कूप निर्माण कार्य ग्राम श्यामपुर | Completed | 246000 | 243560 | 2023-06-29 | 2025-03-10
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719007034/DW/9993658143 — comunnity well awas colony | Completed | 439000 | 421619.74 | 2016-04-22 | 2017-10-29
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/22012034353338 — PLANTATION GP CHITONI khel medan prisar middle schoo(Ladsingh)l | Completed | 335000 | 21344 | 2017-06-28 | 2022-01-30
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007034/IF/22012034416552 — KAPIL DHARA KUP NIRMAN JAGDISH/TULSIRAM | Completed | 214200 | 205692 | 2018-06-22 | 2019-07-20
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007034/IF/22012034470983 — Khet Talab nirman work Keshar singh/Bheru singh | Completed | 295000 | 271028 | 2019-03-11 | 2019-08-31
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/22012034593722 — Individuals Agriculture Land Plantation Project Shetan Bai- Santosh | Completed | 114410 | 36311 | 2020-08-12 | 2023-09-03
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/22012034593724 — Individuals Agriculture Land Plantation Project Ramgopal- Bherulal | Completed | 114410 | 55036 | 2020-08-12 | 2023-09-16
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/22012034593725 — Individuals Agriculture Land Plantation Project badri Uamrav singh | Completed | 114410 | 42946 | 2020-08-12 | 2023-08-30
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/22012034593726 — Individuals Agriculture Land Plantation Project Mangilal-Ramgopal | Completed | 114410 | 53830 | 2020-08-12 | 2024-11-15
SHAJAPUR / SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007034/IF/22012034699237 — खेत तालाब निर्माण कार्य रामनरायन नन्नूलाल (श्यामपुर) | Completed | 337715.44 | 255060 | 2021-05-20 | 2022-08-26
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007034/IF/22012035073291 — Kail daeara kup nirmaan deelip -kelaash | Completed | 385448.86 | 350045 | 2023-04-24 | 2025-01-03
SHAJAPUR / SHUJALPUR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007034/IF/2नविन कूप — नविन कूप निर्र्माण भगवती बाई बापूलाल चितौनी | Completed | 149000 | 64988 | 2009-12-09 | 2011-03-15
SHAJAPUR / SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/9993669551 — nandan ramparsad / babulal | Completed | 77000 | 3400.56 | 2015-08-04 | 2017-10-10
SHAJAPUR / SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/9993670258 — nanadan udham jagannath | Completed | 77000 | 4039.8 | 2015-08-02 | 2017-10-11
SHAJAPUR / SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/9993670392 — nadan rajal bai/ ramgopal | Completed | 77000 | 52090.8 | 2015-08-05 | 2018-10-07
SHAJAPUR / SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/9993670393 — nadan vikram / munalal | Completed | 77000 | 4052.76 | 2015-08-05 | 2017-10-10
SHAJAPUR / SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007034/IF/9993672374 — nandan ajab/ taj singh | Completed | 77000 | 3816 | 2015-08-28 | 2017-10-10
SHAJAPUR / SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007034/IF/9993705869 — kapildhara ram singh parbhulal mukesh | Completed | 261000 | 249788.9 | 2016-01-24 | 2016-11-30
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719007034/IF/9993717683 — Med Bandhan Badrilal s/o Umrav singh Chitouni | Completed | 30000 | 12023.28 | 2016-06-29 | 2016-11-22
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719007034/IF/9993717684 — Med Bandhan Rajal bai W/o Ramgopal Chitouni | Completed | 30000 | 12023.28 | 2016-06-29 | 2016-11-22
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007034/IF/9993720132 — MED BANDHAN PONMCHAND/DHUNGAJI | Completed | 30000 | 10020 | 2016-06-29 | 2016-11-23
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007034/IF/9993720138 — MEDBANDHAN JAGDISH/TULSIRAM | Completed | 30000 | 10020 | 2016-06-29 | 2016-11-23
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007034/IF/9993720146 — MED BANDHAN SHIVNARAYAN S/O TULSIRAM | Completed | 30000 | 12024 | 2016-06-29 | 2016-11-23
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007034/IF/9993720150 — MED BANDHAN SHURAJ SINGH/DHAL SINGH | Completed | 30000 | 12024 | 2016-06-29 | 2016-11-23
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007034/IF/9993720153 — BABULAL/GIRDHARI | Completed | 30000 | 12024 | 2016-06-29 | 2017-10-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719007034/IF/9993742653 — Med Bandhan of Kesar baI W/o bheru singh gram chitouni | Completed | 30000 | 12023.28 | 2016-06-29 | 2016-11-22
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719007034/IF/9993742659 — Med Bandhan of Himmat Singh s/o Tulsiram of gram Chitouni | Completed | 30000 | 12023.28 | 2016-06-29 | 2016-11-22
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1719007034/IF/9993742660 — Med Bandhan of Bhagirath S/o nathu singh of gram chitouni | Completed | 30000 | 12023.28 | 2016-06-29 | 2016-11-22
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1033758 — Construction of IAY House -IAY REG. NO. MP2535550 | Completed | 15480 | 15480 | 2017-10-25 | 2018-02-14
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1039218 — Construction of IAY House -IAY REG. NO. MP2917482 | Completed | 15480 | 15480 | 2017-10-25 | 2018-01-05
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1039896 — Construction of IAY House -IAY REG. NO. MP2965169 | Completed | 15480 | 15136 | 2017-09-13 | 2018-01-05
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1040096 — Construction of IAY House -IAY REG. NO. MP2980469 | Completed | 15480 | 15480 | 2017-10-25 | 2018-01-05
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1182263 — Construction of IAY House -IAY REG. NO. MP2981184 | Completed | 15480 | 15480 | 2017-10-25 | 2018-02-14
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1250375 — Construction of IAY House -IAY REG. NO. MP2511123 | Completed | 15480 | 16704 | 2018-06-18 | 2018-09-20
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1250397 — Construction of IAY House -IAY REG. NO. MP2527247 | Completed | 15480 | 15660 | 2018-06-27 | 2018-08-29
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1381163 — Construction of IAY House -IAY REG. NO. MP2527243 | Completed | 15480 | 14616 | 2018-06-13 | 2018-09-24
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1442585 — Construction of IAY House -IAY REG. NO. MP1242777 | Completed | 15480 | 15660 | 2018-06-13 | 2018-09-14
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1461482 — Construction of IAY House -IAY REG. NO. MP2104087 | Completed | 15480 | 14616 | 2018-06-13 | 2018-09-24
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1462173 — Construction of IAY House -IAY REG. NO. MP2147318 | Completed | 15480 | 15660 | 2018-06-18 | 2018-09-14
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1466928 — Construction of IAY House -IAY REG. NO. MP2288227 | Completed | 15480 | 15660 | 2018-06-13 | 2018-08-30
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1467880 — Construction of IAY House -IAY REG. NO. MP2342589 | Completed | 15480 | 15312 | 2018-06-18 | 2019-01-05
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1469963 — Construction of IAY House -IAY REG. NO. MP2445412 | Completed | 15480 | 15660 | 2018-06-18 | 2018-12-07
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1470025 — Construction of IAY House -IAY REG. NO. MP2449973 | Completed | 15480 | 15660 | 2018-06-18 | 2018-12-07
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1483904 — Construction of IAY House -IAY REG. NO. MP2916649 | Completed | 15480 | 15660 | 2018-06-18 | 2018-10-13
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1484743 — Construction of IAY House -IAY REG. NO. MP2953293 | Completed | 15480 | 15660 | 2018-06-13 | 2018-08-30
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1495373 — Construction of IAY House -IAY REG. NO. MP3407414 | Completed | 15480 | 15660 | 2018-06-13 | 2018-08-15
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1518637 — Construction of IAY House -IAY REG. NO. MP3764886 | Completed | 15480 | 15660 | 2018-06-13 | 2018-11-18
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1564426 — Construction of IAY House -IAY REG. NO. MP2382727 | Completed | 15480 | 15660 | 2018-06-13 | 2018-08-30
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1669418 — Construction of IAY House -IAY REG. NO. MP2383148 | Completed | 15660 | 15660 | 2018-06-18 | 2018-09-14
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1670526 — Construction of IAY House -IAY REG. NO. MP3758620 | Completed | 15660 | 15660 | 2018-05-28 | 2018-12-01
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1916350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4268914 | Completed | 15660 | 15660 | 2018-09-05 | 2018-11-18
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1916351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4268970 | Completed | 15660 | 15660 | 2018-09-05 | 2018-12-17
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1916444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4376774 | Completed | 15660 | 15660 | 2018-09-05 | 2018-11-14
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/1916463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4389737 | Completed | 15660 | 15486 | 2018-09-05 | 2019-02-07
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/2126749 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4690274 | Completed | 15840 | 15840 | 2019-07-24 | 2019-12-01
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/2127238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4703832 | Completed | 15840 | 15840 | 2019-07-24 | 2019-12-18
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/318682 — Construction of IAY House -IAY REG. NO. MP1066773 | Completed | 15030 | 15330 | 2017-01-30 | 2017-12-07
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/367129 — Construction of IAY House -IAY REG. NO. MP1174132 | Completed | 15030 | 15480 | 2017-02-08 | 2018-02-23
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/373850 — Construction of IAY House -IAY REG. NO. MP1346057 | Completed | 15030 | 15460.2 | 2017-02-08 | 2018-01-05
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4069796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117428307 | Completed | 18360 | 17544 | 2022-07-01 | 2022-09-06
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4069817 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117433696 | Completed | 18360 | 18360 | 2022-06-25 | 2022-08-30
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4069850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117438399 | Completed | 18360 | 18360 | 2022-06-25 | 2022-08-30
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/421503 — Construction of IAY House -IAY REG. NO. MP1336967 | Completed | 15030 | 15480 | 2017-02-15 | 2017-12-07
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4237296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143150378 | Completed | 18360 | 17748 | 2022-07-01 | 2022-10-03
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4251952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126483972 | Completed | 18360 | 17952 | 2022-07-15 | 2022-09-06
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/438208 — Construction of IAY House -IAY REG. NO. MP1453697 | Completed | 15030 | 15480 | 2017-02-15 | 2018-02-21
SHAJAPUR / SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4396237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113972418 | Completed | 19890 | 19890 | 2023-07-22 | 2023-10-10
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4701826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117431942 | Completed | 21870 | 20412 | 2024-11-14 | 2025-03-08
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4748631 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113972488 | Completed | 21870 | 20412 | 2024-11-14 | 2025-01-21
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4763702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122092207 | Completed | 21870 | 21627 | 2024-11-14 | 2025-02-22
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4778976 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126478487 | Completed | 21870 | 20412 | 2024-11-14 | 2025-01-21
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/4792806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127207077 | Completed | 21870 | 20412 | 2024-11-30 | 2025-03-08
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5256753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126465921 | Completed | 23490 | 23229 | 2025-04-20 | 2025-08-05
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5262345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125075920 | Completed | 23490 | 23229 | 2025-05-22 | 2025-09-15
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5268199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123839815 | Completed | 23490 | 23229 | 2025-04-20 | 2026-02-22
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5268237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126491444 | Completed | 23490 | 23097 | 2025-04-20 | 2025-06-28
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5286566 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126436967 | Completed | 23490 | 23229 | 2025-04-20 | 2025-08-13
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5302619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122125701 | Completed | 23490 | 22914 | 2025-04-20 | 2025-08-05
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5303389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123474685 | Completed | 23490 | 23229 | 2025-04-20 | 2025-09-15
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5324508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128146076 | Completed | 23490 | 23229 | 2025-04-20 | 2025-08-13
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/57110 — Construction of IAY House -IAY REG. NO. MP-19-007-034-002/16 | Completed | 14310 | 11112 | 2016-11-23 | 2018-03-07
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5711821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126467039 | Completed | 23490 | 23490 | 2025-09-29 | 2025-10-24
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5711826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116115254 | Completed | 23490 | 23490 | 2025-09-19 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/57568 — Construction of IAY House -IAY REG. NO. MP-19-007-034-001/3 | Completed | 14310 | 8015.56 | 2016-07-06 | 2017-12-07
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5768200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115329528 | Completed | 23490 | 23490 | 2025-08-28 | 2025-10-31
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5769315 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114062321 | Completed | 23490 | 23490 | 2025-08-28 | 2026-02-02
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5811723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126467728 | Completed | 23490 | 23490 | 2025-09-17 | 2025-10-06
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5812157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126440554 | Completed | 23490 | 23490 | 2025-10-05 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5812443 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119599097 | Completed | 23490 | 23490 | 2025-10-05 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5812572 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115330267 | Completed | 23490 | 23490 | 2025-09-19 | 2025-10-18
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/5886815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125520195 | Completed | 23490 | 23490 | 2026-03-04 | 2026-05-31
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007034/IF/IAY/5886900 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125074874 | Completed | 23490 | 23490 | 2026-04-22 | 2026-07-13
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007034/IF/IAY/5887096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117445789 | Completed | 23490 | 23490 | 2026-03-15 | 2026-08-06
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/844142 — Construction of IAY House -IAY REG. NO. MP1412939 | Completed | 15480 | 15480 | 2017-10-25 | 2018-01-05
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/847459 — Construction of IAY House -IAY REG. NO. MP1457386 | Completed | 15480 | 15480 | 2017-10-25 | 2018-02-14
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/906146 — Construction of IAY House -IAY REG. NO. MP2222481 | Completed | 15480 | 15480 | 2017-10-26 | 2018-03-07
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/907766 — Construction of IAY House -IAY REG. NO. MP2244956 | Completed | 15480 | 15480 | 2017-10-26 | 2018-03-07
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/910886 — Construction of IAY House -IAY REG. NO. MP2288047 | Completed | 15480 | 15480 | 2017-10-25 | 2018-03-07
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/910893 — Construction of IAY House -IAY REG. NO. MP2288116 | Completed | 15480 | 15480 | 2017-10-25 | 2018-03-07
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/911189 — Construction of IAY House -IAY REG. NO. MP2292042 | Completed | 15480 | 15480 | 2017-10-25 | 2018-01-05
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/911643 — Construction of IAY House -IAY REG. NO. MP2298371 | Completed | 15480 | 15136 | 2017-09-13 | 2018-01-05
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007034/IF/IAY/914816 — Construction of IAY House -IAY REG. NO. MP2344808 | Completed | 15480 | 15480 | 2017-10-11 | 2018-01-12
SHAJAPUR / SHUJALPUR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007034/IF/नवीनकूप निर्माण तुलसीराम हरनाथसिंह च — नवीनकूप निर्माण तुलसीराम हरनाथसिंह चितौनी | Completed | 59600 | 47691 | 2009-06-01 | 2011-03-16
SHAJAPUR / SHUJALPUR | 2009-2010 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007034/IF/नवीनकूप‍ निर्माण सूरजसिंह पन्‍नालाल — नवीनकूप‍ निर्माण सूरजसिंह पन्‍नालाल चितौनी | Completed | 59600 | 60365 | 2009-06-01 | 2011-09-14
SHAJAPUR / SHUJALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007034/LD/22012034227577 — khel medan primary school shyampur | Completed | 121000 | 119562.49 | 2015-07-21 | 2016-05-28
SHAJAPUR / SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1719007034/LD/22012034295205 — CHITONI ME KHAI MAIDAN NIRMAN M V ME | Completed | 906000 | 455571.11 | 2016-12-21 | 2018-06-09
SHAJAPUR / SHUJALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007034/LD/नंदनवन फलोधान बापूलाल चुन्‍नीलाल चित — नंदनवन फलोधान बापूलाल चुन्‍नीलाल चितौनी | Completed | 73600 | 21885 | 2008-07-05 | 2012-12-11
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034155873 — panch parmeshwar+manrega se CC road and nali nirma | Completed | 193000 | 127320 | 2013-06-06 | 2014-05-01
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034170038 — panch parmeshwar+manrega se CC road and nali nirma | Completed | 163000 | 162126.58 | 2013-06-07 | 2015-06-25
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034201123 — CHITONI ME PP+MANREGA SE CC ROAD AND NALI NIRMAN B | Completed | 171000 | 127640 | 2014-02-01 | 2014-06-23
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007034/RC/22012034206961 — CHITONI ME KHET SADAK NIRMAN PRADHANMANTRI SADAK S | Completed | 1440000 | 1081241.5 | 2014-02-25 | 2016-01-22
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034209875 — CHITONI KE SHYAMPUR ME PP+MANREGA SE CC ROAD AND N | Completed | 171000 | 68242 | 2014-03-01 | 2014-10-22
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007034/RC/22012034211706 — CHITONI ME KHET SADAK BADLI KE GRAVEL ROAD SE AMAR | Completed | 1440000 | 1023589.7 | 2014-03-06 | 2016-06-07
SHAJAPUR / SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034282448 — cc road and nali nirman shivkumar kushwaha ke makahan se devisingh kushwaha ke makan tak | Completed | 98000 | 97989 | 2015-08-11 | 2016-01-25
SHAJAPUR / SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034291054 — C.C. Road and Nali Nirman Mukhya Sadak Se Gopal Singh Ke Ghar Tak | Completed | 104000 | 103719 | 2016-01-06 | 2016-12-03
SHAJAPUR / SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034328744 — CHITONI ME CC ROAD AND NALI NIRMAN HARIJAN BASTI AND NALA GHAR WALI GALI | Completed | 135000 | 129892 | 2017-03-08 | 2018-05-03
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034390331 — C C Road And Nali Nirman work Munshilal ke makan se P W D Road Tak | Completed | 85700 | 84962 | 2018-10-08 | 2019-05-21
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034449530 — C C Road And Nali Nirman work Laxminarayan ke ghar se Aagnwadi ke pas tak | Completed | 116621 | 83720 | 2019-03-08 | 2020-04-02
SHAJAPUR / SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034505388 — C C Road Nirman P.M. Sadak Se Kaulash Ke Makan Tak Gram Shayampur me | Completed | 92850 | 87824 | 2019-12-10 | 2020-03-20
SHAJAPUR / SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034516909 — सी सी रोड निर्माण कार्य पंचायत भवन के सामने फूलसिंह से प्रधानमंत्र्ी सडक तक | Completed | 32691 | 29220 | 2020-02-28 | 2021-09-13
SHAJAPUR / SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034552897 — C C Road And Nali Work hari singh Ke Makan Se Krashan Bai Ke Makan Tak O Aanya Galiya | Completed | 19186 | 16705 | 2021-01-24 | 2022-08-26
SHAJAPUR / SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034552900 — C C Road Nirman Work Sarvjanik Parisar Ramdev Mandir Ke pas | Completed | 47430 | 30193 | 2021-01-24 | 2023-07-11
SHAJAPUR / SHUJALPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034623635 — Harisingh ke makan se naale tak | Completed | 156000 | 153627.18 | 2022-12-24 | 2023-08-25
SHAJAPUR / SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034633612 — सीसी रोड निर्माण कार्य प्रेमसिंह के मकान से अजबसिंह के मकान तक ग्राम चितौनी | Completed | 69700 | 68982 | 2023-08-31 | 2023-10-10
SHAJAPUR / SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/22012034662462 — सी सी रोड निर्माण कार्य राम मंदिर चौक से गोवर्धन के मकान तक ग्राम चीतौनी | Completed | 29600 | 27362 | 2023-10-07 | 2024-04-18
SHAJAPUR / SHUJALPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007034/RC/2/सी0सी0 र — सी0सी0 रोड् एवं नाली निर्माण ग्राम चितोनी श्री राम मंदिर गली | Completed | 100000 | 134078 | 2011-06-08 | 2011-09-08
SHAJAPUR / SHUJALPUR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007034/RC/अर्थवर्क च — अर्थवर्क चितोनी बडली से टिटवास कांकड तक चितोनी | Completed | 0 | 495046 | 2011-09-28 | 2013-03-22
SHAJAPUR / SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007034/RS/22012034698604 — नाली निर्माण कार्य हुकमसिंह के घर से नाले तक | Completed | 78400 | 77400.01 | 2023-09-21 | 2024-04-08
SHAJAPUR / SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007034/WC/22012034424391 — Nala Trencha Nirman work | Completed | 159000 | 132029 | 2018-10-03 | 2019-08-31
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007034/WC/22012034545584 — Sokpit recharge p.s.shayampur | Completed | 14283.77 | 10260 | 2020-05-04 | 2020-09-04
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719007034/WC/22012034545585 — Sokpit recharge m.s.chitoni | Completed | 14283.77 | 10260 | 2020-05-04 | 2020-09-03
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007034/WC/22012034546340 — सामुदायिक तालाब निर्माण (चितोनी ) | Completed | 208495.76 | 206164.57 | 2020-05-11 | 2021-09-13
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Coastal Block Plantation - Farm Forestry-Community / Along the coast Block Plantation of Farm Forestry Trees for Community | Plantation | 1719007034/WC/22012034564586 — sokpit recharge p.s.school ke pass tubel kepass shayampur | Completed | 14283.77 | 8420 | 2020-07-02 | 2021-03-12
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007034/WC/22012034564594 — ROP WATET HARVSTINGH M.S.SCHOOL CHITONI | Completed | 19409.46 | 11367 | 2020-07-25 | 2021-12-23
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007034/WC/22012034805486 — रूप वाटर हार्वेस्टिग प्राथमिक विद्यालय चितोनी | Completed | 12134 | 10422 | 2021-09-14 | 2021-11-19
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007034/WC/22012034805491 — रूप वाटर हार्वेस्टिग प्राथमिक विद्यालय ग्राम श्यामपुर | Completed | 12134 | 11773 | 2021-09-14 | 2022-01-26
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007034/WC/22012034805494 — रूप वाटर हार्वेस्टिग ई कक्ष पंचायत भवन ग्राम चितोनी | Completed | 12134 | 10808 | 2021-09-14 | 2022-01-26
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007034/WC/22012034814427 — रूप वाटर हार्वेस्टिग कार्य शासकिय प्राथमिक विद्यालय ग्राम चितोनी | Completed | 12134 | 11580 | 2021-11-03 | 2022-01-17
SHAJAPUR / SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007034/WC/22012034940274 — Roof water Harvesting karya GP Chitoni | Completed | 12200 | 11544 | 2022-04-11 | 2023-07-26
SHAJAPUR / SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007034/WC/22012034940313 — Roof water Harvesting karya GP Chitoni | Completed | 12200 | 11310 | 2022-04-11 | 2023-08-17
SHAJAPUR / SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007034/WC/22012035012223 — Amrit sarovar dugout pond Gp chitoni | Completed | 918867.53 | 784545.96 | 2022-11-24 | 2025-01-03
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1719007034/WC/22012035016583 — Amrat sarovar dag pond nirman karya Chitoni 01 | Completed | 516223.68 | 420626.24 | 2022-11-24 | 2025-02-16
SHAJAPUR / SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007034/WC/22012035016585 — Amrat sarovar dag pond nirman karya Chitoni 02 | Completed | 564378.81 | 459114.92 | 2022-11-24 | 2024-07-09
SHAJAPUR / SHUJALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007034/WC/नवीनकूप निर्माण भागीरथ नारायणसिंह चि — नवीनकूप निर्माण भागीरथ नारायणसिंह चितौनी | Completed | 44000 | 92479.5 | 2008-05-11 | 2010-02-18
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719007034/WH/22012034921449 — स्टॉप डेम जीर्णोधर कार्य ग्राम चीतौनी | Completed | 9600 | 1254 | 2022-03-22 | 2023-12-30