## Work List
Exported on: 2026-10-21 14:23:12
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JAMNER
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719007041/AV/22012034566342 — Shantidham Shed Nirman Work Nadi Kinare | Physically Completed | 285945.37 | 0 | 2021-06-01 | 2026-09-09
SHAJAPUR / SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1719007041/AV/22012034662657 — पुलिया निर्माण कार्य पंचायत भवन के पास | Approved | 67000 | 0 | 2024-04-04
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1719007041/DP/22012034494191 — सामुदायिक प्‍लानटेशन कार्य खेडा से तालाब तक | Ongoing | 390826.48 | 0 | 2020-09-13
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1719007041/DP/22012034495802 — shaskiya sanjay Nikunj Nursary sthapna karya jamner | Physically Completed | 4382560 | 0 | 2020-09-17 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1719007041/DP/22012034527670 — poshan vatika Gram jamner Open Well Nirman Work Narsri ke pas | Ongoing | 571353.21 | 0 | 2021-05-22
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012034595128 — Individuals Agriculture Land Plantation Project Prakash- Laxminarayan | Physically Completed | 114410 | 0 | 2020-08-20 | 2026-10-12
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012034618197 — Individuals Agriculture Land Plantation Project Dhamendra -Kantaprasad | Physically Completed | 144900 | 0 | 2020-10-17 | 2026-10-12
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1719007041/IF/22012035017618 — निजी फलोधान राकेश पिता रामचंद्र जामनेर | Physically Completed | 125831.88 | 0 | 2023-08-26 | 2026-09-28
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1719007041/IF/22012035021077 — निजी फलोधान कार्य संतोष पिता सिद्धनाथ मालवीय | Ongoing | 125831.88 | 0 | 2023-08-25
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1719007041/IF/22012035021080 — निजी फलोधान कार्य नसरुद्दीन पिता हबीब अंशारी जामनेर | Ongoing | 125831.88 | 0 | 2023-08-29
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1719007041/IF/22012035021083 — निजी फलोधान कार्य फिरोजा बी पति बाबु खान जामनेर | Physically Completed | 152560.72 | 0 | 2023-08-27 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1719007041/IF/22012035021086 — निजी फलोधान कार्य इंदरसिंह पिता रामलाल जामनेर | Physically Completed | 125831.88 | 0 | 2023-08-29 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1719007041/IF/22012035021089 — निजी फलोधान कार्य विष्णु प्रसाद बाबूलाल जामनेर | Physically Completed | 125831.88 | 0 | 2023-08-27 | 2026-09-28
SHAJAPUR / SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035039182 — kapel dhara dev karan sankar lal | Ongoing | 256641.98 | 0 | 2023-04-20
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation - Shelter Belt for Individuals / Line Plantation of Forestry Trees for Individual | Plantation | 1719007041/IF/22012035040744 — निजी वर्क्षारोपण जुम्मा शाह पिता कासम शाह ग्राम जामनेर | Ongoing | 124084.2 | 9300 | 2023-08-27
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035206818 — कपिलधारा कूप निर्माण कार्य | New | 0 | 0 | 2024-04-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035221297 — कपिलधारा कूप निर्माण कार्य देवराज पिता प्रेमनारायण ग्राम जामनेर | Ongoing | 282417.57 | 0 | 2025-04-25
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035221301 — कपिलधारा कूप निर्माण कार्य हुकमसिंह पिता बाबूलाल ग्राम जामनेर | Ongoing | 282417.57 | 0 | 2025-04-19
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035221332 — कपिलधारा कूप निर्माण कार्य जुगल किशोर मालवीय पिता जयराम ग्राम जामनेर | Ongoing | 282417.57 | 0 | 2025-04-22
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035221338 — कपिलधारा कूप निर्माण कार्य भगवती बाई पति बाबूलाल ग्राम जामनेर | Ongoing | 282417.57 | 600 | 2025-04-19
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035221343 — कपिलधारा कूप निर्माण कार्य यूनुस खान पिता माजिद ग्राम जामनेर | Ongoing | 282417.57 | 0 | 2025-04-22
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035311131 — निजी फलौघान ऊंकार सिंह पिता बलवंत सिंह | Approved | 141756 | 0 | 2024-08-15
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035311147 — निजी फलौघान गोरीलाल पिता पुना जी | Approved | 141756 | 0 | 2024-08-15
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035332230 — खेत तालाब निर्माण कार्य पवन पिता दिलीप | Physically Completed | 407897.87 | 0 | 2025-04-17 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035332246 — खेत तालाब निर्माण कार्य मांगीलाल पिता रतनलाल | Ongoing | 407897.87 | 0 | 2025-04-18
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035332259 — खेत तालाब निर्माण कार्य नानूराम पिता रामरतन मालवीय | Physically Completed | 407897.87 | 0 | 2025-04-21 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035332274 — खेत तालाब निर्माण कार्य विष्णु प्रसाद पिता रामगोपाल | Physically Completed | 407897.87 | 0 | 2025-04-16 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1719007041/IF/22012035362850 — सामुदायिक कपिलधारा रिचार्ज पीठ स्टाफ डैम के पास wk1719007041/DP/22012034521850 | Approved | 0 | 0 | 2025-04-15
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1719007041/IF/22012035363002 — सामुदायिक कपिलधारा रिचार्ज पीठ Mata Mandir ke pass1719007041/DP/22012034487752 | Approved | 0 | 0 | 2025-04-15
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Borewell for Individual | Well Recharge | 1719007041/IF/22012035363483 — सामुदायिक कपिलधारा रिचार्ज पीठ मेला ग्राउंड 1719007041/DP/22012034484233 | Approved | 0 | 0 | 2025-04-15
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035421039 — खेत तालाब निर्माण कार्य जगदीश पिता भवानी सिंह | Physically Completed | 407897.87 | 0 | 2025-05-05 | 2026-09-28
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035421628 — खेत तालाब निर्माण कार्य कृष्ण लाल राजाराम पाटीदार | Approved | 407897.87 | 0 | 2025-04-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035421753 — खेत तालाब निर्माण कार्य बद्री लाल पिता भागीरथ | Ongoing | 407897.87 | 0 | 2025-05-02
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035423228 — खेत तालाब निर्माण कार्य मेमुना बी सलीम खान | Physically Completed | 407897.87 | 0 | 2025-05-03 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035468443 — खेत तालाब निर्माण कार्य नागेश्वर जोशी पिता बंसीलाल जामनेर | Physically Completed | 407897.87 | 0 | 2025-05-14 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007041/IF/22012035538467 — खेत तालाब निर्माण कार्य गंगा बाई पति बद्री प्रसाद | Ongoing | 407397.87 | 0 | 2025-05-29
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035545959 — कपिलधारा कूप निर्माण अंबाराम नरबत सिंह मालवीय | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035545979 — निजी फलोद्यान कार्य इस्माइल खा पिता मांगू खा | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035562152 — कपिलधारा कूप निर्माण कार्य इल्‍यास खां इशाक खां | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1719007041/IF/22012035562164 — कपिलधारा कूप निर्माण कार्य नवाबखां पिता नजरअली खां | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035598606 — Ek Bagiya Maa Ke Naam Sajan Bai MP19007041001 883 | Approved | 0 | 0 | 2025-08-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035598609 — Ek Bagiya Maa Ke Naam Shyamu Bai Malviya MP19007041001 4328 | Ongoing | 263510.03 | 12000 | 2025-09-25
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035605016 — Ek Bagiya Maa Ke Naam Girja Bai MP19007041001 1669 | Ongoing | 263510.03 | 1800 | 2025-09-18
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035605019 — Ek Bagiya Maa Ke Naam Hema Patidar MP19-007041001 1771 | Ongoing | 263510.03 | 0 | 2025-09-18
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035620831 — Ek Bagiya Maa Ke Naam Laleeta Bai MP19007041001 4330 | Ongoing | 263510.03 | 11400 | 2025-09-18
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035620836 — Ek Bagiya Maa Ke Naam Pushpaa Bai MP19007041001 1833 | Approved | 0 | 0 | 2025-08-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035620844 — Ek Bagiya Maa Ke Naam Sangeeta Patidar MP19007041001 4332 | Approved | 0 | 0 | 2025-08-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035620927 — Ek Bagiya Maa Ke Naam Rekha Bai MP19007041001 873 | Ongoing | 263511.37 | 3300 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035620946 — Ek Bagiya Maa Ke Naam Raju Bai MP19007041001 4257 | New | 0 | 0 | 2025-08-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035620955 — Ek Bagiya Maa Ke Naam Shakila Bee MP19007041001 1183-A | Ongoing | 263511.37 | 13500 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035621967 — Ek Bagiya Maa Ke Naam Upasana Malviya MP-19-007-041-001/4222 | Ongoing | 263511.37 | 11400 | 2025-11-13
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035633610 — Ek Bagiya Maa Ke Naam Prem Bai malviya MP19007041001 4159 | New | 0 | 0 | 2025-08-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1719007041/IF/22012035633621 — Ek Bagiya ma ke naam SAVATRA BAI MP19007041001 650-A | Ongoing | 263511.37 | 27000 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/2130725 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4781389 | Ongoing | 27000 | 0 | 2019-06-24
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/2199898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5246749 | Ongoing | 27000 | 0 | 2019-07-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/5620343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117720335 | Ongoing | 27000 | 0 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/5812083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106054324 | Ongoing | 27000 | 0 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/5812350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122822980 | Ongoing | 27000 | 0 | 2025-11-03
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/6252797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115938241 | Ongoing | 27000 | 300 | 2026-10-10
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/6349637 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116686435 | Ongoing | 27000 | 600 | 2026-10-10
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/6372278 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117721176 | Approved | 27000 | 0 | 2025-03-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/6372389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117719589 | Approved | 27000 | 0 | 2025-04-17
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007041/IF/IAY/6372524 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120920788 | Approved | 27000 | 0 | 2025-03-04
SHAJAPUR / SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007041/RC/22012034476529 — C C Road And Nali Nirman work Ramdev Ke Othle Se P.M. Road Tak | Ongoing | 114750 | 0 | 2019-10-24
SHAJAPUR / SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007041/RC/22012034476531 — C C Road And Nali Nieman Work P.M.m Road Se Shamshan v Maata mandir Tak | Ongoing | 140250 | 0 | 2019-10-24
SHAJAPUR / SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007041/RC/22012034476537 — C C Road And Nali Nirman work hat Bajar Se P.M. Road Tak | Ongoing | 91800 | 0 | 2019-11-04
SHAJAPUR / SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007041/RC/22012034631000 — सीसी रोड निर्माण कार्य मेन रोड से पंचायत भवन एवं आंगनवाडी की और ग्राम जामनेर | Physically Completed | 215300 | 6000 | 2025-02-14 | 2026-09-12
SHAJAPUR / SHUJALPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007041/RC/22012034631004 — सीसी रोड नाली निर्माण मेन रोड से गुलाब सिंह के मकान तक जामनेर | Ongoing | 181500 | 22800 | 2024-07-21
SHAJAPUR / SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1719007041/RS/22012034621679 — C C Nali Nirman Work Dabra Bas Stand Ke pas Gram Jamner | Ongoing | 105770 | 0 | 2022-02-11