## Work List
Exported on: 2026-10-16 04:06:28
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: RICHHODA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1719007043/DP/22012034603019 — वसुधा वंदन मेरी माटी मेरा देश ग्राम पंचायत रीछोदा | Ongoing | 55847.4 | 0 | 2023-09-16
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1719007043/IF/22012035356385 — JGSA 2025 Recharge Structure Chetan singh Devkaran1719007043/22012035356269 | New | 0 | 0 | 2025-05-14
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1719007043/IF/22012035357436 — JGSA 2025 Recharge Structure Chetan Devkaran 1719007043/IF/22012035357353 | New | 0 | 0 | 2025-05-14
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1719007043/IF/22012035465796 — open well RECHARGE STUCTURE 2025 DULARI BAI THAN SINGH | Approved | 0 | 0 | 2025-04-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1719007043/IF/22012035522542 — Khet Talab Nirman Karya Nijam Khan Pita Ajij Khan Rechoda | Approved | 408999.79 | 0 | 2025-04-14
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/3668067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115005666 | Approved | 27000 | 0 | 2022-04-30
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/3918875 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128049247 | Ongoing | 27000 | 0 | 2022-07-11
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/4212499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115808116 | Approved | 27000 | 0 | 2022-06-15
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/4225356 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303888 | Approved | 27000 | 0 | 2022-06-17
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5951149 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126651749 | Completed | 27000 | 9100 | 2026-03-28 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5952236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123525035 | Completed | 23490 | 261 | 2026-03-28 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5953584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128048390 | Completed | 23490 | 261 | 2026-03-28 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5961364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123521365 | Completed | 23490 | 1566 | 2026-05-05 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5961368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123446830 | Completed | 27000 | 10593 | 2026-05-08 | 2026-10-12
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5962139 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126631953 | Completed | 27000 | 15237 | 2026-03-28 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5962515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117307100 | Completed | 23490 | 261 | 2026-03-28 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5962726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123451831 | Completed | 27000 | 0 | 2026-04-07 | 2026-09-15
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5964115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115808222 | Completed | 27000 | 4437 | 2026-03-28 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5964116 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115808232 | Ongoing | 27000 | 10332 | 2026-03-28
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5966078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117291177 | Physically Completed | 27000 | 0 | 2026-03-28 | 2026-09-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/5966079 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117291212 | Completed | 27000 | 7550 | 2026-03-28 | 2026-10-12
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6082171 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122412903 | Physically Completed | 27000 | 6900 | 2026-05-08 | 2026-10-11
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6083687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123524164 | Completed | 27000 | 9396 | 2026-05-05 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6088400 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126608901 | Completed | 27000 | 100 | 2026-05-08 | 2026-09-22
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6288640 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126559297 | Approved | 27000 | 0 | 2026-03-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6294533 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123524701 | Approved | 27000 | 0 | 2026-03-17
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6336084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124834294 | Approved | 27000 | 0 | 2025-03-05
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6351629 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128074501 | Approved | 27000 | 0 | 2026-07-31
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6353781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123519650 | Ongoing | 27000 | 900 | 2026-10-08
SHAJAPUR / SHUJALPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1719007043/IF/IAY/6353906 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123531963 | Ongoing | 27000 | 1800 | 2026-10-08
SHAJAPUR / SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007043/RC/22012034655465 — C C Road vinod ke khet se kamla bai khet tak | Ongoing | 81651 | 0 | 2023-10-12
SHAJAPUR / SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007043/RC/22012034678141 — कवर्ड नाली निर्माण कार्य हनुमान मंदिर से मानसिंह के मकान तक | New | 0 | 0 | 2024-01-24
SHAJAPUR / SHUJALPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007043/WC/22012035216214 — कंस्ट्रक्शन ऑफ़ गबियोंन स्ट्रक्चर ग्राम Richhoda 3 | New | 0 | 0 | 2024-06-08