## Work List
Exported on: 2026-09-03 20:51:52
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: MAGRANIYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1719007050/AV/22012034373542 — Puliya Nirman Shamshan wala sotla nala | Completed | 92000 | 93786 | 2018-06-15 | 2018-07-31
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1719007050/AV/22012034400183 — shanti dham magraniya | Closed | 0 | 0 | 2019-01-26
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719007050/AV/22012034462754 — Shantidham Shed nirman work Magraniay me | Completed | 180000 | 179805 | 2019-03-10 | 2021-03-20
SHAJAPUR / SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007050/AV/22012034581994 — DYNING HALL ARRANGMENT MIDDLE SCHOOL GP MAGRNIYA | Closed | 21925.39 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007050/AV/22012034583458 — DYNING HALL ARRNAMENT MIDDLE SCHOOL GP MAGRANIYA | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007050/AV/3517 — Aanganbadi/Other Rural Infrastructure,SHUJALPUR | Completed | 180000 | 83831.02 | 2015-09-04 | 2018-07-12
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007050/DP/01/निर्मलव — निर्मलवाटिका रूगनाथसिंह जगन्‍नाथ मगरानिया | Completed | 4672 | 0 | 2010-06-17 | 2014-12-03
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/03/निर्मलव — निर्मलवाटिका बाबुलाल कनीराम मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/04/निर्मलव — निर्मलवाटिका लक्ष्‍मीनारायण देविलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-25 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/05/निर्मलव — 1719007050/DP/05/निर्मलव | Deleted | 4672 | 0 | 2010-07-18
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/05निर्मलवा — निर्मलवाटिका बद्रीलाल कषिनलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/06/निर्मलव — निर्मलवाटिका विजयसिंह भागीरथ मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/07/निर्मलव — निर्मलवाटिका पर्वतसिंह मोतीलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/08/निर्मलव — निर्मलवाटिका जगदीश छोटूलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/09/निर्मलव — निर्मलवाटिका रामप्रसाद मुन्‍नालाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-26 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/10/निर्मलव — निर्मलवाटिका देविसिंह गिरधारीलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/11/निर्मलव — निर्मलवाटिका राजेश मूलचंद मगरानिया | Completed | 4672 | 1671.73 | 2010-06-25 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/12/निर्मलव — निर्मलवाटिका भंवरजी घासीराम मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/13/निर्मलव — निर्मलवाटिका अमरसिंह भगवानसिंह मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/14/निर्मलव — निर्मलवाटिका उमरावसिंह गंगाराम मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/15निर्मलवा — निर्मलवाटिका हीरालाल गंगाराम मगरानिया | Completed | 4672 | 1671.73 | 2010-06-25 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/16/निर्मलव — निर्मलवाटिका बिहारीलाल अमरसिंह मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/17/निर्मलव — निर्मलवाटिका शंकरलाल हरजी मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/18/निर्मलव — निर्मलवाटिका प्रभुलाल पर्वतसिह मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/19निर्मलवा — निर्मलवाटिका गंगाराम हरजी मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/1निर्मलवाट — निर्मलवाटिका रूगनाथसिंह जगन्‍नाथ मगरानिया | Completed | 4672 | 1671.73 | 2010-06-25 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/20/निर्मलव — निर्मलवाटिका अर्जुन गणपत मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/21/निर्मलव — निर्मलवाटिका हीरालाल भागीरथ मगरानिया | Completed | 4672 | 1671.73 | 2010-07-03 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007050/DP/22012034242710 — Govt, Middle School Ground Plantation Magraniya | Closed | 335000 | 0 | 2017-05-29
SHAJAPUR / SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007050/DP/22012034407028 — Vracharpan PM Sadak Se Mata mandir Eariya Me | Deleted | 342000 | 1044 | 2018-06-19
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007050/DP/22012034529899 — Plantation van abhyaran magraniya | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007050/DP/22012034545409 — MAA KI BAGIYA MIDDLE SCHOOL GP magrniya | Completed | 9619.45 | 9092.73 | 2022-02-13 | 2023-07-21
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007050/DP/22012034546946 — MA KI BAGIYA NIRMAN KARY P.VIDHALAY MAGRANIYA | Closed | 0 | 0 | 2021-10-21
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007050/DP/22012034602794 — वसुधा वंदन मेरी माटी मेरा देश ग्राम पंचायत मगरानीया | Deleted | 55847.4 | 10 | 2023-10-08
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007050/DP/22012034603088 — वसुधा वंदन मेरी माटी मेरा देश ग्राम पंचायत मगरानीया | Closed | 0 | 0 | 2023-08-01
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/22/निर्मलव — निर्मलवाटिका गिरधारी नंदराम मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/23/निर्मलव — निर्मलवाटिका पर्वतसिंह रामलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/24/ निर्मल — निर्मलवाटिका भगवतबाई मोहनलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/25/निर्मलव — निर्मलवाटिका मोहनलाल नारायणसिंह मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/26/निर्मलव — निर्मलवाटिका राजाराम लालजीराम मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/27/निर्मलव — निर्मलवाटिका देविसिंह रामलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/28/निर्मलव — निर्मलवाटिका शिवनारायण नन्‍नूलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/29/निर्मलव — निर्मलवाटिका गणपतसिंह भगवान मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/2/निर्मलवा — निर्मलवाटिका राधेलाल छोटेलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/30/निर्मलव — निर्मलवाटिका भागीरथ बोंदाजी मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/31/निर्मलव — निर्मलवाटिका सिद्वनाथ गिरधारी मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/32/निर्मलव — निर्मलवाटिका राधेलाल कनीराम मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/33/निर्मलव — निर्मलवाटिका राजाराम जगन्‍नाथ मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/34/निर्मलव — निर्मलवाटिका मांगीलाल रामलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/35/निर्मलव — निर्मलवाटिका बद्रीलाल पर्वतसिंह मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/36निर्मलवा — निर्मलवाटिका भेरूसिंह रामलाल मगरानिया | Completed | 4672 | 1671.73 | 2010-07-02 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/37/ निर्मल — निर्मलवाटिका रतनासिंह काशीराम मगरानिया | Completed | 4672 | 1671.73 | 2010-06-23 | 2011-12-29
SHAJAPUR / SHUJALPUR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007050/DP/9993628648 — varcharopan karya badli per | Deleted | 315000 | 0 | 2015-07-23
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719007050/DW/22012034293682 — SARVJANIK KOOP NIRMAN TALAI KE NIKAT GRAM MAGRANIA | Deleted | 439000 | 0 | 2017-01-13
SHAJAPUR / SHUJALPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1719007050/DW/22012034293712 — MAGRANIA ME SARWAJANIK KOOP NIRMAN TALAI KE PASS | Deleted | 439000 | 0 | 2016-01-26
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034334856 — HITESHI KAPILDHARAKUP SAHA KHEAT TALAB CHANDRAKALABAI RAMCHARAN G.P. MAGRANIYA | Closed | 232000 | 0 | 2017-04-23
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034338541 — HITESHI kapildhara saha khet talab BHURIBAI s% MUKESH JAT | Completed | 234600 | 224884 | 2017-05-30 | 2019-06-23
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007050/IF/22012034352856 — PLANTATION GP MAGRANIYA | Completed | 335000 | 119224 | 2017-07-13 | 2022-01-20
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034416037 — kapildharakup babulal bakshilal | Completed | 210000 | 208968 | 2018-06-11 | 2019-08-25
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034416909 — kapildharakup mohan kumawat gehalot | Completed | 210000 | 208824 | 2018-06-11 | 2019-03-08
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034470428 — KAPILDHARA KOOP CHANDRAKALA BAI PATI RAMCHARAN | Completed | 214200 | 166656 | 2019-03-05 | 2022-01-20
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034471899 — Khet Talab Nirman work Mohanlal/kumer singh | Completed | 295000 | 188148 | 2019-03-07 | 2019-06-05
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034472374 — Khet Talab Nirman wprk Dev bai/madho singh | Suspended | 295000 | 0 | 2019-03-07
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034525945 — Kapildhara kup gangaram | Closed | 0 | 0 | 2020-01-26
SHAJAPUR / SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007050/IF/22012034525947 — Khet talab | Closed | 0 | 0 | 2020-01-26
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007050/IF/22012034578013 — खेत समतलीकरण कैलाश पिता रमेश जाट | Closed | 107764.03 | 0 | 2020-04-01
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1719007050/IF/22012034578015 — खेत समतलीकरण बद्रीलाल ि‍पिता भवर जी | Closed | 108303.14 | 0 | 2020-04-01
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007050/IF/22012034593556 — Individuals Agriculture Land Plantation Project Rambabu-karan singh | Completed | 144900 | 79738 | 2020-08-14 | 2025-02-18
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007050/IF/22012034593557 — Individuals Agriculture Land Plantation Project Manisha bai-Ramprasad | Completed | 144900 | 75376 | 2020-08-14 | 2025-01-18
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007050/IF/22012034597044 — Individuals Agriculture Land Plantation Project Sunita Bai | Completed | 114410 | 55580 | 2020-08-14 | 2025-01-18
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034622092 — Niji khet talab nirman brajmohan jadav | Deleted | 0 | 0 | 2020-10-02
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034622094 — Niji khet talab nirman mangilal jagnath | Completed | 332962.02 | 254469 | 2020-11-18 | 2022-08-01
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034623048 — Niji khet talab dinesh dariyavsingh | Deleted | 0 | 0 | 2020-10-02
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034623840 — निजी खेत तालाब ब्रजमोहन भगीरथ | Completed | 332962.02 | 273696 | 2020-11-18 | 2022-08-01
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034623841 — निजी खेत तालाब दिनेश दरियाव सिंह | Completed | 332962.02 | 260599 | 2020-11-18 | 2025-05-15
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034652137 — Khet Talab Nirman Work Babulal | Closed | 0 | 0 | 2020-10-02
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/IF/22012034652138 — Khet Talab Nirman Work Devi Singh | Closed | 0 | 0 | 2020-10-02
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034652156 — Kapil dhara Kup Nirman work Gokal Singh | Closed | 0 | 0 | 2020-10-02
SHAJAPUR / SHUJALPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012034652160 — Kapil dhara Kup Nirman work Prahlad Singh | Closed | 0 | 0 | 2020-10-02
SHAJAPUR / SHUJALPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007050/IF/22012035205889 — कपिलधारा कूप निर्माण जुझारसिंह मेवाडा | New | 0 | 0 | 2024-01-27
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007050/IF/22012035479077 — Jgsa2025 Recharge structure Kapildhara kup Rameshvar bakshilal | Completed | 23899.46 | 21249.77 | 2025-05-10 | 2026-04-26
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007050/IF/22012035485234 — JGSA RECHARGE STRUCTURE KAPILDHARA RAMBABU KARANSINGH | Completed | 23899.46 | 20449.61 | 2025-05-12 | 2026-04-26
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007050/IF/22012035485332 — JGSA RECHARGE STRUCTURE KAPILDHARA CHANDRAKLA BAI | Completed | 23899.46 | 22088.87 | 2025-05-10 | 2026-03-04
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012035530852 — कपिलधारा कूप निर्माण कार्य लक्ष्मीनारायण पिता मनुदास ग्राम मगरानिया | Ongoing | 289832.38 | 179187.7 | 2025-05-30
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/22012035530868 — कपिलधारा कूप निर्माण कार्य भंवरजी पिता घिसाजी ग्राम मगरानिया | Closed | 289832.38 | 261 | 2025-05-30
SHAJAPUR / SHUJALPUR | 2010-2011 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007050/IF/7/नवीनकूप — नवीनकूप निर्माण ram babu kransingh Magrnaiya | Completed | 166000 | 191259 | 2011-02-10 | 2012-03-09
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719007050/IF/9993713017 — PASU SHED | Deleted | 0 | 0 | 2016-04-01
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/1916276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4174998 | Completed | 15660 | 15312 | 2018-08-31 | 2018-12-20
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/1916681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4701744 | Completed | 15660 | 15312 | 2018-08-31 | 2018-12-24
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/1916682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4701803 | Completed | 15660 | 15312 | 2018-08-31 | 2018-12-24
SHAJAPUR / SHUJALPUR | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/1927163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5587648 | Completed | 15660 | 15312 | 2018-09-28 | 2018-12-24
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2101696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4175007 | Completed | 15840 | 15840 | 2019-07-18 | 2020-01-07
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2127942 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4734062 | Completed | 15840 | 15488 | 2019-07-18 | 2019-10-10
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2130429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4774428 | Completed | 15840 | 15840 | 2019-07-18 | 2020-01-20
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2139494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5006260 | Completed | 15840 | 15488 | 2019-09-04 | 2020-05-20
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2164057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5621599 | Completed | 15840 | 15456 | 2019-11-15 | 2020-06-20
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2164234 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5625801 | Completed | 15840 | 15840 | 2019-07-18 | 2020-05-20
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2164355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5629077 | Completed | 15840 | 15840 | 2019-07-18 | 2019-12-28
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2164671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5639403 | Completed | 15840 | 15792 | 2019-08-15 | 2020-05-20
SHAJAPUR / SHUJALPUR | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/2325013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5587701 | Completed | 15840 | 15552 | 2019-12-26 | 2020-07-01
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/3696622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114739250 | Completed | 18360 | 18360 | 2022-11-07 | 2023-02-06
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/3805889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114739293 | Completed | 18360 | 18360 | 2022-11-07 | 2023-02-06
SHAJAPUR / SHUJALPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/3817215 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117324231 | Completed | 18360 | 18122 | 2023-05-13 | 2023-08-09
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/407217 — Construction of IAY House -IAY REG. NO. MP1240392 | Completed | 15030 | 15136 | 2017-07-09 | 2018-04-07
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/415589 — Construction of IAY House -IAY REG. NO. MP1298499 | Completed | 15030 | 15253 | 2017-02-23 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/4168745 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114005020 | Completed | 18360 | 17544 | 2022-07-01 | 2022-10-27
SHAJAPUR / SHUJALPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/4227515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119880682 | Completed | 18360 | 17544 | 2022-07-17 | 2022-11-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/429686 — Construction of IAY House -IAY REG. NO. MP1392165 | Completed | 15030 | 15450 | 2017-02-07 | 2018-02-15
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/430867 — Construction of IAY House -IAY REG. NO. MP1400245 | Completed | 15030 | 15133 | 2017-02-23 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/4551279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113851371 | Completed | 23490 | 23274 | 2025-02-05 | 2025-09-30
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/4555423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114005279 | Completed | 23490 | 21384 | 2024-12-12 | 2025-07-15
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/455731 — Construction of IAY House -IAY REG. NO. MP1636764 | Completed | 15030 | 15106 | 2017-03-07 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/455951 — Construction of IAY House -IAY REG. NO. MP1638856 | Completed | 15030 | 15126 | 2017-02-23 | 2018-03-11
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/456302 — Construction of IAY House -IAY REG. NO. MP1642819 | Completed | 15030 | 15136 | 2017-02-03 | 2018-04-07
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/456684 — Construction of IAY House -IAY REG. NO. MP1647025 | Completed | 15030 | 15253 | 2017-02-23 | 2018-02-15
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/459541 — Construction of IAY House -IAY REG. NO. MP1682707 | Completed | 15030 | 15136 | 2017-03-01 | 2018-03-11
SHAJAPUR / SHUJALPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/460394 — Construction of IAY House -IAY REG. NO. MP1696578 | Completed | 15030 | 15136 | 2017-04-02 | 2018-02-15
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/4659512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148162765 | Completed | 23490 | 21717 | 2024-12-12 | 2025-08-12
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/4861871 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115165541 | Completed | 23490 | 21924 | 2025-02-21 | 2026-03-04
SHAJAPUR / SHUJALPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/4884505 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114773540 | Completed | 23490 | 22518 | 2025-02-05 | 2025-10-31
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/496925 — Construction of IAY House -IAY REG. NO. MP2218392 | Completed | 15030 | 15278 | 2017-03-01 | 2018-02-15
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/501430 — Construction of IAY House -IAY REG. NO. MP2270782 | Completed | 15030 | 15163 | 2017-02-23 | 2018-02-15
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/501515 — Construction of IAY House -IAY REG. NO. MP2272332 | Completed | 15030 | 15086 | 2017-02-07 | 2018-02-15
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/510281 — Construction of IAY House -IAY REG. NO. MP2382973 | Completed | 15030 | 15308 | 2017-02-07 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/510366 — Construction of IAY House -IAY REG. NO. MP2383880 | Completed | 15030 | 15131 | 2017-02-07 | 2018-03-11
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5167643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114004977 | Completed | 23490 | 23490 | 2025-04-16 | 2025-09-30
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/518073 — Construction of IAY House -IAY REG. NO. MP2510279 | Completed | 15030 | 15128 | 2017-03-14 | 2018-03-11
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/518187 — Construction of IAY House -IAY REG. NO. MP2512815 | Completed | 15030 | 15784 | 2017-03-01 | 2017-12-25
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/518353 — Construction of IAY House -IAY REG. NO. MP2516267 | Completed | 15030 | 15136 | 2017-02-07 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/519442 — Construction of IAY House -IAY REG. NO. MP2541632 | Completed | 15030 | 15253 | 2017-02-07 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/520092 — Construction of IAY House -IAY REG. NO. MP2556382 | Completed | 15030 | 14966 | 2017-02-10 | 2017-10-20
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5217807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117430880 | Completed | 23490 | 22707 | 2025-04-16 | 2025-10-31
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5219392 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114005230 | Completed | 23490 | 23490 | 2025-04-16 | 2025-09-30
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5240173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117271702 | Completed | 23490 | 23490 | 2025-04-16 | 2025-10-09
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/535361 — Construction of IAY House -IAY REG. NO. MP2939164 | Completed | 15030 | 15360 | 2017-02-07 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/535679 — Construction of IAY House -IAY REG. NO. MP2946955 | Completed | 15030 | 15330 | 2017-02-07 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/535699 — Construction of IAY House -IAY REG. NO. MP2947314 | Completed | 15030 | 15450 | 2017-03-01 | 2017-12-30
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/536563 — Construction of IAY House -IAY REG. NO. MP2972796 | Completed | 15030 | 15128 | 2017-02-07 | 2018-04-07
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/54630 — Construction of IAY House -IAY REG. NO. MP-19-007-050-002/17 | Completed | 14310 | 11750 | 2016-07-01 | 2018-05-02
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/54631 — Construction of IAY House -IAY REG. NO. MP-19-007-050-002/26 | Completed | 14310 | 10110 | 2016-07-01 | 2018-05-02
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/548225 — Construction of IAY House -IAY REG. NO. MP3310808 | Completed | 15030 | 15234 | 2017-03-14 | 2018-11-08
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/548227 — Construction of IAY House -IAY REG. NO. MP3310958 | Completed | 15030 | 15066 | 2017-02-10 | 2018-05-02
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/548298 — Construction of IAY House -IAY REG. NO. MP3313078 | Completed | 15030 | 15253 | 2017-02-23 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5519338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122793392 | Completed | 23490 | 23490 | 2025-05-20 | 2025-10-08
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5522199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115125725 | Completed | 23490 | 21629 | 2025-05-20 | 2025-10-31
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/560896 — Construction of IAY House -IAY REG. NO. MP3694412 | Completed | 15030 | 15253 | 2017-02-10 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/566079 — Construction of IAY House -IAY REG. NO. MP3894837 | Completed | 15030 | 15158 | 2017-03-01 | 2018-04-07
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/566083 — Construction of IAY House -IAY REG. NO. MP3894910 | Completed | 15030 | 15193 | 2017-02-23 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/567637 — Construction of IAY House -IAY REG. NO. MP3957232 | Completed | 15030 | 15131 | 2017-02-10 | 2018-03-01
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5715590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119880353 | Ongoing | 27000 | 21579 | 2025-10-08
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5733383 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114773579 | Physically Completed | 23490 | 23229 | 2025-09-27 | 2026-04-19
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5811720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115108506 | Completed | 23490 | 23490 | 2025-09-27 | 2025-12-26
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5812053 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119880434 | Physically Completed | 23490 | 21924 | 2025-09-27 | 2025-12-10
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5812519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119883668 | Physically Completed | 23490 | 23229 | 2025-10-10 | 2026-06-14
SHAJAPUR / SHUJALPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/5861463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115111123 | Ongoing | 27000 | 22623 | 2026-01-06
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/613300 — Construction of IAY House -IAY REG. NO. MP1636813 | Completed | 15030 | 15136 | 2017-03-01 | 2018-03-11
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/617402 — Construction of IAY House -IAY REG. NO. MP2970457 | Completed | 15030 | 15450 | 2017-03-01 | 2017-11-01
SHAJAPUR / SHUJALPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007050/IF/IAY/617404 — Construction of IAY House -IAY REG. NO. MP2970911 | Completed | 15030 | 15248 | 2017-03-01 | 2018-02-15
SHAJAPUR / SHUJALPUR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007050/LD/2014 — ग्रामीण क्रीडागन खेल मैदान स्‍कूल परिसर मगरानिया | Completed | 190000 | 189803 | 2012-05-29 | 2015-02-16
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1719007050/LD/22012034565583 — Cpt nirman kary van abhyaran magraniya | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034155014 — sansad nidhi+manrega se CC road and nali nirman panchayat bhawan se shantilal ke makan tak dehandi | Deleted | 0 | 0 | 2012-11-19
SHAJAPUR / SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034155881 — panch parmeshwar+manrega se CC road and nali nirman laxminarayan ke makan se sotla hand pupm tak | Deleted | 0 | 0 | 2012-11-01
SHAJAPUR / SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034155882 — panch parmeshwar+manrega se CC road and nali nirman dhansingh ke makan se ramprasad ke makan tak | Deleted | 0 | 0 | 2012-11-01
SHAJAPUR / SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034155883 — panch parmeshwar+manrega se CC road and nali nirman panchayat bhawan se shankar ke makan tak | Deleted | 0 | 0 | 2012-11-01
SHAJAPUR / SHUJALPUR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007050/RC/22012034155884 — grawal road shantidham tak | Deleted | 0 | 0 | 2012-11-01
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034195651 — MAGRANIA ME PP+MANREGA SE CC ROAD AND NALI NIRMAN | Completed | 203000 | 202232 | 2013-12-26 | 2015-02-17
SHAJAPUR / SHUJALPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1719007050/RC/22012034221988 — magraniya me pp+manrega se cc road and nali nirman | Completed | 219000 | 213183 | 2014-09-08 | 2015-02-17
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034221989 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26
SHAJAPUR / SHUJALPUR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034221990 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26
SHAJAPUR / SHUJALPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007050/RC/22012034223012 — MAGRANIA ME KHET SADAK PRADHANMANTRI SADAK SE MOHA | Deleted | 1440000 | 0 | 2014-06-25
SHAJAPUR / SHUJALPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034230557 — cc raod avam nali nirman avaas colony se parisar me | Completed | 124600 | 124564 | 2014-09-30 | 2014-12-25
SHAJAPUR / SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034299142 — CC ROAD | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034299536 — CC ROAD NALI NIRMAN | Closed | 0 | 0 | 2016-01-26
SHAJAPUR / SHUJALPUR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034312449 — cc nali nirman beragarh mohalla magraniya | Deleted | 0 | 0 | 2015-12-12
SHAJAPUR / SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034312450 — cc nali nirman beragarh mohala | Completed | 159000 | 155670 | 2016-05-16 | 2017-03-30
SHAJAPUR / SHUJALPUR | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034320841 — cc road and nali nirman | Closed | 0 | 0 | 2016-08-15
SHAJAPUR / SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007050/RC/22012034369675 — SUDUR SAMPARK SADAK YOJNA MAGRANIYA | Closed | 0 | 0 | 2018-01-26
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034393609 — C C ROAD AND NALI NIRMAN WORK BANSHILAL SE MUNSHILAL KE GHAR TAK | Completed | 70000 | 70470 | 2018-09-29 | 2019-05-15
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034439699 — cc road and nali nirman | Closed | 0 | 0 | 2019-01-26
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034443362 — सी सी रोड निर्माण हेण्‍डपम्‍प से राजू तमोली के मकान तक | Completed | 49600 | 49546 | 2019-03-01 | 2019-08-26
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034449096 — C C Road And Nali Nirman work Hendpamp se puliya Tak | Completed | 104036 | 101540 | 2019-03-05 | 2020-05-31
SHAJAPUR / SHUJALPUR | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034449097 — C C Road And Nali Nirman work Aambaram se Hiralal ke Ghar Tak | Completed | 165364 | 161352 | 2019-03-04 | 2020-05-31
SHAJAPUR / SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034512109 — C C Road Nirman Work Holi Tekar Se vabal Singh ke Makan Tak | Completed | 155092 | 155100 | 2020-01-05 | 2021-12-06
SHAJAPUR / SHUJALPUR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034512110 — C C Road Nirman Work Aabaram Se Puliya tak | Completed | 118000 | 118063 | 2020-01-05 | 2021-12-06
SHAJAPUR / SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007050/RC/22012034554234 — Aproch Road Nirman Work Radheshyam Ke Makan Se Shamshan Tak | Ongoing | 1495314.87 | 629230.78 | 2021-02-02
SHAJAPUR / SHUJALPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034561438 — C C Road And nali Nirman Work P M Road Se Aadbhut Tekari Par | Completed | 39324 | 38694 | 2021-03-17 | 2023-07-14
SHAJAPUR / SHUJALPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034620903 — सीसी रोड निर्माण कार्य देवनारायण सेन के घर से अम्बाराम के घर तक | Completed | 47850 | 39576 | 2022-12-03 | 2024-01-06
SHAJAPUR / SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007050/RC/22012034631338 — सीसी रोड निर्माण कार्य नाले के पास से मोहन कुमेर सिंह मेवाडा तक | Closed | 47000 | 442 | 2023-10-05
SHAJAPUR / SHUJALPUR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Anganwadi Toilets / Construction of Anganwadi Multi Unit Toilets for Community | Construction of Toilets | 1719007050/RS/22012034275347 — Nala nirman work gram magraniya me sotala nala nir | Completed | 202000 | 201728.84 | 2014-10-17 | 2015-10-07
SHAJAPUR / SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007050/RS/22012034358072 — TOILET GP MAGRANIYA | Completed | 192000 | 146584 | 2017-07-25 | 2018-07-24
SHAJAPUR / SHUJALPUR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007050/RS/22012034379379 — SHOCHALAY NIRMAN 2 MAGRANIYA | Closed | 0 | 0 | 2017-08-15
SHAJAPUR / SHUJALPUR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007050/RS/22012034691766 — सीसी नाली निर्माण कार्य देवनारायण के घर से अम्बाराम के घर तक | Closed | 32000 | 0 | 2022-10-02
SHAJAPUR / SHUJALPUR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007050/RS/22012035124778 — नाली निर्माण कार्य रमेश के घर से सियाराम के घर तक एवं कैलाश के घर से पुलिया तक ग्राम मगरानीय | Ongoing | 103500 | 75784 | 2024-03-07
SHAJAPUR / SHUJALPUR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1719007050/WC/18/??????? — 1719007050/WC/18/ | Completed | 0 | 101053.44 | 2012-05-29 | 2013-09-22
SHAJAPUR / SHUJALPUR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007050/WC/18/सार्वजन — सार्वजनिक कुप निर्माण lamdya maharaj magraniya | Completed | 363000 | 253302.17 | 2011-02-23 | 2013-06-23
SHAJAPUR / SHUJALPUR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007050/WC/1/बोल्‍डर — बोल्‍डर चैक डेम रोड वाले नाले पर मगरानिया | Completed | 300000 | 90792 | 2011-05-26 | 2013-03-25
SHAJAPUR / SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007050/WC/22012034424043 — Nala trenches nirman work Sorla Nala | Deleted | 157000 | 174 | 2018-10-01
SHAJAPUR / SHUJALPUR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1719007050/WC/22012034436120 — CC ROAD | Closed | 0 | 0 | 2019-01-26
SHAJAPUR / SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007050/WC/22012034477671 — sokt pit aganvadi bhavan magraniya | Closed | 0 | 0 | 2019-06-07
SHAJAPUR / SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007050/WC/22012034477675 — sokt pits shala bhavan magraniya | Completed | 20319.4 | 7833 | 2019-08-27 | 2022-01-31
SHAJAPUR / SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007050/WC/22012034480800 — Soka pit Gagdde work Sarvajik Parisar me | Closed | 13427.22 | 0 | 2019-07-25
SHAJAPUR / SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007050/WC/22012034480982 — Soka Pit Gadde work Nirman Savjanik Parisar me Soka Pit Gadde work Nirman Savjanik Parisar me | Closed | 13427.22 | 0 | 2019-07-25
SHAJAPUR / SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007050/WC/22012034481090 — Soka Pit gadde Sarvajnik Parisar Me | Closed | 13427.22 | 0 | 2019-07-25
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007050/WC/22012034751764 — Richarge pit shaskiy kup ke pas | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007050/WC/22012034775776 — Talab nirman karya van abhyaran Magrania | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007050/WC/22012034775778 — Talab nirman karya van abhyaran Magrania | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007050/WC/22012034775779 — Talab nirman karya van abhyaran Magrania | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719007050/WC/22012034776445 — Contour trench nirman magraniya pahadi | Closed | 194024.54 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1719007050/WC/22012034776447 — Contour trench nirman magraniya pahadi | Closed | 0 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719007050/WC/22012034780323 — Construction Of Tank Van Abhyaran Magraniya 1 | Closed | 470300.89 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719007050/WC/22012034780325 — Construction Of Tank Van Abhyaran Magraniya 2 | Closed | 470300.89 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719007050/WC/22012034780330 — Construction Of Tank Van Abhyaran Magraniya 3 | Closed | 470300.89 | 0 | 2021-04-14
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007050/WC/22012034813019 — रूप वाटर हार्वेस्टिग कार्य शासकिय प्राथमिक विद्यालय ग्राम मगरानिया | Completed | 12134 | 11966 | 2021-10-15 | 2022-08-01
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007050/WC/22012034813020 — रूप वाटर हार्वेस्टिग कार्य शासकिय माध्यमिक विद्यालय ग्राम मगरानिया | Completed | 12134 | 11966 | 2021-11-26 | 2022-08-01
SHAJAPUR / SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1719007050/WC/22012034940589 — 1719007019/WC/22012034940583 | Closed | 0 | 0 | 2022-04-01
SHAJAPUR / SHUJALPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007050/WC/22012034944370 — Sokt pit gp magraniya 2 | Closed | 0 | 0 | 2022-04-09
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1719007050/WC/22012035271713 — JGSA Recharge Structure Samudayik koop 1719007050/WC/22012035271693 | Physically Completed | 23899.46 | 7821.92 | 2025-05-03 | 2026-04-16
SHAJAPUR / SHUJALPUR | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007050/WC/नवीन कूप निर्माण भागीरथ बोंदा मगरानि — नवीन कूप निर्माण भागीरथ बोंदा मगरानिया | Completed | 44000 | 92437 | 2008-05-21 | 2010-03-31
SHAJAPUR / SHUJALPUR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719007050/WH/19959735 — Renovation of Tank PM Road ke pass | Completed | 354000 | 351932.1 | 2017-05-29 | 2019-07-29
SHAJAPUR / SHUJALPUR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007050/WH/22012034442269 — Rinovation of tenk talai | Closed | 0 | 0 | 2020-01-26
SHAJAPUR / SHUJALPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007050/WH/22012034445876 — Talab Renovtion khadan vala | Closed | 0 | 0 | 2020-10-02
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007050/WH/22012034452038 — RENOVATION OF MAGRANIYA TALAB G.P MAGRANIYA | Closed | 0 | 0 | 2021-08-18
SHAJAPUR / SHUJALPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1719007050/WH/22012034455709 — talab renovation khadana vala gram pan.magraniya | Completed | 291912.44 | 107089 | 2022-02-09 | 2025-01-18