## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719007071/AV/22012034371603 — SHANTIDHAMA SHED NIRAM WORK BATWADI | Completed | 180000 | 178607.92 | 2018-01-20 - 2018-04-28
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1719007071/AV/22012034447730 — शांतिधाम परिसर का समतलीकरण ग्राम बटवाडी | Completed | 318000 | 262923 | 2019-03-04 - 2021-12-22
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007071/AV/22012034597180 — DYNING HALL ARANEMENT AT MIDDLE SCHOOL GP Batwadi | Deleted | 19487.5 | 386 | 2021-10-03 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719007071/AV/22012034597198 — DYNING HALL ARANEMENT AT Primary school GP Batwadi | Deleted | 19487.5 | 386 | 2021-10-03 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/10निर्मलवा — निर्मलवाटिका सुरेशदास विष्‍णुदास बटवाडी | Completed | 4672 | 2565 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/11निर्मलवा — निर्मलवाटिका रमेशचंद्र अमरसींह बटवाडी | Completed | 4672 | 2464 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/12निर्मलवा — निर्मलवाटिका शंकरलाल पन्‍नालाल बटवाडी | Completed | 4672 | 2465 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/13निर्मलवा — 1719007071/DP/13निर्मलवा | Completed | 0 | 1308 | 2010-07-14 - 2014-12-03
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/14निर्मल व — निर्मल वाटिका देविलाल छीताजी बटवाडी | Completed | 4672 | 1157 | 2010-08-10 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/14निर्मलवा — 1719007071/DP/14निर्मलवा | Completed | 4672 | 1306 | 2010-07-14 - 2014-12-03
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/15निर्मलवा — निर्मलवाटिका सुमनबाई रामलाल बटवाडी | Completed | 4672 | 2465 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/16निर्मलवा — निर्मलवाटिका रमेश जगाजी बटवाडी | Completed | 4672 | 2563 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/17निर्मलवा — निर्मलवा‍टिका रामप्रसाद देविलाल बटवाडी | Completed | 4672 | 2565 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/18निर्मलवा — निर्मलवा‍टिका सुरेश भेरूलाल बटवाडी | Completed | 4672 | 2565 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/19निर्मल व — निर्मल वाटिका बदरूद्वीन युसुफखां ‍बटवाडी | Completed | 4672 | 1257 | 2010-08-10 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/19निर्मलवा — निर्मलवा‍टिका शिवनारायण लक्ष्‍मण बटवाडी | Completed | 4672 | 2465 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/1निर्मलवाट — निर्मलवाटिका कुंवरजी बाबलजी बटवाडी | Completed | 4672 | 2513 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/20निर्मलवा — निर्मलवा‍टिका गोराबाई सेवाराम बटवाडी | Completed | 4672 | 2563 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/21निर्मलवा — निर्मलवा‍टिका रामकुंवरबाई मांगीलाल बटवाडी | Completed | 4672 | 2565 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007071/DP/22012034243334 — SADAK KINARE HADLAY JOD SE BATWADI JOD TAK | Deleted | 33500000000 | 0 | 2017-06-04 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007071/DP/22012034244178 — plantation badodrana | Deleted | 33500000000 | 0 | 2017-06-11 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007071/DP/22012034406871 — Vracharopan santi dham parisar batwari | Ongoing | 342000 | 97922 | 2018-06-11 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1719007071/DP/22012034590522 — PLANTATION WORK MERI MATI MERA DESH | Closed | 55847.4 | 2327 | 2023-09-09 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/22निर्मलवा — निर्मलवा‍टिका क़पालसिंह भागीरथ बटवाडी | Completed | 4672 | 2463 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/23निर्मलवा — निर्मलवा‍टिका केलाश भागीरथ बटवाडी | Completed | 4672 | 2513 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/2निर्मलवाट — निर्मलवाटिका रमेश सिद्वुलाल बटवाडी | Completed | 4672 | 2514 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/3निर्मलवाट — निर्मलवाटिका कुसुबाई भेरूलाल बटवाडी | Completed | 4672 | 2513 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/4निर्मलवाट — निर्मलवाटिका राजूबाई अमरसिंह बटवाडी | Completed | 4672 | 2515 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/5निर्मलवाट — निर्मलवाटिका मानूसिंह भागीरथ बटवाडी | Completed | 4672 | 2513 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/6निर्मलवाट — निर्मलवाटिका गोविन्‍द अमरसिंह बटवाडी | Completed | 4672 | 2563 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/7निर्मलवाट — निर्मलवाटिका प्रेमनारायण देवीलाल बटवाडी | Completed | 4672 | 2563 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/8निर्मलवाट — निर्मलवाटिका रामचंद्र पन्‍नालाल बटवाडी | Completed | 4672 | 2565 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1719007071/DP/9निर्मलवाट — निर्मलवाटिका देवकरण प्रेमसिंह बटवाडी | Completed | 4672 | 2563 | 2010-07-14 - 2011-12-24
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012034357269 — plantation batwadi purusottam s/o karansingh | Completed | 335000 | 45482 | 2017-06-30 - 2020-10-01
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012034357959 — PLANTATION GP BATWADI GRAM BADODRANA AT SHANTIDHAM | Completed | 335000 | 34842 | 2017-07-02 - 2020-09-19
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007071/IF/22012034438221 — kapildhara kup kumersingh/ghisaji | Completed | 214200 | 209920 | 2018-10-05 - 2019-08-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007071/IF/22012034464602 — KAPILDHARA KUP NIRMAAN (RAJMAL S/O KUNWARJI) | Completed | 210000 | 209796 | 2019-03-01 - 2019-08-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012034471462 — Khet Talab Nirman work Kameri bai/Bhanwar lal | Completed | 295000 | 276124 | 2019-03-06 - 2019-06-30
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012034472567 — Khet Talab Nirman work Aantae singh/Kumer singh | Completed | 295000 | 288696 | 2019-03-08 - 2019-06-30
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1719007071/IF/22012034605500 — NIJI FALODHYAN JAGDISH KUMERSINGH | Deleted | 0 | 0 | 2020-08-15 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coast Line plntation of Forestry Trees-Individuals / Along the coast Line Plantation of Forestry Trees for Individuals | Plantation | 1719007071/IF/22012034605503 — NIJI FALODHYAN JAGDISH KUMERSINGH | Completed | 114410 | 98824 | 2020-09-04 - 2024-07-10
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007071/IF/22012034693591 — Kapildharakup devkaran s/o ramprasad | Completed | 338267.21 | 322350 | 2021-04-23 - 2024-10-24
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1719007071/IF/22012034767795 — Recharge pit deep singh | Deleted | 14467.3 | 772 | 2021-06-03 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007071/IF/22012034767831 — Recharge pit Jagdish kumer | Closed | 15140.3 | 0 | 2021-04-14 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012034960548 — KHET TALAB NIRMAAN | Closed | 356340.1 | 0 | 2022-04-01 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012034970782 — KHET TALAB NIRMAAN(MNGILAL AMARSINGH) | Completed | 356340.1 | 268328 | 2022-05-11 - 2024-02-17
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012035196974 — khet talab lakhan sitaram | Ongoing | 349700.58 | 12 | 2024-03-11 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007071/IF/22012035219451 — kapil dhara kup - kamal singh-khushilal | Completed | 330281.59 | 315744 | 2024-03-14 - 2025-07-08
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007071/IF/22012035298715 — Kapildhara kup Sandeep tewa bhimpura | Ongoing | 282497.49 | 195154.75 | 2025-02-20 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007071/IF/22012035309446 — Kapildhara kup vinod kunwarji batwadi | Ongoing | 299242.08 | 208024 | 2025-03-29 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1719007071/IF/22012035312124 — Kapildhara Kup kalusingh ghasiram bhimpura | Ongoing | 308066.08 | 220878 | 2025-03-30 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007071/IF/22012035357324 — JGSA RECHARGE STRUCTURE KAPILDHARA KUP DEVKARAN RAMPASAD1719007071/22012034693591 | Completed | 23899.46 | 21254.14 | 2025-04-24 - 2026-01-15
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007071/IF/22012035357665 — JGSA RECHARGE STRUCTURE KAPILDHARA KUP KUMERSINGH GHISAJI 1719007071/22012034438221 | Completed | 23899.46 | 21254.3 | 2025-04-24 - 2026-01-15
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007071/IF/22012035362596 — JGSA RECHARGE STRUCTURE KAPILDHARA KUP RAJMAL KUNWARJI | New | 0 | 0 | 2025-04-14 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007071/IF/22012035362693 — JGSA RECHARGE STRUCTURE KAPILDHARA KUP RAJMAL KUNWARJI 1719007071/22012034464602 | Completed | 23899.46 | 21254.14 | 2025-04-30 - 2026-01-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012035516322 — Khet Talab nirman dharmita Bai mohan singh | Closed | 380018.24 | 522 | 2025-05-16 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012035526507 — Khet Talab nirman laadkunwar bai ajab singh | Completed | 380018.24 | 248994 | 2025-05-18 - 2026-05-21
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012035543367 — Khet Talab Nirman Rambha Bai Mewada | Completed | 408999.79 | 139374 | 2025-05-29 - 2026-05-21
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1719007071/IF/22012035570763 — khet talab nirmaan vijendr | Completed | 397462.86 | 270918 | 2025-06-24 - 2026-05-21
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035593029 — Ek Bagiya Ma Ke Naam Aruna MP19007071002 100 | Ongoing | 263510.03 | 110067 | 2025-09-13 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035598558 — Ek Bagiya Maa Ke Naam Bhagwati Bai Rathore MP19007071002 103 | Ongoing | 263510.03 | 87038.6 | 2025-09-16 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035620676 — Ek Bagiya Maa Ke Naam Leela Bai Karada MP19007017002 48 | Ongoing | 263510.03 | 91159.97 | 2025-09-16 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035620692 — Ek Bagiya Maa Ke Naam Geeta Bai Mewada MP19007071002 51 | Ongoing | 263510.03 | 99130.56 | 2025-09-16 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035633556 — Ek Bagiya Maa Ke Naam Ranu Bai MP19007017002 105-A | Ongoing | 263511.37 | 91909.8 | 2025-10-29 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035635370 — Ek bagiya maa ke naam Shanta bai Gp Batwadi Gram bheempura | Ongoing | 265045.01 | 93605 | 2025-10-29 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035635398 — Ek bagiya maa ke naam Prakash bai Gp Batwadi Gram Bheempura | Ongoing | 263511.37 | 99226 | 2025-10-29 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035635418 — Ek Bagiya Maa Ke Naam Shanta Bai MP1907017002 105 | New | 0 | 0 | 2025-08-01 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1719007071/IF/22012035642512 — Ek Bagiya Maa Ke Naam Lila Bai Karada | New | 0 | 0 | 2025-08-01 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719007071/IF/9993712400 — cattel shed | Deleted | 0 | 0 | 2016-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719007071/IF/9993712403 — cattel shed | Deleted | 0 | 0 | 2016-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1719007071/IF/9993712405 — cattle shed | Deleted | 0 | 0 | 2016-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/1021502 — Construction of IAY House -IAY REG. NO. MP2001784 | Completed | 15480 | 15660 | 2018-05-10 - 2018-10-17
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/1182115 — Construction of IAY House -IAY REG. NO. MP2515793 | Completed | 15480 | 15330 | 2017-12-08 - 2018-05-13
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/1516687 — Construction of IAY House -IAY REG. NO. MP3725894 | Completed | 15480 | 14666 | 2018-04-24 - 2018-09-05
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/1916543 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4486550 | Completed | 15660 | 15660 | 2018-08-17 - 2019-01-08
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2095456 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4043199 | Completed | 15840 | 15840 | 2019-06-30 - 2019-10-14
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2095635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4047443 | Completed | 15840 | 15840 | 2019-06-30 - 2019-10-14
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2138855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4988157 | Completed | 15840 | 15840 | 2019-06-30 - 2019-10-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2139489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5006075 | Completed | 15840 | 15840 | 2019-07-20 - 2019-11-05
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2139553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5007803 | Completed | 15840 | 15840 | 2019-07-20 - 2019-10-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2140147 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5021435 | Completed | 15840 | 15488 | 2019-10-16 - 2020-01-20
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2140335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5025613 | Completed | 15840 | 15488 | 2019-10-16 - 2020-02-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/2173144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4992241 | Completed | 15840 | 15840 | 2019-07-12 - 2019-11-01
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/342790 — Construction of IAY House -IAY REG. NO. MP1114551 | Completed | 15030 | 15240 | 2017-02-22 - 2017-10-10
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/345466 — Construction of IAY House -IAY REG. NO. MP1119077 | Completed | 15030 | 15450 | 2017-03-10 - 2017-09-30
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/3664483 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106890773 | Completed | 18360 | 17340 | 2022-06-24 - 2022-11-07
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/3664484 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106890812 | Completed | 18360 | 18360 | 2022-05-27 - 2022-09-05
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/368444 — Construction of IAY House -IAY REG. NO. MP1196674 | Completed | 15030 | 15300 | 2017-02-22 - 2017-09-30
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/3694027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483167 | Completed | 18360 | 18360 | 2022-05-27 - 2022-11-11
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/3694041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483711 | Completed | 18360 | 18360 | 2022-05-27 - 2022-09-16
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/3694046 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483915 | Completed | 18360 | 18360 | 2022-05-27 - 2022-09-16
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/369544 — Construction of IAY House -IAY REG. NO. MP1211882 | Completed | 15030 | 15300 | 2017-02-22 - 2017-09-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/369549 — Construction of IAY House -IAY REG. NO. MP1211907 | Completed | 15030 | 15360 | 2017-02-22 - 2017-09-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/3696033 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684324 | Completed | 18360 | 18360 | 2022-05-27 - 2022-09-29
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/370361 — Construction of IAY House -IAY REG. NO. MP1224604 | Completed | 15030 | 15450 | 2017-02-22 - 2017-09-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/370364 — Construction of IAY House -IAY REG. NO. MP1224617 | Completed | 15030 | 15360 | 2017-02-22 - 2017-09-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4207676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009528 | Completed | 18360 | 18360 | 2022-07-17 - 2022-09-16
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4215919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130279794 | Completed | 18360 | 17748 | 2022-07-17 - 2022-11-07
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4374952 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009830 | Completed | 18360 | 17952 | 2022-11-23 - 2022-12-19
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4547527 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684260 | Completed | 21870 | 21870 | 2024-11-05 - 2025-03-07
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4551667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483327 | Completed | 23490 | 22230 | 2024-12-03 - 2025-05-13
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4742562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483252 | Completed | 23490 | 21870 | 2024-12-03 - 2025-04-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4744612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009493 | Completed | 23490 | 21717 | 2024-12-10 - 2025-04-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4869183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148363516 | Completed | 23490 | 22986 | 2024-12-10 - 2025-05-28
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4878073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483131 | Completed | 23490 | 23238 | 2025-02-20 - 2025-08-17
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4985517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113672778 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4985518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113672806 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4985519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113672848 | Completed | 23490 | 23490 | 2025-04-02 - 2025-09-28
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4990862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483845 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4991517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684222 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/4991520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684305 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5000510 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117454043 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5000511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117454118 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/507910 — Construction of IAY House -IAY REG. NO. MP2355773 | Completed | 15030 | 15480 | 2017-06-06 - 2017-10-24
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5082179 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009585 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5082180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009676 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5082181 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009704 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5082182 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009775 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5082183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009794 | Completed | 23490 | 23490 | 2025-04-02 - 2025-08-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5088248 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129285065 | Completed | 23490 | 23490 | 2025-04-02 - 2025-10-03
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5096781 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145140833 | Completed | 23490 | 23490 | 2025-04-19 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5260667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130280043 | Completed | 23490 | 23490 | 2025-04-19 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5265810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129286812 | Completed | 23490 | 23490 | 2025-04-19 - 2025-08-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5311547 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009613 | Completed | 23490 | 23490 | 2025-04-19 - 2025-08-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/54638 — Construction of IAY House -IAY REG. NO. MP-19-007-071-001/021 | Completed | 14310 | 8016 | 2016-07-07 - 2017-04-01
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/54639 — Construction of IAY House -IAY REG. NO. MP-19-007-071-001/28 | Completed | 14310 | 13176 | 2016-07-07 - 2017-11-28
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5696714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117454050 | Completed | 23490 | 23490 | 2025-07-16 - 2025-09-28
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5711804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684356 | Completed | 23490 | 23490 | 2025-07-30 - 2025-11-17
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5735394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113483211 | Completed | 23490 | 23490 | 2025-08-18 - 2025-10-03
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5737027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116082001 | Completed | 23490 | 23490 | 2025-08-18 - 2025-10-03
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5739793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126648488 | Completed | 23490 | 23490 | 2025-08-18 - 2025-12-03
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5740257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009756 | Completed | 23490 | 23490 | 2025-08-18 - 2025-11-25
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5741500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684295 | Completed | 23490 | 23490 | 2025-08-18 - 2025-10-03
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5741501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684341 | Completed | 23490 | 23490 | 2025-08-18 - 2025-10-03
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5741966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106684246 | Completed | 23490 | 23490 | 2025-08-18 - 2025-10-03
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5826733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148374601 | Physically Completed | 23490 | 23490 | 2026-01-12 - 2026-07-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5826734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148374622 | Physically Completed | 23490 | 23490 | 2026-01-12 - 2026-07-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5844678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150524052 | Physically Completed | 23490 | 23490 | 2026-01-12 - 2026-07-12
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5951377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117453979 | Ongoing | 23490 | 7308 | 2026-06-13 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5958035 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113672712 | Ongoing | 23490 | 11223 | 2026-05-22 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5958036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113672752 | Ongoing | 23490 | 9135 | 2026-05-14 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5961363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131684449 | Ongoing | 23490 | 9135 | 2026-05-16 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5961377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114009727 | Ongoing | 23490 | 11223 | 2026-05-22 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/5965489 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106891780 | Ongoing | 23490 | 9135 | 2026-05-16 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/6108123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117454103 | Approved | 23490 | 0 | 2026-03-11 -
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/784186 — Construction of IAY House -IAY REG. NO. MP1424291 | Completed | 15480 | 15480 | 2017-05-13 - 2018-02-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/797120 — Construction of IAY House -IAY REG. NO. MP2328212 | Completed | 15480 | 15480 | 2017-05-13 - 2018-01-24
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/798826 — Construction of IAY House -IAY REG. NO. MP2468117 | Completed | 15480 | 15480 | 2017-05-13 - 2018-01-24
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/799175 — Construction of IAY House -IAY REG. NO. MP2511484 | Completed | 15480 | 15480 | 2017-05-13 - 2018-02-15
SHAJAPUR / SHUJALPUR / BATWADI | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719007071/IF/IAY/799343 — Construction of IAY House -IAY REG. NO. MP2529186 | Completed | 15480 | 15480 | 2017-10-06 - 2018-02-15
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1719007071/LD/22012034300523 — BATWADI KE BAROD RANA ME SHANTIDHAM SHED NIRMAN KARYA | Completed | 180000 | 178857 | 2017-02-10 - 2018-04-28
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007071/LD/3799382116 — shantidham batwadi | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1719007071/LD/3799382117 — shantidham badodrana | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Other Works | Infrastructure for NADEP composting / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1719007071/OP/9425892499 — BATWADI ME PANCHAYAT NIRMAN KARYA | Completed | 514000 | 512927 | 2017-03-03 - 2018-04-28
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/001 — मिटटीक़त मार्ग शाला भवन से मुख्‍य मार्ग तक बटवाडी | Completed | 170000 | 7480 | 2008-05-20 - 2008-05-31
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034155024 — panch parmeshwar+manrega se CC road and nali nirman amratlal ke makan se keshuji ke makan tak batwad | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034155025 — panch parmeshwar+manrega se CC road and nali nirman mata mandir se tejpuri ke makan tak batwadi | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034155026 — panch parmeshwar+manrega se CC road and nali nirman babulal ke makan se colony tak batwadi | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034155030 — panch parmeshwar+manrega se CC road and nali nirman suraj singh ke makan se badruddin ke makan tak b | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034155031 — panch parmeshwar+manrega se CC road and nali nirman devji ke makan se mata mandir tak batwadi | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034155032 — panch parmeshwar+manrega se CC road and nali nirman fulsingh ke makan se colony tak badodrana | Deleted | 0 | 0 | 2012-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034194125 — BATWADI ME CC ROAD AND NALI NIRMAN MATA MANDIR SE | Completed | 224000 | 223544.7 | 2013-12-17 - 2014-07-07
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034201796 — BATWADI KE BARODRANA ME PP+MANREGA SE CC ROAD AND | Completed | 164000 | 163164.2 | 2014-02-01 - 2014-07-05
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034208969 — BATWADI ME PP+MANREGA SE CC ROAD AND NALI NIRMAN B | Completed | 135000 | 132836 | 2014-03-01 - 2016-03-02
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034208971 — BATWADI KE BARODRANA ME PP+MANREGA SE CC ROAD AND | Completed | 135000 | 35248.29 | 2014-03-01 - 2015-07-06
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007071/RC/22012034208974 — BATWADI ME KHET SADAK NIRMAN HADLAYKALA MUKHYA MAR | Completed | 1440000 | 1752 | 2014-03-01 - 2016-08-26
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034221956 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034221957 — pp+manrega se cc road and nali nirman shriram ke m | Deleted | 191000 | 0 | 2014-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034221958 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034221959 — pp+manrega se cc road and nali nirman | Deleted | 0 | 0 | 2014-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034230240 — batwad me pp+manrega se CC road and nali nirman shri ram ke makan se devnarayan mandir tak | Deleted | 191000 | 0 | 2014-09-22 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034282669 — cc road and nali nirman hanumaan mandir se rame nayak ke makan tak | Completed | 125000 | 125207 | 2015-08-16 - 2016-05-28
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034296042 — cc road devi singh ke makan se ladsingh avam gorilal ki gali tak | Completed | 50000 | 45792 | 2016-01-13 - 2016-06-07
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007071/RC/22012034297546 — antrik marg shivnarayan ke ghar se vikram malviya ke ghar tak | Deleted | 170000 | 0 | 2015-12-21 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007071/RC/22012034299086 — grewal road | Deleted | 0 | 0 | 2016-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034299087 — c c road | Deleted | 0 | 0 | 2016-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034317477 — C.C.ROAD VINOD KE MAKAN SE NANNU KE MAKAN TAQ batwadi | Completed | 21000 | 20875 | 2016-12-10 - 2017-01-31
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034317478 — C.C.ROAD BABULAL KE MAKAN SE MAKHAN,HUKUM EVAM PEEPLI HANDPUMP TAQ BATWADI | Completed | 71800 | 71977 | 2016-12-16 - 2017-03-16
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034320794 — cc road and nali nirman | Deleted | 0 | 0 | 2016-08-15 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034321280 — c.c.road and nali nirman | Deleted | 0 | 0 | 2016-10-02 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034368293 — C.c.road nirman | Deleted | 0 | 0 | 2017-11-23 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034392841 — C.C.road nirman harinarayan ke ghar se Bharat ke ghar tak | Completed | 35600 | 34938 | 2018-08-23 - 2019-08-20
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034394523 — C C Road Nirman Work Colony Hndpamp Se Kankad Ghatha Tak | Completed | 84300 | 80562 | 2018-09-28 - 2019-01-10
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034440084 — c.c.road nirmaan | Deleted | 0 | 0 | 2019-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034440144 — c.c.road nirmaan | Deleted | 0 | 0 | 2019-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034467374 — सी सी रोड निर्माण स्‍कुल प्रांगण मे | Completed | 23100 | 22176 | 2019-07-31 - 2019-09-17
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034479230 — C C Road And Nali Nirman Shri Ram ke Makan Se Kumer singh Pathel Ke Makan Tak | Completed | 75700 | 75630 | 2019-11-02 - 2020-05-21
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034511559 — C C Road Nirman Work Kundi Se Shri Ram ke Ghar Tak | Completed | 13800 | 13966 | 2020-01-25 - 2020-05-25
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034513212 — सी.सी.रोड निर्माण | Deleted | 0 | 0 | 2019-10-02 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034513213 — सी.सी.रोड निर्माण | Deleted | 0 | 0 | 2019-10-02 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034513214 — सी.सी.रोड निर्माण | Deleted | 0 | 0 | 2019-10-02 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034513215 — सी.सी.रोड निर्माण | Deleted | 0 | 0 | 2019-10-02 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007071/RC/22012034516279 — grawal sadak nirmaan | Deleted | 0 | 0 | 2020-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1719007071/RC/22012034524111 — APROCH ROAD | Completed | 1345580.3 | 1175908.56 | 2020-06-16 - 2023-07-05
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034525725 — C C Road And nali Nirman Work Nannulal ke Makan Se Babulal ke makan Tak | Completed | 24500 | 26410 | 2020-08-07 - 2020-12-16
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034525726 — C C Road And nali Nirman Work Ram Mandir Se main Sadak Tak | Deleted | 25240 | 190 | 2020-08-07 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034546990 — C C Road And Nali Nirman Work Kundi se Shri Shyamlal ke Makan Tak | Completed | 27000 | 26980 | 2020-11-04 - 2021-03-23
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034554458 — C C Road And Nali Nirman Work Gorelal Se Aamrtlal v Ramesh Se Nannulal Tak | Completed | 21164 | 21090 | 2020-12-30 - 2021-03-10
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034589742 — C C Road Nirman Work Aamrtalal Ke Makan Se Shri ram Ke makan Ki Aur | Completed | 74400 | 74305 | 2021-10-30 - 2021-12-20
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034622393 — सी॰ सी॰ रोड निर्माण कार्य फुलसिंग के मकान से रायसिंग के मकान तक बड़ोदराणा ग्राम् पंचायत बट्वाडी | Completed | 42916 | 42890 | 2022-12-13 - 2024-01-24
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034646804 — सीसी रोड निर्माण कार्य भेरुलाल के मकान से नन्नूलाल मालवीय के माकन तक | Completed | 96200 | 95719 | 2023-09-24 - 2024-04-09
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034673075 — लालबाई माता मंदिर से श्री हुकमसिंह के माकन तक ग्राम बटवाडी | Completed | 94000 | 92840 | 2024-01-30 - 2024-06-28
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034678118 — c.c.road nirmaan | New | 0 | 0 | 2024-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/22012034831250 — सीसी रोड एवं नाली निर्माण कार्य मोहनलाल से देवीलाल व कालू सिंह से अंतर सिंह तक | Ongoing | 99900 | 72414 | 2024-12-03 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/67 — पंच परमेश्‍वर व मनरेगा से सीसी रोड एवं नाली निर्माण दिनेश से बाबूलाल के घर तक बटवाडी | Completed | 100000 | 137992 | 2012-05-29 - 2013-03-30
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/70 — RC/70 | Completed | 82500 | 3200 | 2013-03-15 - 2024-03-09
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719007071/RC/राज्‍य वित — राज्‍य वित्‍त आयोग (मनरेगा) सी0सी0रोड एवं नाली का निर्माण राममंदिर से देवजी के मकान तक बटबाडी | Completed | 82500 | 103244 | 2012-05-29 - 2013-03-25
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1719007071/RS/22012034503267 — सामुदायिक स्वच्छता परिसर कार्य राम मंदिर के पास बडोदराना | Completed | 44000 | 42625 | 2020-12-16 - 2021-12-22
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & maint of Open/Covered Grey_Water for Comm / Repair and maintenance of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007071/RS/22012034680363 — नाली निर्माण कार्य लखन विश्वकर्मा के माकन से नारायण के माकन तक | Completed | 54700 | 54525 | 2022-12-16 - 2024-01-24
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007071/RS/22012034703428 — Nali Nirman Work Devisingh ke makan se purana School tak graam batwadi | Completed | 20200 | 19932 | 2023-10-12 - 2024-06-28
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007071/RS/22012035121983 — नाली निर्माण कार्य लालबाई मंदिर से श्रीराम के माकन तक ग्राम बटवाडी | Completed | 13000 | 12912 | 2024-01-30 - 2024-03-20
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719007071/RS/22012035123640 — nali nirmaan badodrana | New | 0 | 0 | 2024-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1719007071/RS/40150 — suganbai ratanlal manrega+maryada | Completed | 4400 | 6292 | 2013-06-29 - 2015-06-17
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007071/WC/22012034423288 — Nala Trnches Nirman Work Badodrana | Deleted | 158970 | 174 | 2018-09-28 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007071/WC/22012034423289 — Nala Tranches Nirman Work Batbadi | Completed | 158970 | 119064 | 2018-09-28 - 2019-08-25
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1719007071/WC/22012034436423 — nala tranch nirmaan | Closed | 0 | 0 | 2019-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007071/WC/22012034436446 — ckech dem nirmaan | Closed | 0 | 0 | 2019-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007071/WC/22012034436462 — ckech dem nirmaan | Closed | 0 | 0 | 2019-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1719007071/WC/22012034436464 — chech dem nirmaan | Closed | 0 | 0 | 2018-10-02 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1719007071/WC/22012034475696 — WATER RESERVOIR PANCHAYAT BHAVAN BATWADI | Completed | 19407.24 | 16608 | 2019-08-17 - 2019-10-03
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1719007071/WC/22012034475699 — WATER RESERVOIR PS BATWADI | Closed | 0 | 0 | 2019-06-24 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1719007071/WC/22012034475700 — WATER RESERVOIR PS BARODRANA | Closed | 0 | 0 | 2019-06-24 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1719007071/WC/22012034475701 — WATER RESERVOIR MS BARODRANA | Closed | 0 | 0 | 2019-06-24 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Grps / Construction of Sand filter for openwell recharge for Groups | Well Recharge | 1719007071/WC/22012034475726 — WATER RESERVOIR ANGANWADI BHAWAN | Closed | 0 | 0 | 2019-06-24 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007071/WC/22012034480769 — Soka pit Gagdde work Sarvajik Parisar me | Closed | 0 | 0 | 2019-07-25 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007071/WC/22012034480875 — Shoka pit Gadde work Sarvjik Parisar me | Closed | 0 | 0 | 2019-07-25 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007071/WC/22012034728001 — Roof Water Harvesting Aaganwadi Bhvan Badodrana | Completed | 11652 | 10112 | 2021-06-03 - 2023-08-18
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007071/WC/22012034728011 — Roof Water Harvesting P.S Bhavan Badodrana | Completed | 11652 | 10112 | 2021-06-03 - 2023-07-21
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1719007071/WC/22012034728019 — Roof Water Harvesting Middil School Bhavan par Badodrana | Completed | 11652 | 9908 | 2021-06-03 - 2023-08-01
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007071/WC/22012034730608 — recharge pit school handpump badodrana | Completed | 14467.3 | 7505 | 2022-05-04 - 2024-04-09
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719007071/WC/22012034730620 — recharge pit school handpump badodrana | Completed | 14467.3 | 6482 | 2022-05-04 - 2024-04-09
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1719007071/WC/22012034995266 — रिचार्ज ट्रेंज ग्राम बटवाडी | Closed | 0 | 0 | 2022-08-18 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007071/WC/22012035169158 — talab jirnodwar | New | 0 | 0 | 2024-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Community Ponds for Comm / Repair and maintenance of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1719007071/WC/22012035169159 — talab jirnodwar | New | 0 | 0 | 2024-01-26 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Mini Percolation tank / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1719007071/WC/9993669221 — talab ghehrikaran batwadi buchan wali ke pass | Deleted | 0 | 0 | 2016-08-08 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719007071/WH/19957123 — Talab marammat (gehrikaran) gram batwadi ki talai | Deleted | 100000 | 0 | 2016-06-06 -
SHAJAPUR / SHUJALPUR / BATWADI | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1719007071/WH/19960685 — Renovation of Sarvjanik Talab Batwadi | Completed | 504700 | 450161.22 | 2017-05-23 - 2017-10-25