## Work List
Exported on: 2026-10-11 02:10:10
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: MAYAPUR
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007072/IF/22012035452520 — JGSA 2025 Rechrge Structure Dugwell Recharge Makhansingh | Physically Completed | 23538.4 | 23133 | 2025-05-06 | 2026-04-10
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007072/IF/22012035452579 — JGSA 2025 Rechrge Structure Dugwell Recharge Dharmendra Sharma | Physically Completed | 23538.4 | 23264 | 2025-05-06 | 2026-04-10
SHAJAPUR / SHUJALPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1719007072/IF/22012035483408 — JGSA 2025 Recharge Structure Kapil dara kup Bagvat Singh Rajput | Physically Completed | 23893.97 | 22938 | 2025-05-10 | 2026-04-10
SHAJAPUR / SHUJALPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1719007072/RC/22012034850961 — CC Road Nirman Kary Middile School Se Men Road Tak | Physically Completed | 41555 | 41276 | 2026-02-02 | 2026-09-07