## Work List
Exported on: 2026-09-06 02:17:08
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: HARUKHEDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
SHAJAPUR / KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1719008081/AV/22012034631157 — शांतिधाम शेड निर्माण हरुखेड़ी | Closed | 0 | 0 | 2023-01-26
SHAJAPUR / KALAPIPAL | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Anganwadi/Other Rural Infrastructure | Construction of Cattle Shelter for Community / Construction of Cattle Shelter for Community | Cattle Shed | 1719008081/AV/22012034631159 — शांतिधाम शेड निर्माण सेमलीखेड़ा | Closed | 0 | 0 | 2023-01-26
SHAJAPUR / KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719008081/AV/22012034650852 — Shanti Dham Shed Nirman Harukhedi | Closed | 226381.46 | 0 | 2023-10-02
SHAJAPUR / KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719008081/AV/22012034650853 — Shanti Dham Shed Nirman Shemlikheda | Closed | 0 | 0 | 2023-10-02
SHAJAPUR / KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1719008081/AV/22012034650854 — Shanti Dham Shed Nirman Shemlikheda | Closed | 0 | 0 | 2023-10-02
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1719008081/DP/22012034599666 — Vasudha Vandan Amrit Vatika Gram Panchayat HARUKHEDi | Closed | 0 | 0 | 2023-08-01
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1719008081/IF/22012035184006 — Khet Talab Nirman Gajraj Singh Govardhan singh | Completed | 385261.22 | 314448 | 2024-02-07 | 2024-08-30
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4689227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113551319 | Completed | 21870 | 21870 | 2024-10-22 | 2025-03-20
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4704003 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120938009 | Completed | 21870 | 21870 | 2024-11-01 | 2025-02-19
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4704006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120940020 | Completed | 21870 | 21870 | 2024-11-01 | 2025-02-19
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4717730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130980905 | Completed | 21870 | 21870 | 2024-11-01 | 2025-01-23
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4752083 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303810 | Completed | 23490 | 21717 | 2024-12-09 | 2025-08-05
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4783714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130494683 | Completed | 21870 | 21870 | 2024-12-03 | 2025-02-13
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4863971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303992 | Completed | 23490 | 22986 | 2025-02-27 | 2025-07-22
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4872924 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130494860 | Completed | 23490 | 23490 | 2025-07-05 | 2026-02-23
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4873909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303828 | Completed | 23490 | 23238 | 2025-02-27 | 2026-03-01
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/4882311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113551078 | Completed | 23490 | 22986 | 2025-02-27 | 2025-07-22
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5822410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117303962 | Completed | 23490 | 23490 | 2025-09-29 | 2025-11-06
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5822453 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120937330 | Completed | 23490 | 23490 | 2026-01-01 | 2026-03-16
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5823203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120926025 | Completed | 23490 | 23490 | 2025-09-29 | 2025-11-04
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5823206 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120940621 | Completed | 23490 | 23490 | 2026-01-15 | 2026-05-12
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5826841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120941805 | Completed | 23490 | 23490 | 2025-09-29 | 2025-11-04
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5827586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120940304 | Completed | 23490 | 23490 | 2025-11-03 | 2026-02-15
SHAJAPUR / KALAPIPAL | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5827939 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120935189 | Approved | 27000 | 0 | 2025-02-24
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5828325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144841106 | Completed | 23490 | 23490 | 2026-01-01 | 2026-03-13
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5843582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130494487 | Completed | 23490 | 23490 | 2025-11-03 | 2026-03-13
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5845279 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144840499 | Completed | 23490 | 23490 | 2025-11-03 | 2026-02-11
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5845651 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150858626 | Completed | 23490 | 23490 | 2026-01-15 | 2026-05-12
SHAJAPUR / KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5940876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120940792 | Ongoing | 27000 | 16443 | 2026-04-22
SHAJAPUR / KALAPIPAL | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/5981818 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117304085 | Approved | 27000 | 0 | 2026-02-23
SHAJAPUR / KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/6003107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP144839445 | Ongoing | 27000 | 15708 | 2026-05-29
SHAJAPUR / KALAPIPAL | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1719008081/IF/IAY/6060986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117304118 | Ongoing | 27000 | 10962 | 2026-05-13
SHAJAPUR / KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008081/RC/22012034643966 — सी सी रोड निर्माण मुकेन्द्र के मकान से दश्‍रथसिंह माली के मकान तक | Completed | 54000 | 53703 | 2023-09-20 | 2024-03-11
SHAJAPUR / KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008081/RC/22012034673924 — C C Road Nirman Work Gram me | New | 0 | 0 | 2024-01-27
SHAJAPUR / KALAPIPAL | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008081/RC/22012034673925 — C C Road Nirman Work Gram me | New | 0 | 0 | 2024-01-27
SHAJAPUR / KALAPIPAL | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008081/RC/22012034821435 — c c road nirman dashrath mali ke makan se prathmik school ki or harukhedi | Completed | 45334 | 45198 | 2024-08-01 | 2024-11-05
SHAJAPUR / KALAPIPAL | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008081/RC/22012034821438 — c c road nirman dhiraj singh ke makan se prathmik school ki or harukhedi | Completed | 32199 | 32076 | 2024-10-08 | 2024-11-05
SHAJAPUR / KALAPIPAL | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008081/RC/22012034848414 — C C Road Nirman Work P m Road Se Lakhan Ke Makan Ki Aur Gram Semalikheda | Completed | 98754 | 97614 | 2025-09-04 | 2025-11-28
SHAJAPUR / KALAPIPAL | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1719008081/RC/22012034848415 — C C Road And Nali Nirman Work Chok me Gram Semlikheda | Completed | 39476 | 39150 | 2025-09-12 | 2026-05-12
SHAJAPUR / KALAPIPAL | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1719008081/RS/22012035129790 — R C C Nali Nirman Work Antar Singh Ke Makan Se Shripal Singh Ke Makan ki Aur Gram Semalikheda | Approved | 26243 | 0 | 2024-07-26
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035112680 — सोक्ता गडडा निर्माण माता मंदिर के पास का हेण्डपम्प | Deleted | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035112714 — सोक्ता गडडा निर्माण हरिजन मोहल्ला केशु के मकान के पास हण्डपम्प | Deleted | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035112720 — सोक्ता गडडा निर्माण कल्ला मोहल्ला के मूलचन्द्र के मकान का हेण्डपम्प | Deleted | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035112727 — सोक्ता गडडा निर्माण प्राथमिक स्कूल के पास का हेण्डपम्प | Deleted | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035112736 — सोक्ता गडडा निर्माण सपेरा मोहल्ला का हेण्डपम्प | Deleted | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035112752 — सोक्ता गडडा निर्माण राम मंदिर का हेण्डपम्प | Deleted | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035112753 — सोक्ता गडडा निर्माण राजपूत मोहल्ला का हेण्डपम्प | Deleted | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035113639 — सोक्ता गडडा निर्माण माता मंदिर के पास का हेण्डपम्प | Completed | 20171.62 | 12694 | 2023-10-03 | 2025-05-17
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035113640 — सोक्ता गडडा निर्माण हरिजन मोहल्ला केशु के मकान के पास हण्डपम्प | Completed | 20171.62 | 12597 | 2023-10-04 | 2025-10-07
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035113642 — सोक्ता गडडा निर्माण कल्ला मोहल्ला के मूलचन्द्र के मकान का हेण्डपम्प | Closed | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035113644 — सोक्ता गडडा निर्माण प्राथमिक स्कूल के पास का हेण्डपम्प | Completed | 20171.62 | 12597 | 2023-10-04 | 2025-10-07
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035113645 — सोक्ता गडडा निर्माण सपेरा मोहल्ला का हेण्डपम्प | Completed | 20510 | 12756 | 2023-09-25 | 2025-05-17
SHAJAPUR / KALAPIPAL | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1719008081/WC/22012035113647 — सोक्ता गडडा निर्माण राजपूत मोहल्ला का हेण्डपम्प | Closed | 0 | 0 | 2023-08-16
SHAJAPUR / KALAPIPAL | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1719008081/WC/22012035298340 — JGSA 2025 RECHARGE STRUCTURE sarvajanik kup manglik bhavan k pas Harrukhedi | Approved | 0 | 0 | 2025-04-01