## Work List
Exported on: 2026-10-12 16:16:22
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: MURAMYA
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1720002003/AV/22012034371668 — शांतीधाम मुरम्‍या | Physically Completed | 180000 | 123972 | 2018-02-25 | 2026-05-20
DEWAS / SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002003/IF/22012034616803 — Khet talab kailash bhagirath | Physically Completed | 332962.02 | 201144 | 2020-11-25 | 2026-04-27
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002003/IF/22012035351451 — khet talab nirman keshar bai nabbu ji | Physically Completed | 376711.85 | 211131.12 | 2025-05-09 | 2026-06-12
DEWAS / SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/4762006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120572004 | Physically Completed | 21870 | 21627 | 2024-12-23 | 2026-05-20
DEWAS / SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/4765371 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115409022 | Physically Completed | 21870 | 21384 | 2024-12-23 | 2026-06-15
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720002003/IF/IAY/5158441 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119915067 | Physically Completed | 23490 | 22707 | 2025-10-09 | 2026-08-19
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5159635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102428118 | Physically Completed | 23490 | 23490 | 2025-08-25 | 2026-05-18
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5182928 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105328800 | Physically Completed | 23490 | 23229 | 2025-07-13 | 2026-05-20
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5185006 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100638714 | Physically Completed | 23490 | 23490 | 2025-10-26 | 2026-03-15
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5214327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102427020 | Physically Completed | 23490 | 23490 | 2025-06-17 | 2026-03-15
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5216819 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145726770 | Physically Completed | 23490 | 23229 | 2025-10-09 | 2026-05-20
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5225528 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113538097 | Physically Completed | 23490 | 23490 | 2025-07-13 | 2026-05-18
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5228140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147725063 | Physically Completed | 23490 | 23490 | 2025-07-13 | 2026-04-12
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5653592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147634843 | Physically Completed | 23490 | 23490 | 2025-08-18 | 2026-03-15
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5654170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119465632 | Physically Completed | 23490 | 23229 | 2025-09-02 | 2026-03-06
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002003/IF/IAY/5654955 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122059471 | Physically Completed | 23490 | 22968 | 2025-09-02 | 2026-06-15
DEWAS / SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel / Mitti Murram Road for Community | Construction of Road and Culvert | 1720002003/RC/22012034340982 — सुदूर सड़क,पीपलरावां रोड से मुरम्या कालोनी | Physically Completed | 2973000 | 2284583.19 | 2017-06-14 | 2026-10-06
DEWAS / SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002003/WC/22012034625326 — Percolation tank bheru singh ke khet ke paas | Physically Completed | 420786.25 | 234468 | 2021-10-06 | 2026-05-07
DEWAS / SONKATCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002003/WC/22012035227103 — Parcolation tank surjana raste par | Physically Completed | 199972.56 | 116596.34 | 2024-12-04 | 2026-05-08
DEWAS / SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720002/WC/22012035279462 — JGSA2025 dugwell recharge nirmal neer motisingh ke khet ke pas | Physically Completed | 25899.46 | 25294.99 | 2025-05-04 | 2026-04-27
DEWAS / SONKATCH | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720002/WC/22012035279534 — JGSA2025 dugwell recharge nirmal neer st mohalla | Physically Completed | 25899.46 | 25138.97 | 2025-05-04 | 2026-05-01