## Work List
Exported on: 2026-10-21 05:30:02
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: KHUTKHEDA
Status: Closed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002009/AV/22012034589216 — डाईनिंग हाल बैठक व्यवस्था कार्य मिडिल स्कूल लकुमडी | Closed | 0 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002009/AV/22012034589454 — डाइनिंग हाल बैठक व्यवस्था कार्य मिडिल स्कूल प्राइमरी स्कूल | Closed | 0 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002009/AV/22012034589457 — डाइनिंग हाल में बैठक व्यवस्था गर्ल प्राइमरी स्कूल | Closed | 23925.39 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002009/AV/22012034589488 — डाइनिंग हाल बैठक व्यवस्था कार्य मिडिल स्कूल KHUTKHEDA | Closed | 23925.39 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002009/AV/22012034589489 — डाइनिंग हाल बैठक व्यवस्था कार्य प्राइमरी स्कूल खुत्खेदा | Closed | 23925.39 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1720002009/DP/22012034551226 — मा की बगिया - आगनवाड़ी भवन खुत्खेडा | Closed | 14675.4 | 0 | 2021-08-15
DEWAS / SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1720002009/DP/22012034564729 — वृक्षा रोपण कार्य - अमृत सरोवर के पास खुटखेड़ा | Closed | 412718.19 | 0 | 2022-07-28
DEWAS / SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002009/IF/22012034538659 — khet talab (chatarsingh/ umrawsingh) | Closed | 310386.65 | 0 | 2020-01-26
DEWAS / SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002009/IF/22012034672401 — खेत तालाब कुंता बाई | Closed | 326801.1 | 0 | 2021-01-26
DEWAS / SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002009/IF/22012034672402 — खेत तालाब गीता बाई | Closed | 332962.02 | 0 | 2021-01-26
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002009/IF/22012034814460 — व्यक्तिगत सोख्ता गड्ढा निर्माण कार्य /SLWM/5 | Closed | 17639.02 | 0 | 2021-04-26
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002009/IF/22012034815211 — व्यग्तिगत सोंक पिट निर्माण कार्य /slwm/15 | Closed | 52917.07 | 0 | 2021-04-26
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002009/IF/22012034831203 — व्यक्तिगत सोंक पिट निर्माण कार्य / slwm / 14 | Closed | 49000.28 | 0 | 2021-04-26
DEWAS / SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002009/RC/22012034529378 — सी सी रोड निर्माण सोबाल्सिंह के मकान से हरिसिंह के मकान तक | Closed | 0 | 0 | 2020-04-26
DEWAS / SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002009/RC/22012034542078 — c c road kara ropan st colony se raam mandir road | Closed | 0 | 0 | 2020-04-26
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002009/RC/22012034576806 — सुदूर सड़क (बद्री के खेत से मुंडला काकड तक) | Closed | 0 | 0 | 2021-04-26
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002009/RC/22012034576813 — सुदूर / खेत सड़क बद्रीलाल के खेत से मुंडला काकड़ तक | Closed | 0 | 0 | 2021-04-26
DEWAS / SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002009/RC/22012034619570 — अमृत सरोवर पहुंच मार्ग उप स्वस्थ केंद्र से फकरु खान के खेत तक भाग 1 | Closed | 0 | 0 | 2022-10-21
DEWAS / SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002009/RC/22012034619571 — अमृत सरोवर पहुंच मार्ग फकरु खान के अमृत सरोवर तक भाग 2 | Closed | 0 | 0 | 2022-10-21
DEWAS / SONKATCH | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1720002009/RS/22012034475270 — soke pit (patel chouk devendr ke makan ke paas) | Closed | 13427.22 | 0 | 2019-08-15
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1720002009/RS/22012034537645 — slwm nadep nirman ajay singh sidhnathsingh | Closed | 12630.91 | 0 | 2021-04-26
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1720002009/RS/22012034537648 — slwm nadep nirman mahendr singh narayan singh | Closed | 12630.91 | 0 | 2021-08-05
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1720002009/RS/22012034540981 — सामुदाइक सोंक पिट प्राथमिक शाला भवन के सामने | Closed | 17696.08 | 0 | 2021-04-26
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720002009/RS/22012034547167 — SLWM नाली निर्माण धुलजी के माकन से तखत सिंह के मकान तक | Closed | 0 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002009/WC/22012034765139 — CTR - Roof water harwesting panchayat bhawan ke pass | Closed | 26144.98 | 0 | 2021-04-26
DEWAS / SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1720002009/WC/22012034940793 — नवीन तालाब खर्चा वाला नाले पर | Closed | 1467335.32 | 0 | 2022-04-05
DEWAS / SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002009/WC/22012035029592 — parkolation Tank - Dhandheda marg pahadi par Khutkheda | Closed | 0 | 0 | 2022-11-26
DEWAS / SONKATCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002009/WC/22012035235936 — Percolation tank gaushala ke pass | Closed | 493954.28 | 0 | 2024-10-02
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720002/IF/22012034859969 — slwm nadep nirmandilipsingh motisingh | Closed | 12630.91 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720002/IF/22012034859971 — slwm nadep nirman jiwan singh raisingh | Closed | 12630.91 | 0 | 2021-08-15
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720002/IF/22012034859972 — slwm nadep nirman arjunsingh ratan singh | Closed | 12630.91 | 0 | 2021-08-15