## Work List
Exported on: 2026-10-23 01:52:31
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: GARHKHAJURIYA
Status: Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1720002015/AV/156 — Aanganbadi Bhavan Nirman Sewa Kendra,SONKATCH | Completed | 548000 | 154529 | 2013-08-29 | 2020-11-06
DEWAS / SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720002015/DP/22012034485860 — Nirmal nir Mata Goya | Completed | 450949.98 | 416552.1 | 2020-03-13 | 2024-05-28
DEWAS / SONKATCH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/1000018146 — खेत तालाब रामसिह पूनाजी | Completed | 367000 | 93732 | 2013-06-08 | 2015-06-22
DEWAS / SONKATCH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/1000034908 — खेत तालाब जगदीश भेराजी | Completed | 367000 | 159432 | 2013-09-11 | 2015-06-22
DEWAS / SONKATCH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/1000034910 — खेत तालाब केसरसिह उमरावसिह | Completed | 367000 | 876 | 2013-09-11 | 2015-02-26
DEWAS / SONKATCH | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/1000034912 — खेत तालाब हरूबाई दोलतसिह | Completed | 367000 | 183726 | 2013-09-11 | 2015-06-22
DEWAS / SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012034302517 — इंदरा आवास संतोस / राजाराम | Completed | 14310 | 14028 | 2016-12-27 | 2017-05-25
DEWAS / SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002015/IF/22012034340214 — वृक्षारोपण-शांतीधाम परिशर मे | Completed | 335000 | 64030 | 2017-05-18 | 2023-02-19
DEWAS / SONKATCH | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002015/IF/22012034340419 — वृक्षारोपण खेत सड़क मनोहर राठी के खेत से बाबूलाल शर्मा के खेत तक के किनारे | Completed | 335000 | 37492 | 2017-05-18 | 2023-01-20
DEWAS / SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1720002015/IF/22012034385234 — निजी खेत में फलौउद्यान -रमेश चन्द्र बाल मुकुंद | Completed | 154000 | 136411 | 2020-12-17 | 2024-03-22
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/22012034447523 — Khet talab kuldeep Gyansingh | Completed | 288000 | 183376 | 2018-12-24 | 2019-08-13
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002015/IF/22012034470562 — kupnirman tarun rathi | Completed | 210000 | 201644 | 2019-03-05 | 2019-09-15
DEWAS / SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/22012034589339 — खेत तालाब निर्माण - रविन्द्र पिता कमल सिंह | Completed | 313425.85 | 184300 | 2020-08-11 | 2021-08-30
DEWAS / SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/22012034622146 — खेत तालाब (बोन्दरमल पिता हीरालाल | Completed | 322416.59 | 178600 | 2020-11-19 | 2021-08-30
DEWAS / SONKATCH | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/22012034660023 — खेत तालाब निर्माण सीताराम पूरण | Completed | 307650.24 | 138464 | 2021-03-05 | 2023-02-28
DEWAS / SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1720002015/IF/22012034678015 — Khet talab Sharda bai -jivan singh ke khet par | Completed | 314018.23 | 233804 | 2021-04-01 | 2023-03-25
DEWAS / SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720002015/IF/22012034678791 — khet talab nirman sushil bhim singh | Completed | 314018.23 | 170805 | 2021-04-01 | 2022-03-25
DEWAS / SONKATCH | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002015/IF/22012034786807 — CTR khet talab nirman ramchandra / bonda ji | Completed | 319371.91 | 173004 | 2021-06-14 | 2024-05-03
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002015/IF/22012034959552 — Kapil Dhara Kup Nirman kalu singh rajal bai bane singh | Completed | 257014.43 | 241163.69 | 2022-04-14 | 2024-02-13
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012035017476 — PMAY - Ashok Nagjiram | Completed | 18360 | 17119 | 2022-09-06 | 2024-06-19
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012035017531 — PMAY - Bhagirat Bheraji | Completed | 18360 | 19142 | 2022-09-23 | 2023-12-06
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012035017541 — PAMY - AAwas Gokul Ganapat | Completed | 18360 | 18360 | 2022-09-07 | 2023-12-14
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012035017548 — PMAY - Rameshchandra hiralal | Completed | 18360 | 18156 | 2022-09-10 | 2023-07-18
DEWAS / SONKATCH | 2022-2023 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720002015/IF/22012035042355 — Nadep nirman Bhadar singh -Fate singh | Completed | 19893.05 | 11313 | 2023-01-01 | 2024-03-21
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012035044314 — PMAY चंदाबाई पिता चैन सिंह जाब कार्ड क्रमांक | Completed | 18360 | 17612 | 2022-12-13 | 2023-08-14
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012035044315 — PMAY लीलाबाई मानसिंह जॉब कार्ड क्रमांक | Completed | 18360 | 17612 | 2022-12-13 | 2023-12-06
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/22012035044317 — PMAY सोबल सिंह रामचंद्र जी जाब कार्ड क्रमांक | Completed | 18360 | 18276 | 2022-12-13 | 2023-12-06
DEWAS / SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1720002015/IF/22012035057915 — खेत तलाब निर्माण- जितेंद्र सिंह - बाबूलाल शर्मा के खेत पर | Completed | 357289.21 | 110224 | 2023-05-08 | 2025-05-22
DEWAS / SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/9993698447 — इंदरा आवास,बसन्‍ताबाई सुखराम | Completed | 7155 | 8493 | 2015-12-21 | 2017-05-25
DEWAS / SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/9993698449 — इंदरा आवास,कैलासनारायण लक्ष्मिनारायण | Completed | 14310 | 10020 | 2016-12-27 | 2017-05-25
DEWAS / SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1720002015/IF/9993721819 — खेत तालाब कोशल्य कूवर के खेत पर | Completed | 298612.59 | 184680 | 2020-04-22 | 2020-09-24
DEWAS / SONKATCH | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1720002015/IF/9993721985 — खेत तालाब पन्नालाल-गम्भिर | Completed | 298612.59 | 189240 | 2020-04-22 | 2020-11-20
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1879619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4353399 | Completed | 15660 | 15660 | 2018-08-07 | 2019-01-14
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1880864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4593413 | Completed | 15660 | 15660 | 2018-08-07 | 2019-01-01
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1880919 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4628325 | Completed | 15660 | 15660 | 2018-08-01 | 2019-01-01
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1881598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5291373 | Completed | 15660 | 15660 | 2018-08-07 | 2019-01-01
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1887954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4332064 | Completed | 15660 | 14616 | 2018-08-07 | 2019-01-01
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1888519 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4558374 | Completed | 15660 | 15660 | 2018-08-07 | 2018-11-23
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1893232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4568700 | Completed | 15660 | 15660 | 2018-08-07 | 2019-01-01
DEWAS / SONKATCH | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/1896941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4630127 | Completed | 15660 | 15660 | 2018-08-07 | 2019-01-01
DEWAS / SONKATCH | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/2109751 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4321040 | Completed | 15840 | 15664 | 2019-07-18 | 2019-09-08
DEWAS / SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/376913 — Construction of IAY House -IAY REG. NO. MP1514187 | Completed | 15030 | 14991 | 2017-01-31 | 2018-05-03
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3919859 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106174496 | Completed | 18360 | 18360 | 2022-09-01 | 2023-11-07
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3920805 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117296939 | Completed | 18360 | 18360 | 2022-08-03 | 2023-01-01
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3923110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113865766 | Completed | 18360 | 17799 | 2022-07-18 | 2023-08-10
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3925869 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113926896 | Completed | 18360 | 18360 | 2022-06-19 | 2023-06-28
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3930044 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116638621 | Completed | 18360 | 18122 | 2022-09-01 | 2023-08-01
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3930513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106527388 | Completed | 18360 | 18360 | 2022-07-25 | 2023-12-14
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3932693 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105990900 | Completed | 18360 | 18360 | 2022-08-04 | 2023-01-24
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3935848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114153149 | Completed | 18360 | 17544 | 2022-08-04 | 2023-07-26
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/3938390 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120849468 | Completed | 18360 | 18292 | 2022-09-01 | 2024-05-21
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/4242606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113777508 | Completed | 18360 | 18360 | 2022-07-18 | 2023-01-20
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/4243160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812367 | Completed | 18360 | 18360 | 2022-08-30 | 2022-12-30
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/4244173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117419607 | Completed | 18360 | 17238 | 2022-08-03 | 2023-12-06
DEWAS / SONKATCH | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/4395544 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113852445 | Completed | 19890 | 2652 | 2023-10-02 | 2023-11-28
DEWAS / SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/4542764 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106015344 | Completed | 21870 | 18954 | 2024-10-01 | 2026-03-23
DEWAS / SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/4668680 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100588479 | Completed | 23490 | 21141 | 2024-10-08 | 2025-11-30
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5112887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114067027 | Completed | 23490 | 23490 | 2025-04-05 | 2026-07-30
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5122049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114081496 | Completed | 23490 | 22968 | 2025-04-05 | 2026-07-30
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5457833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106170227 | Completed | 23490 | 23490 | 2025-10-25 | 2026-07-30
DEWAS / SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/557108 — Construction of IAY House -IAY REG. NO. MP3564612 | Completed | 15030 | 14612 | 2017-02-01 | 2018-05-03
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5841469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113783799 | Completed | 23490 | 22968 | 2025-11-19 | 2026-07-30
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5841953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113647397 | Completed | 23490 | 23490 | 2025-11-09 | 2026-03-23
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5841982 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812453 | Completed | 23490 | 23490 | 2025-11-11 | 2026-07-21
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5842042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116140907 | Completed | 23490 | 23229 | 2025-11-15 | 2026-07-21
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5842232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113641455 | Completed | 23490 | 22446 | 2025-11-08 | 2026-07-21
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/5842336 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113772090 | Completed | 23490 | 23229 | 2025-12-03 | 2026-07-21
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/59945 — Construction of IAY House -IAY REG. NO. MP-20-002-015-001/48 | Completed | 14310 | 15521 | 2022-08-24 | 2024-01-23
DEWAS / SONKATCH | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/59946 — Construction of IAY House -IAY REG. NO. MP-20-002-015-001/70 | Completed | 14310 | 15555 | 2022-08-29 | 2024-01-23
DEWAS / SONKATCH | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002015/IF/IAY/639491 — Construction of IAY House -IAY REG. NO. MP4566803 | Completed | 15030 | 14672 | 2017-03-03 | 2018-05-03
DEWAS / SONKATCH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/2010 — क्रीडांगन,मा.शाला भवन | Completed | 193000 | 64153 | 2010-06-02 | 2013-02-13
DEWAS / SONKATCH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/2011 — क्रीडांगन प्राथमिक शाला भवन | Completed | 44000 | 81972 | 2010-06-02 | 2012-04-18
DEWAS / SONKATCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/22012034230921 — मेड गंधान - रामसिंह धनसिंह | Completed | 36000 | 5837 | 2015-12-21 | 2016-09-24
DEWAS / SONKATCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/22012034230923 — मेड बंधान - मणिधर किशन | Completed | 36000 | 3339 | 2015-11-02 | 2016-09-24
DEWAS / SONKATCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/22012034230924 — मेड बंधान - कोश्‍ल्‍याबाई सुरेन्‍द्रसिंह | Completed | 36000 | 34670 | 2015-11-02 | 2016-09-24
DEWAS / SONKATCH | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/22012034230926 — मेड बंधान - हरिसिंह प्रहलादसिंह | Completed | 36000 | 954 | 2015-11-04 | 2016-09-24
DEWAS / SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1720002015/LD/22012034302186 — shantidham nirman gadhkhajuriya | Completed | 575000 | 4472 | 2017-02-16 | 2022-10-22
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799394106 — मेढ बधा्ंन बनेसिह सजनसिह | Completed | 33000 | 24528 | 2013-06-08 | 2014-05-15
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799394111 — मेढ बधांन धर्मेन कीशन | Completed | 33000 | 20148 | 2013-06-08 | 2014-05-15
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799394115 — मेढ बधांन फुलकुवर कमलसिह | Completed | 33000 | 17520 | 2013-06-08 | 2014-11-11
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799394116 — मेढ बधांन ललीता बाई बिहारीलाल | Completed | 33000 | 14892 | 2013-09-11 | 2014-11-11
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799394117 — मेढ बधान हरीसिह रामसिह | Completed | 33000 | 15768 | 2013-06-08 | 2014-11-11
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799403930 — भुमी समतलीकरण कंवरलाल पूरणसिह | Completed | 195000 | 170820 | 2013-09-11 | 2014-05-15
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799403933 — भूमी समतलीकरण राधेश्‍याम पूरण | Completed | 195000 | 162060 | 2013-09-11 | 2014-05-20
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799403936 — भुमीसमतलीकरण ठाकुरसिह मोतीसिह | Completed | 195000 | 876 | 2013-09-11 | 2015-02-14
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799403937 — भूमी समतलीकरण कमलसिह धनसहि | Completed | 195000 | 147752 | 2013-09-11 | 2014-05-20
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799403938 — भुमी समतलीकरण पन्‍नालाल गंभीर | Completed | 195000 | 175200 | 2013-09-11 | 2014-05-15
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799404134 — मेड बंधान बनेसिह बोंदा | Completed | 33000 | 876 | 2013-09-11 | 2015-02-14
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799404145 — मेड बधांन तकेसिह बोदांजी | Completed | 33000 | 876 | 2013-09-11 | 2015-02-14
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799404150 — भुमी समतलीकरण बोन्‍दरमल हिरालाल | Completed | 195000 | 126144 | 2013-09-11 | 2014-05-15
DEWAS / SONKATCH | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/3799412875 — भुमि समतलिकरण,मणिधरसिंह किशनसिंह | Completed | 205000 | 158556 | 2013-11-27 | 2015-02-14
DEWAS / SONKATCH | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002015/LD/9926705622 — भुमी समतलीकरण,अयोध्‍याबाई रामसिंह | Completed | 71000 | 59505 | 2014-05-30 | 2016-01-31
DEWAS / SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034174951 — पंच परमेश्‍वर.प्रेम सोनी के मकान से कमलसिंह के घर | Completed | 188000 | 170062 | 2013-07-14 | 2015-03-12
DEWAS / SONKATCH | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002015/RC/22012034204585 — सुदूर सड़क गडखजुरीया/मनोहर राढी के खेत से बाबुलाल के | Completed | 1494000 | 1200663.96 | 2014-02-13 | 2024-05-22
DEWAS / SONKATCH | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002015/RC/22012034219419 — सुदूर सड़क ,बद्रीलाल के खेत से कमलसिंह के खेत | Completed | 1482000 | 932720.56 | 2014-05-30 | 2024-05-22
DEWAS / SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034286704 — पंच परमेश्‍वर,नाली निर्माण देवेन्‍द्र के बाडे से नाले तक | Completed | 20000 | 18126 | 2015-10-14 | 2016-05-15
DEWAS / SONKATCH | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034293698 — पंच परमेश्‍वर,नगजीराम के घर से देवधर्मराज मंन्दिर तक | Completed | 57000 | 49240 | 2015-12-21 | 2016-09-24
DEWAS / SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034325188 — सी सी रोड् निर्माण बाजार चौक गडखजुरिया | Completed | 66264 | 31062 | 2017-02-04 | 2018-07-15
DEWAS / SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034325201 — सी सी निर्माण नगजीराम के मकान से सुरज के मकान तक | Completed | 35778 | 14358 | 2017-02-06 | 2018-07-10
DEWAS / SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034331360 — c.c.road nirman dayaram ke makan se prathmik vidhyalay tak (ajaa mohalla) | Completed | 66331 | 30540 | 2017-03-18 | 2018-07-10
DEWAS / SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034337370 — सी.सी.रोड निर्माण झिंडा चोक पर | Completed | 88194 | 25972 | 2017-05-11 | 2018-07-10
DEWAS / SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002015/RC/22012034339697 — सुदूरसम्पर्क मार्ग मा.वि. कालोनि से अम्बाराम के खेत तक | Completed | 1498000 | 1467620.75 | 2017-05-30 | 2021-08-31
DEWAS / SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034339908 — सि.सि.रोड-सुरज के मकान से क्र्पाराम के मकान तक | Completed | 401200 | 1032 | 2017-06-08 | 2019-10-18
DEWAS / SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034520019 — C.C. Road Puliya nirman Bhawani singh ke makan se kaccha shamshan tak | Completed | 103000 | 94620 | 2020-04-26 | 2021-08-25
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034581532 — सी सी रोड निर्माण - मेनरोड से भागीरथ योगी के मकान तक | Completed | 81000 | 72761 | 2021-08-31 | 2021-12-28
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/22012034603187 — CC road Nirman shasakiy seva Sanstha ke pass | Completed | 46000 | 38412 | 2022-01-04 | 2022-09-18
DEWAS / SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002015/RC/262 — ग्रेव सडक,पप्पुसिह के खेत से बद्रीलाल के खेत तक | Completed | 496000 | 533262 | 2011-04-15 | 2015-03-11
DEWAS / SONKATCH | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002015/RC/263 — ग्रेवल सडक,नई आबादी से पप्पु शर्मा के खेत तक | Completed | 494000 | 389192 | 2012-03-17 | 2015-03-11
DEWAS / SONKATCH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002015/RC/3 — ग्रेवल सड्क, गढ्खजुरिया से ढाबला मार्ग | Completed | 487000 | 704834 | 2009-07-15 | 2012-04-18
DEWAS / SONKATCH | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002015/RC/33 — गेवल सड्क, तालोद मार्ग | Completed | 497000 | 416752 | 2010-04-03 | 2012-10-21
DEWAS / SONKATCH | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002015/RC/4 — आंतरिक मुरमीकरण, माध्‍यमिक शाला से टुंगनी मार्ग | Completed | 292000 | 286453 | 2009-07-01 | 2012-04-18
DEWAS / SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/406 — पंच परमेश्‍वर, बंशीलाल टेलर के घर से रजापुर | Completed | 151000 | 28512 | 2012-04-01 | 2012-12-19
DEWAS / SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002015/RC/531 — पंच परमेश्‍वर, राधेश्‍याम के मकान से क्रष्‍ण मन्दिर | Completed | 397000 | 137912 | 2013-01-29 | 2013-02-24
DEWAS / SONKATCH | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002015/RC/532 — पंच परमेश्‍वर, अनोखीलाल के मकान से भोलेनाथ के मकान तक | Completed | 127000 | 71512 | 2013-02-25 | 2015-05-14
DEWAS / SONKATCH | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002015/RC/पंचायत गढ्खजुरिया ग्रेवल सड्क, — ग्राम पंचायत गढ्खजुरिया ग्रेवल सड्क, गढ्खजुरिया से जामगोद मार्ग | Completed | 1917000 | 2828106 | 2008-03-29 | 2009-08-30
DEWAS / SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002015/RC/सी;रो्ड्, सोसायटी भवन से नई आबादी — ग्राम पंचायत गढ्खजुरिया, सीसीरो्ड्, सोसायटी भवन से नई आबादी तक | Completed | 231000 | 160110 | 2009-01-10 | 2009-01-23
DEWAS / SONKATCH | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002015/RC/ सी;सी;रो्ड्, श्रीक़ष्‍ण — ग्राम पंचायत गढ्खजुरिया, सीसीरो्ड्, श्रीक़ष्‍ण मंदिर से मदन ठाकुर के मकान तक | Completed | 129000 | 103542 | 2009-01-09 | 2009-01-15
DEWAS / SONKATCH | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002015/RS/22012034389694 — मानक प्राकलन शौचालय निर्माण विक्रम सिंह उमराव सिंह | Completed | 11000 | 2064 | 2018-01-20 | 2019-01-20
DEWAS / SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720002015/RS/22012034497485 — SBM- सामुदायिक स्वच्छता परिसर ग्राम Gadkhajuriya | Completed | 44000 | 39900 | 2020-09-28 | 2021-01-21
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720002015/RS/22012034506485 — नाली निर्माण - दयाराम के घर से गंगाराम के मकान तक | Completed | 47000 | 22388 | 2021-09-01 | 2022-11-02
DEWAS / SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1720002015/RS/22012034507258 — नाडेप निर्माण - कमला बाई पति रामसिंह | Completed | 14971.96 | 13112.5 | 2021-02-18 | 2022-11-16
DEWAS / SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1720002015/RS/22012034507260 — नाडेप निर्माण - अम्बाराम पिता देवाजी | Completed | 14687.93 | 12843 | 2021-02-20 | 2022-12-18
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1720002015/RS/22012034507261 — नाडेप निर्माण - लड्कुवर कन्हेयालाल | Completed | 14702.95 | 10894 | 2021-08-24 | 2023-01-17
DEWAS / SONKATCH | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of NADEP Compost structure for Groups / Construction of NADEP Compost structure for Groups | Construction of NADEP/Vermi Compost Pit | 1720002015/RS/22012034507262 — नाडेप निर्माण - ठाकुर लाल पिता गणपत | Completed | 14941.02 | 13613 | 2021-02-20 | 2022-11-16
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1720002015/RS/22012034542811 — SLWM Nadep Nirman DHARMEN SINGH SENDHAV KE BADE ME | Completed | 16615.96 | 12017 | 2021-10-14 | 2022-12-20
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720002015/RS/22012034550440 — नाली निर्माण - दयाराम के मकान से गंगाराम के मकान तक | Completed | 47000 | 3474 | 2021-11-27 | 2024-04-12
DEWAS / SONKATCH | 2016-2017 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1720002015/WC/22012034313132 — स्टॉप डेम सुधरीकरण उम्मेदसिह के खेत के पास | Completed | 160000 | 78076 | 2016-11-29 | 2019-12-07
DEWAS / SONKATCH | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1720002015/WC/22012034329936 — नवीन तालाब निर्माण माता | Completed | 266000 | 141286 | 2017-06-21 | 2019-06-04
DEWAS / SONKATCH | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002015/WC/22012034382223 — check dam (roji ghat) | Completed | 588000 | 539627 | 2018-05-14 | 2019-06-24
DEWAS / SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002015/WC/22012034485161 — recharge pit gadkhajuriya(middile school handpump) | Completed | 13427.22 | 9236 | 2019-08-26 | 2020-07-08
DEWAS / SONKATCH | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002015/WC/22012034485163 — recharge pit gadkhjuriya (lakhan ke ghar handpump) | Completed | 13427.22 | 8180 | 2019-08-27 | 2020-07-08
DEWAS / SONKATCH | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002015/WC/22012034768836 — CTR - रुफ वाटर हार्वेस्टिंग आगनवाड़ी भवन प्रा. वि. के पास गडखजूरिया | Completed | 24626.18 | 10240 | 2021-09-06 | 2024-07-19
DEWAS / SONKATCH | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720002015/WC/22012034877504 — CTR NALA DISTINGA DIVERSION | Completed | 228104.78 | 122257 | 2022-02-01 | 2024-05-16
DEWAS / SONKATCH | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002015/WC/22012034981904 — अमृत सरोवर योजना नवीन तालाब निर्माण आनंदी बाई के होडे के पास | Completed | 1122000 | 918612 | 2022-05-26 | 2024-04-24
DEWAS / SONKATCH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002015/WC/55 — तलाई निर्माण, रोटी बल्‍डी | Completed | 285000 | 278804 | 2010-04-22 | 2013-07-11
DEWAS / SONKATCH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002015/WC/56 — सार्वजनिक कुप निर्माण, माशा के सामने | Completed | 355000 | 178800 | 2010-04-22 | 2010-09-20
DEWAS / SONKATCH | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002015/WC/57 — सार्वजनिक कुप निर्माण, माता गोया के पास | Completed | 355000 | 255074 | 2010-04-01 | 2012-06-24
DEWAS / SONKATCH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002015/WC/गढ्खुरिया, तलाई निर्माण झीरी नाला — ग्राम पंचायत गढ्खुरिया, तलाई निर्माण झीरी नाला | Completed | 500000 | 397104 | 2009-02-25 | 2009-06-30
DEWAS / SONKATCH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sub Surface Dam / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720002015/WC/, तलाई निर्माण, माता का गोया — ग्राम पंचायत गढ्खजुरिया, तलाई निर्माण, माता का गोया | Completed | 500000 | 125651 | 2009-02-11 | 2009-06-18
DEWAS / SONKATCH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1720002015/WH/गढ्खजुरिया , तलाई जीर्णोऋार, बगीचे क — ग्राम पंचायत गढ्खजुरिया , तलाई जीर्णोऋार, बगीचे के पास | Completed | 157000 | 65520 | 2009-02-11 | 2009-05-14
DEWAS / SONKATCH | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1720002015/WH/तलाई जीर्णोऋार, मोगिया होड्ा — ग्राम पंचायत लोंदिया जागीर, तलाई जीर्णोऋार, मोगिया होड्ा | Completed | 140000 | 1911 | 2009-02-22 | 2009-02-28