## Work List
Exported on: 2026-09-10 22:54:55
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: JAMGOD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / SONKATCH | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1720002017/DP/22012034602847 — वसुंधा वंदन अमृत वाटिका मदनी धाम जामगोद | Ongoing | 55847.4 | 0 | 2023-09-06
DEWAS / SONKATCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Farm Forestry-Community / Boundary Line Plantation of Farm Forestry Trees for Community | Plantation | 1720002017/DP/22012034625205 — Walmiki Miyawaki Community Dense Plantation 0/25Acre Hanuman Mandir Parisar Jamgod | Ongoing | 343764.98 | 0 | 2024-09-16
DEWAS / SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/129073 — Construction of IAY House -IAY REG. NO. MP-20-002-017-001/52 | Approved | 27000 | 0 | 2016-02-05
DEWAS / SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/40994 — Construction of IAY House -IAY REG. NO. MP-20-002-017-001/058 | Approved | 27000 | 0 | 2015-11-24
DEWAS / SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/40995 — Construction of IAY House -IAY REG. NO. MP-20-002-017-001/18 | Approved | 27000 | 0 | 2015-11-24
DEWAS / SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/40996 — Construction of IAY House -IAY REG. NO. MP-20-002-017-001/28 | Approved | 27000 | 0 | 2015-11-24
DEWAS / SONKATCH | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/40997 — Construction of IAY House -IAY REG. NO. MP-20-002-017-002/1 | Approved | 27000 | 0 | 2015-11-24
DEWAS / SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/4563261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115923822 | Ongoing | 27000 | 0 | 2024-11-24
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5250014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104935256 | Ongoing | 27000 | 0 | 2025-05-26
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5262325 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812764 | Ongoing | 27000 | 0 | 2025-08-18
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5262626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113728041 | Physically Completed | 23490 | 0 | 2026-02-18 | 2026-08-16
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5263025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114113704 | Physically Completed | 23490 | 0 | 2026-02-18 | 2026-07-26
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5263327 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812605 | Ongoing | 27000 | 0 | 2026-02-20
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5270001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115812806 | Ongoing | 27000 | 0 | 2025-07-29
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5275726 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115802059 | Ongoing | 27000 | 0 | 2025-08-18
DEWAS / SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5290205 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115018689 | Approved | 27000 | 0 | 2025-03-17
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5301773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115355698 | Ongoing | 27000 | 0 | 2025-08-22
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5303057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115813226 | Ongoing | 27000 | 0 | 2025-08-18
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5315638 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104934884 | Ongoing | 27000 | 0 | 2025-08-18
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5322660 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106475202 | Ongoing | 27000 | 0 | 2025-09-17
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5324409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115796915 | Ongoing | 27000 | 0 | 2025-08-13
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5643579 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104934430 | Ongoing | 27000 | 0 | 2025-08-26
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113740036 | Ongoing | 27000 | 0 | 2026-02-20
DEWAS / SONKATCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116335604 | Ongoing | 27000 | 4200 | 2026-05-14
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864377 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116057391 | Ongoing | 27000 | 2100 | 2026-02-10
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114113686 | Ongoing | 27000 | 0 | 2026-01-30
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113727732 | Ongoing | 27000 | 0 | 2026-01-22
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126763160 | Ongoing | 27000 | 0 | 2026-01-14
DEWAS / SONKATCH | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113728000 | Approved | 27000 | 0 | 2025-03-03
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864402 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114708735 | Ongoing | 27000 | 0 | 2026-01-22
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864408 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115348794 | Ongoing | 27000 | 0 | 2026-01-14
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864433 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115797692 | Ongoing | 27000 | 0 | 2026-01-22
DEWAS / SONKATCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117587523 | Ongoing | 27000 | 3900 | 2026-06-06
DEWAS / SONKATCH | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126653836 | Approved | 27000 | 0 | 2025-04-09
DEWAS / SONKATCH | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002017/IF/IAY/5864502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114148373 | Ongoing | 27000 | 3000 | 2026-08-06
DEWAS / SONKATCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002017/WC/22012035240721 — Navin Nistar Talab nirman kary kajal koyari | Ongoing | 1895000 | 0 | 2025-01-12
DEWAS / SONKATCH | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Afforestation using forstry Trees for Comm / Along the coast Afforestation using forestry Trees for Community | Plantation | 1720/DP/22012034628900 — BAMBOO PLANTATION JAMGOD COMPT P 50 | Ongoing | 2217352 | 0 | 2025-02-15