## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002035/RC/22012034178110 — पंच परमेश्‍वर,सादीखेडा रोड से सवरसी रोड तक | Deleted | 253000 | 0 | 2013-08-14 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1720002037/AV/1062 — Aanganbadi Bhavan Nirman Sewa Kendra,SONKATCH | Completed | 709000 | 184260 | 2014-03-05 - 2016-10-25
DEWAS / SONKATCH / KULALA | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of workshed for Livelihood activity (Grps) / Construction of workshed for Livelihood activity for Groups | Construction of building/workshed for SHG | 1720002037/AV/22012034573675 — SLWM Segrication shed Kulala | Closed | 635824.35 | 0 | 2021-04-14 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Cyclone shelter for Community / Construction of Cyclone shelter for Community | Construction of Other Community Building/Assets | 1720002037/AV/22012034573900 — सेग्रिगेशन शेड निर्माण कुलाला | Closed | 0 | 0 | 2021-04-26 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1720002037/AV/22012034595413 — डाइनिंग हाल निर्माण मिडिल स्कूल कुलाला | Closed | 29369.97 | 0 | 2021-08-15 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720002037/DP/22012034435092 — सार्वजनिक पेयजल कूप निर्मल नीर सकत तलई के पास | Completed | 535000 | 442113 | 2018-12-29 - 2020-06-19
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720002037/DP/22012034435093 — जल कूप निर्मल नीर सकत तलई के पास | Deleted | 535000 | 0 | 2018-04-14 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720002037/DP/22012034483500 — nirmal neer nirman samsan ke pass | Deleted | 511874.63 | 1506 | 2020-03-11 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1720002037/DP/22012034600436 — वसुंधा वंदन अमृत वाटिका शांति धाम परिसर ग्राम पंचायत कुलाला | Closed | 0 | 0 | 2023-04-26 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1720002037/DP/22012034605385 — वसुधा वाटिका शासकीय विद्यालय परिसर कुलाला | Ongoing | 55847.4 | 221 | 2023-08-24 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720002037/DP/9993629276 — बास रोपण-शमशान घाट पर | Deleted | 24000 | 0 | 2015-08-24 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720002037/DP/कुलाला, रतनजोत रोपण, गांव से भोंरासा — ग्राम पंचायत कुलाला, रतनजोत रोपण, गांव से भोंरासा काकड्. | Completed | 54000 | 20683 | 2008-08-22 - 2008-08-11
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720002037/DP/कुलाला, रतनजोत रोपण, देवमहाराम मंदिर — ग्राम पंचायत कुलाला, रतनजोत रोपण, देवमहाराम मंदिर से बुदासा की ओर | Completed | 24000 | 24230 | 2008-08-01 - 2009-08-30
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720002037/DP/कुलाला, रतनजोत रोपण, नई आबादीसे भलाई — ग्राम पंचायत कुलाला, रतनजोत रोपण, नई आबादीसे भलाईखुर्द | Completed | 13000 | 5870 | 2008-08-14 - 2009-08-20
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720002037/DP/कुलाला, रतनजोत रोपण, भोंरासा काकड्. — ग्राम पंचायत कुलाला, रतनजोत रोपण, भोंरासा काकड्. | Completed | 47000 | 41460 | 2008-08-24 - 2008-08-28
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1720002037/DW/9993659433 — सार्वजनिक कूप निर्माण शमशान घाट सादी खेडा मार्ग | Deleted | 425000 | 0 | 2016-01-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002037/IF/1000016785 — खेत तालाब, सीगाराम पुनाजी | Completed | 127000 | 114912 | 2013-06-05 - 2014-06-15
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/2058 — कुप निर्माण,मनीबाई ओंकारलाल | Completed | 241000 | 118809 | 2011-06-06 - 2012-05-25
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002037/IF/2059 — खेत तालाब,छगनलाल रामचन्द्र | Completed | 119000 | 59292 | 2011-05-28 - 2013-07-05
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/2158 — कुप निर्माण,दिलीप रमेशचन्द | Completed | 256000 | 303374 | 2012-04-22 - 2014-02-17
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034337374 — kapildhara saha khet talab baulal dungaji | Completed | 230000 | 229552 | 2017-05-06 - 2018-07-02
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002037/IF/22012034341767 — पौध रोपण रामचरन चौधरी के मकान से शान्तिधाम तक | Completed | 335000 | 48952 | 2017-05-22 - 2022-11-03
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002037/IF/22012034351938 — vraksha ropan samudayak parisar anganwadi etc. | Completed | 335000 | 38374 | 2017-07-07 - 2022-11-03
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034385275 — Khet talab with kup nirman | Deleted | 0 | 0 | 2017-10-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034406071 — कपिलधारा कूप निर्माण फूलसिंह पिता उदयसिंह यादव | Completed | 210000 | 180144 | 2018-05-12 - 2019-09-28
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034415777 — kapildhara kup with recharj pit Ranchhod salagram | Completed | 210000 | 200224 | 2018-06-01 - 2019-09-28
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1720002037/IF/22012034473275 — kupnirman surajsingh/motisingh | Deleted | 0 | 0 | 2019-01-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034473278 — kupnirman suraj singh/moti singh | Completed | 210000 | 200658 | 2019-03-10 - 2019-09-20
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034473970 — कपिलधारा कूप निर्माण सुरजसिंह छोगालाल | Completed | 210000 | 195876 | 2019-03-11 - 2024-02-13
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1720002037/IF/22012034672874 — खेत तालाब निर्माण लीलाबाइ हरनाथ कुलाला | Completed | 332145.94 | 231601 | 2021-04-10 - 2024-02-13
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen graded Bund for Individuals / Construction of Earthen graded Bund for Individuals | Construction of Bund | 1720002037/IF/22012034714861 — CTR MED BANDHAN UNKARLAL MOTISINGH | Completed | 59880.45 | 54040 | 2021-04-24 - 2022-09-09
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002037/IF/22012034737962 — कूप निर्माण कार्य पार्वतीबाइ,श्यामुबाइ,सावित्राबाइ | Completed | 239834.22 | 211779 | 2021-05-06 - 2025-06-21
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Staggered Trench for individual / Construction of Staggered Trench for individual | Construction of Trench | 1720002037/IF/22012034779870 — CTR MED BANDHAN RAMCHARAN GHASIRAM | Deleted | 0 | 0 | 2021-05-13 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1720002037/IF/22012034782171 — खेत तालाब निर्माण कार्य महेश गेंदालाल | Closed | 335158.83 | 0 | 2021-05-30 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Const of Level Bench Terrace for Individual / Construction of Level Bench Terrace for Individual | Terracing | 1720002037/IF/22012034792888 — CTR MED BANDHAN | Deleted | 0 | 0 | 2021-05-30 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002037/IF/22012034814444 — व्यक्तिगत सोख्ता गड्डा निर्माण कार्य/SLWM/5 | Completed | 17639.02 | 5790 | 2021-10-07 - 2022-06-20
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720002037/IF/22012034846705 — व्यक्तिगत सोक पिट निर्माण - संख्या 15 | Closed | 53180.73 | 0 | 2021-08-02 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1720002037/IF/22012034864059 — वृक्षारोपण कार्य शांतीधाम परिसर कुलाला | Deleted | 70000 | 965 | 2021-10-25 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034890472 — कूप निर्माण कार्य अजय, विजय, रुखमाबाई | Deleted | 0 | 0 | 2021-10-02 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/22012034917694 — कूप निर्माण कार्य अजय,सुनिल,माँनसिंह कुलाला | Deleted | 363452.8 | 204 | 2022-05-13 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1720002037/IF/22012035399517 — JGSA2025 Recharge structure Suraj Singh -Motisingh | Physically Completed | 25899.46 | 24691.94 | 2025-05-08 - 2026-03-31
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002037/IF/22012035450304 — JGSA2025 Recharge structure Sitaram -Hameer | Physically Completed | 25899.46 | 24430.94 | 2025-05-08 - 2026-04-25
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720002037/IF/22012035543238 — JGSA2025 Recharge structure Manibai-onkarlal kulala | Physically Completed | 25899.46 | 24449.15 | 2025-06-10 - 2026-03-31
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720002037/IF/22012035618751 — EK BAGIYA MAA KE NAM MAMTA YADAV MP-20-002-037-001/134 | Ongoing | 272600.27 | 30685 | 2025-09-18 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002037/IF/77 — खेत तालाब पूरणसिंह किशनसिंह | Completed | 39000 | 40000 | 2010-05-18 - 2010-06-14
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/9993681725 — इंदरा आवास,सिगाराम पुनाजी अजा कुलाला | Completed | 7155 | 6996 | 2015-10-21 - 2017-05-25
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/9993681730 — इंदरा आवास,कमल जगन्‍नाथ पि वर्ग कुलाला | Completed | 7155 | 6678 | 2015-10-21 - 2017-05-25
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1720002037/IF/9993681732 — इंदिरा अवास,मुन्‍नालाल उमराव पि वर्ग कुलाला | Completed | 7155 | 6678 | 2015-10-21 - 2017-05-25
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/9993681735 — इंदिरा अवास,कुमेरसिंह मुन्‍शी अजा कुलाला | Completed | 7155 | 6996 | 2015-10-21 - 2017-05-25
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002037/IF/9993728254 — med bandhan mahesh nandkishor | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002037/IF/9993728255 — med bandhan babulal rameshwar | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002037/IF/9993728257 — med bandhan rajendra-chhogalal | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Liquid Bio Manures: Sanjeevak or Amrit Pani / Construction of Infrastructure for Liquid Biomanure for Individuals | Bio-Fertilizer | 1720002037/IF/9993728272 — med bandhan kishor badrilal (obc) | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Liquid Bio Manures: Sanjeevak or Amrit Pani / Construction of Infrastructure for Liquid Biomanure for Individuals | Bio-Fertilizer | 1720002037/IF/9993728275 — khet talab, babulal-dongaji | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Leveling and Shaping / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720002037/IF/9993728279 — bhumi samtalikarn, sakuntla bai -gangaram | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/194136 — Construction of IAY House -IAY REG. NO. MP-20-002-037-001/85 | Approved | 23490 | 0 | 2015-12-17 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/2118507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4495268 | Closed | 17100 | 0 | 2019-06-27 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/254736 — Construction of IAY House -IAY REG. NO. MP2101847 | Completed | 15030 | 15390 | 2017-01-25 - 2018-04-25
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/3924850 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106322939 | Completed | 18360 | 18156 | 2022-05-28 - 2023-07-13
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/3933727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106626699 | Completed | 18360 | 17136 | 2022-05-28 - 2022-11-24
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/4381898 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114850324 | Completed | 18360 | 18241 | 2022-11-22 - 2023-07-13
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/4544324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106626728 | Ongoing | 23490 | 20412 | 2024-10-17 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/4544667 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106105727 | Physically Completed | 21870 | 21870 | 2024-10-17 - 2026-05-18
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5112853 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114055687 | Completed | 23490 | 23490 | 2025-04-09 - 2025-10-03
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5114886 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105432417 | Physically Completed | 23490 | 23490 | 2025-04-02 - 2026-05-18
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5117154 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151203366 | Physically Completed | 23490 | 23490 | 2025-04-09 - 2026-04-05
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5117673 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142744625 | Approved | 23490 | 0 | 2024-09-15 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5117677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142784997 | Approved | 23490 | 0 | 2025-03-02 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5118102 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114850216 | Physically Completed | 23490 | 23490 | 2025-05-14 - 2026-05-18
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5122770 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100995682 | Completed | 23490 | 23490 | 2025-04-02 - 2025-10-03
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5126699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106322875 | Ongoing | 23490 | 20619 | 2025-04-02 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5129904 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106626593 | Ongoing | 23490 | 21924 | 2025-09-04 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5130103 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100970945 | Physically Completed | 23490 | 23490 | 2025-07-31 - 2025-12-25
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5133624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106323100 | Physically Completed | 23490 | 23490 | 2025-07-31 - 2026-02-24
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5133625 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106323199 | Physically Completed | 23490 | 23229 | 2025-04-02 - 2026-02-11
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5166674 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114850145 | Physically Completed | 23490 | 23490 | 2025-07-02 - 2025-12-13
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5182021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142729215 | Physically Completed | 23490 | 23490 | 2025-04-09 - 2026-01-03
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5182082 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147611403 | Approved | 23490 | 0 | 2025-03-05 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5186245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142746385 | Physically Completed | 23490 | 23490 | 2025-04-09 - 2026-05-18
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5189395 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106109168 | Ongoing | 23490 | 18792 | 2025-07-31 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5198690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147611471 | Ongoing | 23490 | 14094 | 2025-07-31 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5200050 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114850062 | Physically Completed | 23490 | 23490 | 2026-01-14 - 2026-06-14
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5201506 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142770208 | Approved | 23490 | 0 | 2025-03-06 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5202217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100971359 | Physically Completed | 23490 | 23229 | 2025-05-14 - 2026-05-20
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5219845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106626657 | Ongoing | 23490 | 21924 | 2025-04-19 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5222856 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115100948 | Physically Completed | 23490 | 23490 | 2025-07-02 - 2026-05-18
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5229378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114849798 | Physically Completed | 23490 | 23490 | 2025-07-23 - 2026-01-14
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5231641 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142773827 | Completed | 23490 | 23490 | 2025-05-23 - 2025-10-03
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5237099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105432097 | Ongoing | 23490 | 6264 | 2025-04-02 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5240878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142789629 | Approved | 23490 | 0 | 2025-03-05 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5262115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142744225 | Approved | 23490 | 0 | 2025-03-02 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5572796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141862994 | Ongoing | 23490 | 21924 | 2025-09-04 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/5770000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114849914 | Ongoing | 23490 | 3132 | 2026-06-09 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/68205 — Construction of IAY House -IAY REG. NO. MP-20-002-037-001/51 | Approved | 23490 | 0 | 2016-01-01 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/68206 — Construction of IAY House -IAY REG. NO. MP-20-002-037-001/80 | Approved | 23490 | 0 | 2016-01-01 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720002037/IF/IAY/769608 — Construction of IAY House -IAY REG. NO. MP3416017 | Completed | 15030 | 13416 | 2017-09-20 - 2019-06-07
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720002037/IF/कूप निर्माण, सीताराम हमीर — कपिलधारा कूप निर्माण, सीताराम हमीर | Completed | 201000 | 109360 | 2009-05-15 - 2011-03-16
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/22012034231170 — मेड बंधान - चन्‍द्रकान्‍ता रामचरण | Completed | 35000 | 23850 | 2016-01-12 - 2016-05-15
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/22012034231171 — मेड बंधान - बाबुलाल कन्‍हैयालाल | Deleted | 35000 | 0 | 2015-10-01 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/22012034231172 — मेड बंधान - बाबुलाल डुगाजी | Completed | 35000 | 10924 | 2015-12-30 - 2016-05-15
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Pebble Bunding / Construction of Pebble peripheral/farm/field Bund for Community | Construction of Bund | 1720002037/LD/22012034263950 — मेड बंधान मूकेश भूरा | Deleted | 25000 | 0 | 2015-07-01 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/3799392975 — मेढ बधांन सिंगाराम पूना | Completed | 33000 | 31536 | 2013-06-05 - 2013-10-16
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/3799392980 — मेढ बधांन पदमसिह चेनसिह | Completed | 33000 | 27156 | 2013-06-05 - 2014-02-15
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/3799396116 — मेड बंधान,कमल नराण | Completed | 33000 | 24528 | 2013-06-15 - 2014-05-20
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/3799396117 — मेड बंधान,कैलास पुनमचन्‍द | Completed | 33000 | 25112 | 2013-06-15 - 2014-05-25
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/3799401833 — क्रिडान्‍गन,शासकिय माध्‍यमिक विध्‍यालय | Completed | 206000 | 182163.49 | 2013-08-14 - 2015-02-16
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720002037/LD/3799412895 — मेढ बंधान,प्रकाश जगन्‍नाथ | Completed | 33000 | 13140 | 2013-11-28 - 2014-02-15
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/139 — ग्रेवल सडक निर्माण,नाथुसिह के खेत से चोकीदार के खेत तक | Completed | 497000 | 351080 | 2010-12-01 - 2013-01-05
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/140 — ग्रेवल सडक निर्माण,चोकीदार के खेत से चेनसिह के खेत तक | Completed | 497000 | 427264 | 2010-11-23 - 2013-07-05
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/194 — ग्रेवल सडक निर्माण,कांतीलाल के खेत से सरदारसिह के खेत तक | Completed | 500000 | 500236 | 2011-06-06 - 2013-07-05
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034167886 — पंच परमेश्‍वर, राजेन्‍द्र शर्मा के बाडे से मुन्‍ना | Completed | 98000 | 33303 | 2013-05-30 - 2015-02-16
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034169591 — पंच परमेश्‍वर, उदयसिह के मकान से मनोहर के मकान की | Completed | 416000 | 142815 | 2013-06-05 - 2015-02-16
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034178111 — पंच परमेश्‍वर,शर्मा जी के मकान से राजामहाराज के घर कि और | Completed | 138000 | 138120 | 2013-08-14 - 2014-02-15
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034192503 — पंच परमेश्‍वर,सादीखेडा रोड से सवरसी रोड तक | Completed | 92000 | 91188 | 2013-11-28 - 2014-02-15
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034202270 — खेत सडक,/कुलाला/धीरजसिंह के खेत से प्रकास के खेत त | Deleted | 1281000 | 0 | 2014-02-03 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034202271 — खेत सडक/कुलाला/मनोर के खेत से धीरजसिंह के खेत | Deleted | 1464000 | 0 | 2014-02-03 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034206153 — खेत सडक/कुलाला/हरिसिंह के खेत से सरदार के खेत तक | Completed | 1465000 | 743719 | 2014-02-19 - 2014-11-13
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034218492 — खेत सडक,विक्रम सेट के खेत से चरखा के तरफ | Completed | 553000 | 528043.4 | 2014-05-22 - 2016-01-25
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034218495 — खेत सडक,सरदारसिंह यादव के खेत से काकड तक | Completed | 1465000 | 1106959.82 | 2014-05-22 - 2017-02-25
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034218499 — खेत सडक,नापाखेडी वाले के खेत से पुनमचन्‍द के खेत त | Completed | 823000 | 538236.15 | 2014-05-28 - 2017-01-12
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034223353 — पंच परमेश्‍वर सीसीरोड देवमहाराज से पंचायत भवन तक | Completed | 58000 | 11618 | 2014-07-10 - 2015-04-19
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034224310 — पंच परमेश्‍वर सीसीरोड विजेन‍ के मकान से हरलालसिं | Completed | 175000 | 128147 | 2014-07-10 - 2015-02-20
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034292763 — पंच परमेश्‍वर,बाबुलाल पुनाजी के घर से रमेश के घर तक | Completed | 15000 | 16625 | 2015-12-30 - 2018-02-07
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034296096 — नाली निर्माण ओमसेठ के मकान से सुरजसिंह के मकान तक | Deleted | 0 | 0 | 2015-07-01 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034297147 — cc raod parfamens grand tejaji maharaj ke chok se mansingh beldar ke makan tak | Completed | 58000 | 56573 | 2016-02-05 - 2017-10-25
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034317893 — नालि निर्मााण,ओम सेठ के घर से सुरज बद्रीलाल के घर तक | Completed | 33000 | 33066 | 2016-12-21 - 2018-05-15
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034324498 — cc road nirman dilip Rathore ke ghar se meharvan kesuji ke ghar tak | Deleted | 281000 | 0 | 2017-02-03 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/22012034330339 — सुदुर ग्राम संपर्क सडक निर्माण सकत मोहल्‍ले मजरे सादीखेडा रोड | Completed | 1988000 | 1491175.81 | 2017-03-11 - 2019-06-07
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034330837 — cc road nirman narayansigh ke makan se ramesh ke ghar tak | Completed | 7200 | 3507 | 2017-03-18 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034331799 — cc road nirman sekhar omprakash ke ghar se mansing ke ghar tak | Completed | 71100 | 35730 | 2017-03-18 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034333178 — cc road nirman kalu bapuji ke ghar se girdhari ke ghar tak | Completed | 24200 | 10080 | 2017-03-25 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034333233 — cc road nirman peeru hari ke ghar se prahlad keshu ke ghar tak | Completed | 21000 | 9288 | 2017-05-13 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034333244 — cc road nirman tolaram hari ke ghar se ramsingh ke ghar tak | Completed | 16000 | 7194 | 2017-03-25 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034333249 — cc road nirman meharvan kesuji ke ghar se prahlad somaji ke ghar tak | Completed | 16000 | 7194 | 2017-03-25 - 2019-06-07
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034333252 — cc road nirman devanarayan mandir se anganwadi bhawan tak | Completed | 212000 | 95886 | 2017-03-25 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034338196 — cc road nirman anganwadi bhawan se panchayat bhawan tak | Completed | 128000 | 47472 | 2017-05-18 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034535860 — सी सी रोड निर्माण - हरिजन मोहल्ला (ब्लाक) कुलाला | Completed | 34200 | 33820 | 2020-08-26 - 2022-09-09
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034535863 — सी सी रोड निर्माण - शाशाकीय मधामिक विद्यालय के सामने कुलाला | Completed | 42100 | 39900 | 2020-08-26 - 2022-09-09
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034535864 — नाली निर्माण - शाशाकीय माध्यमिक विद्यालय के सामने कुलाला | Completed | 18800 | 14856 | 2020-12-23 - 2022-09-09
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/22012034553310 — सीसी रोड निर्माण पंचायत भवन से रूप सिंह के मकान की ओर | Completed | 53000 | 54340 | 2020-12-23 - 2022-09-09
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/301 — पंच प्रमेश्व्रर,सी.सी रोड हनुमन्दिर से गाडी तरफ | Completed | 57000 | 303613 | 2012-04-02 - 2013-01-02
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/409 — ग्रेवल सडक निर्माण,बुदासा से मदनलाल के खेत तक | Completed | 499000 | 546629.9 | 2012-06-25 - 2014-02-15
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720002037/RC/410 — आंतरिक मार्ग,मदनलाल के खेत से बद्रीलाल के खेत तक | Completed | 499000 | 605190.8 | 2012-06-25 - 2014-02-17
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720002037/RC/551 — पंच परमेश्‍वर गडी से लक्ष्‍मीनारायण शर्मा पीपल तरफ | Completed | 170000 | 210162.3 | 2013-02-01 - 2014-02-15
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/61 — ग्रेवल सडक,पंचायत भवन से श्मशान घाट तक | Completed | 300000 | 361416 | 2010-05-04 - 2011-10-08
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/68 — आंतरिक मार्ग,हरिजन मोहल्ले से बलवान के मकान तक | Completed | 33000 | 32258 | 2010-08-02 - 2012-04-20
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/69 — आंतरिक मार्ग,आबादी से हरिजन मोहल्ले | Completed | 50000 | 49474 | 2010-07-15 - 2012-04-20
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/70 — आंतरिक मार्ग,हरिजन मोहल्ले से पीरालाल के मकान तक | Completed | 49000 | 48974 | 2010-07-24 - 2012-04-20
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/गेवल रोड देवराज मन्‍दीर से बुदासा की — गेवल रोड देवराज मन्‍दीर से बुदासा की ओर कुलाला | Completed | 1687000 | 1436488 | 2007-12-28 - 2011-09-27
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/गेवल सडक कुलाला देव महारज मन्‍दीर से — गेवल सडक कुलाला देव महारज मन्‍दीर से तालाब पाल तक | Completed | 333000 | 369932 | 2007-11-30 - 2011-03-09
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720002037/RC/गेवल सडक संकेत तालाइ से मीरजापुर काक — गेवल सडक संकेत तालाइ से मीरजापुर काकड तक कुलाल | Completed | 946000 | 990622 | 2008-01-18 - 2011-05-16
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1720002037/RC/ग्रेवल सडक सकत तलाई से मि‍जापुर काकड — ग्रेवल सडक सकत तलाई से मि‍जापुर काकड (कुलाला) | Deleted | 0 | 0 | 2012-04-20 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1720002037/RC/ग्रेवल साडक श्‍मशानघाट से वि‍क्रम चौ — ग्रेवल साडक श्‍मशानघाट से वि‍क्रम चौधरी के खेत तक (कुलाला) | Completed | 713000 | 746970 | 2008-03-24 - 2011-02-25
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002037/RS/22012034289245 — शौचालय निर्माण,जितेन्‍द्र हिरालाल | Completed | 3180 | 3180 | 2015-10-21 - 2016-05-30
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720002037/RS/22012034289251 — शौचालय निर्माण,बब्‍लु - गोरधन पि वर्ग | Completed | 3180 | 3180 | 2015-10-21 - 2016-05-30
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720002037/RS/22012034497363 — SBM- सामुदायिक स्वच्छता परिसर ग्राम कुलाला | Completed | 44000 | 23826 | 2020-09-28 - 2022-11-12
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002037/WC/2084 — नविन तलाई निर्माण,पाखे मे पहाडी के पास | Completed | 324000 | 152856 | 2012-04-23 - 2013-01-05
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1720002037/WC/22012034355036 — Bori Bandhan charnoi chandrakanta bai ke khet ke pas | Completed | 3300 | 1032 | 2017-09-26 - 2018-06-01
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1720002037/WC/22012034355080 — Bori Bandhan charnoi badrilal bhagirath ke khet ke pas | Completed | 3300 | 1032 | 2017-09-26 - 2018-06-01
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002037/WC/22012034437465 — chekdam kulala | Deleted | 0 | 0 | 2019-05-25 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720002037/WC/22012034465756 — परकोलेसन टेंक शमशान घाट के पास | Deleted | 0 | 0 | 2019-04-14 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002037/WC/22012034477342 — recharge pit (government school campouse) | Closed | 13427.22 | 0 | 2019-04-24 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002037/WC/22012034488541 — सोख्ता गड्डा शमशान घाट के पास | Completed | 13427.22 | 6336 | 2019-09-19 - 2020-09-08
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720002037/WC/22012034488542 — सोख्ता गड्डा जितेंद्र के बाड़े के पास | Completed | 13427.22 | 5984 | 2019-09-19 - 2020-09-08
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002037/WC/22012034529404 — parculation tank pahadi pe prem singh ke khet k pass | Completed | 208114.88 | 182956 | 2020-03-11 - 2022-09-09
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002037/WC/22012034529405 — parcolation tank badri ke khet ke pass pahadi par | Completed | 352525.44 | 294864 | 2020-03-11 - 2025-03-20
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720002037/WC/22012034548303 — contour trench (budasa pahadi ke paas) | Completed | 206732.62 | 88350 | 2020-05-18 - 2022-11-24
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002037/WC/22012034548304 — percolation tank (tower ke paas pahadi per) | Completed | 330636.9 | 320910 | 2020-05-18 - 2021-01-20
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002037/WC/22012034615385 — परकोलेसन टेंक 2 टावर के पास | Deleted | 0 | 0 | 2021-01-24 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720002037/WC/22012034615388 — परकोलेसन टेंक पहाड़ी पर | Completed | 506243.31 | 400599.68 | 2021-03-12 - 2025-06-10
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720002037/WC/22012034623684 — सी पी टी पहाड़ी पर टावर के पास | Deleted | 0 | 0 | 2021-03-08 -
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720002037/WC/22012034664343 — CTR NALA TRENCHING SINGARAM PUNAJI KE KHET SE CHANDRKANTA BAAI KE KHET TAKKE KHET SE | Completed | 80596.13 | 83376 | 2021-05-27 - 2022-09-09
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720002037/WC/22012034664348 — CTR NALA TRENCHING MANHOR KE KHET SE SUNIL SHRIRAM KE KHET TAK | Completed | 78386.89 | 56742 | 2021-06-27 - 2022-09-09
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002037/WC/22012034665227 — CTR cpt pahadi per Tower k Pas | Closed | 46127.89 | 0 | 2021-04-14 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720002037/WC/22012034769207 — CTR ROOF WATER HARVESTING PANCHAYAT BHAWAN | Closed | 24484.14 | 0 | 2021-04-14 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1720002037/WC/22012034893304 — तालाब जिर्णोद्वार सकत पर कुलाला | Completed | 491775.25 | 238085 | 2022-04-29 - 2024-06-19
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1720002037/WC/22012034893317 — तालाब जिर्णोद्वार गौ तलाई कुलाला | Deleted | 877629.18 | 204 | 2022-04-11 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen peripheral Bund for Community / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1720002037/WC/22012034948116 — nala diversion work nagjiram ke khet ke pass | Completed | 203548.23 | 170136 | 2022-04-16 - 2024-02-09
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002037/WC/22012035015074 — परकोलेसन टैंक निर्माण - पहाड़ी के उपर नारायण सिंह के खेत के पास | Closed | 394307.17 | 0 | 2022-10-11 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720002037/WC/22012035253401 — Parcolation tank pahadi par part 2 | Closed | 199910.77 | 0 | 2025-01-26 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002037/WC/कपील धारा कुलाला भगीरथ अमरा — कपील धारा कुलाला भगीरथ अमरा | Deleted | 66400 | 0 | 2007-10-31 -
DEWAS / SONKATCH / KULALA | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1720002037/WC/कूप निर्माण, गोया की कुण्‍डी के पास — सार्वजनिक कूप निर्माण, गोया की कुण्‍डी के पास | Deleted | 358000 | 0 | 2009-02-22 -
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720002037/WC/सार्वजनिक कूप निर्माण, गोया की कुण्‍ — सार्वजनिक कूप निर्माण, गोया की कुण्‍डी के पास | Completed | 358000 | 135512 | 2009-02-27 - 2010-06-02
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1720002037/WH/19961514 — talab jirnodhar nirman sakat talai | Completed | 34000 | 20640 | 2017-05-26 - 2018-06-01
DEWAS / SONKATCH / KULALA | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1720002037/WH/कुलाला, तालाब जीर्णोधार, गो तलाई — ग्राम पंचायत कुलाला, तालाब जीर्णोधार, गो तलाई | Completed | 458000 | 66066 | 2009-01-27 - 2012-04-20
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Desilting / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1720002037/WH/तलाई जीर्णोऋार, गो तलाई — ग्राम पंचायत कुलाला, तलाई जीर्णोऋार, गो तलाई | Completed | 458000 | 230503 | 2009-01-27 - 2012-04-20
DEWAS / SONKATCH / KULALA | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1720002/IF/22012034863910 — वृक्षा रोपण कार्य शांतिधाम परिसर कुलाला | Closed | 70000 | 0 | 2021-08-15 -