## Work List
Exported on: 2026-10-19 00:16:49
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: TIGRIYA CHOTA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / DEWAS | 2021-2022 | C--COMMON INFRASTRUCTURE FOR NRLM COMPLIANT SELF HELP GROUPS / Anganwadi/Other Rural Infrastructure | Constr of agri produce storage building for groups / Construction of Agricultural produce storage Building for Groups | Constr of Food Grain storage | 1720003060/AV/22012034591064 — kachara sangrahan sed nirman parwatipura | Completed | 122271.84 | 89144 | 2021-11-10 | 2022-07-08
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1720003060/AV/22012034608668 — kachra sangrahan sed nirman darmshala ke pass | Closed | 0 | 0 | 2021-10-05
DEWAS / DEWAS | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1720003060/AV/22012034631717 — Santidham Sed Nirman Tigriya Chhota | Closed | 0 | 0 | 2023-01-24
DEWAS / DEWAS | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1720003060/AV/22012034636067 — SANTIDHAM NIRMAN TIGRIYA CHHOTA | Completed | 330972.38 | 327166.9 | 2023-07-24 | 2024-08-07
DEWAS / DEWAS | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/DP/103 — निर्मल वाटिका पार्वतीपुरा | Completed | 167000 | 96363 | 2010-06-07 | 2013-03-25
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1720003060/DP/22012034544408 — praimari schhol me nyutrishan gardan t,chhota | Completed | 18429.68 | 5922 | 2022-02-09 | 2024-09-10
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1720003060/DP/22012034544409 — praimari schhol me nyutrishan ghardan parwatipura | Closed | 0 | 0 | 2021-10-02
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1720003060/DP/22012034544410 — praimari schhol me nyutrishan ghardan parwatipura | Completed | 18429.68 | 4764 | 2022-02-14 | 2024-02-15
DEWAS / DEWAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1720003060/DP/22012034602984 — Vasundha vandan Tigriya Chhota | Completed | 55847.4 | 19702 | 2023-08-27 | 2025-07-06
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in Fields for Community | Plantation | 1720003060/DP/22012034618245 — vraksharopan parvatipura 2 | Ongoing | 453563.17 | 118768 | 2024-06-29
DEWAS / DEWAS | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1720003060/DP/31 — व्रिक्शारोपण प्राथमीक शाला | Completed | 0 | 171242 | 2008-12-06 | 2013-03-28
DEWAS / DEWAS | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720003060/DP/9993629062 — Samudayik vraksharopan Tigriya chhota | Completed | 179000 | 23865 | 2015-08-22 | 2018-09-30
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034305262 — nadep composting ramcharan motiram | Completed | 13200 | 13058 | 2016-12-01 | 2017-03-18
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034315220 — नाडेप कम्पोस्ट घनश्याम कन्हेयालाल | Completed | 13200 | 12724 | 2017-02-04 | 2017-03-18
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034315284 — नाडेप कम्पोस्ट राधेश्याम बाबूलाल | Completed | 13200 | 23778 | 2017-02-04 | 2017-03-18
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034315286 — नाडेप कम्पोस्ट बलराम केदार | Completed | 13200 | 13058 | 2017-02-04 | 2017-03-18
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034320667 — नाडेप निर्माण कार्य संजय राम गोपाल | Completed | 13200 | 13058 | 2017-02-15 | 2017-03-18
DEWAS / DEWAS | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003060/IF/22012034343206 — vraksaropan pvatipura school samudayik bhavan | Completed | 335000 | 173264 | 2017-05-26 | 2022-12-12
DEWAS / DEWAS | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003060/IF/22012034343312 — vraksaropan harinarayan kekhet se ranchod ke khet tak | Completed | 335000 | 174294 | 2017-05-26 | 2022-12-12
DEWAS / DEWAS | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003060/IF/22012034344360 — vraksharopan ramesh ke gar se sekhar ke gar tak | Completed | 335000 | 220708 | 2017-05-29 | 2022-12-12
DEWAS / DEWAS | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034538840 — NADEP NIRMAN NILESH S/O BRAMHANNAD | Closed | 12412.41 | 0 | 2020-01-26
DEWAS / DEWAS | 2019-2020 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034538842 — NADEP MIRMAN KAILASH S/O SALIGRAM | Closed | 12412.41 | 0 | 2020-02-26
DEWAS / DEWAS | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034538844 — NADEP NIRMAAN VISHNU DATTU JI | Deleted | 12412.41 | 2280 | 2020-08-17
DEWAS / DEWAS | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034538845 — NADEP NIRMAN GOVRDHAN DATTU JI | Deleted | 12412.41 | 2280 | 2020-08-17
DEWAS / DEWAS | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034538846 — NADEP NIRAMN BADRI DATTU JI | Deleted | 12412.41 | 2280 | 2020-08-17
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1720003060/IF/22012034810261 — dabari nirman shekhar t.chhota | Completed | 100069.2 | 66006 | 2021-06-27 | 2022-10-05
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003060/IF/22012034818231 — sokhata gadha nirman manohar babulal | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003060/IF/22012034818234 — sokhata gadha nirman govind thavarji | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003060/IF/22012034818235 — sokhata gadha nirman govardan dattuji | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003060/IF/22012034818237 — sokhata gadha nirman badri dattu ji | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003060/IF/22012034818245 — sokhata gadha nirman kelash dattu | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003060/IF/22012034818251 — sokhata gadha nirman vishnu dattu | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034845955 — nadep nirman kelash dattu | Closed | 12030.91 | 0 | 2021-08-17
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034845957 — nadep nirman pavan sitaram | Closed | 0 | 0 | 2021-08-17
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034845958 — nadep nirman satish shivjiram | Closed | 0 | 0 | 2021-08-17
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/22012034845960 — nadep nirman balmakund chogalal | Closed | 0 | 0 | 2021-08-17
DEWAS / DEWAS | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation of Horti-Trees for Individuals / Boundary Line Plantation of Horticulture Trees for Individuals | Plantation | 1720003060/IF/22012035131316 — Vraksharopan Hai schhol Se Santidham Tak | Ongoing | 427106.07 | 176450.99 | 2023-08-27
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1720003060/IF/22012035327844 — Boldar Chek Dam Nale Par T chhota | Approved | 0 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720003060/IF/22012035448249 — Khet Talab Ambaram t chhota | Approved | 226284.9 | 0 | 2025-04-25
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720003060/IF/22012035463598 — JGSA 202Dag vell Rechargh Stroctur Anil | Approved | 0 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720003060/IF/22012035463623 — JGSA 202Dag vell Rechargh Stroctur Anil | New | 0 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720003060/IF/22012035463649 — JGSA 202Dag vell Rechargh Stroctur Ramcharan | Physically Completed | 23899.46 | 21710.6 | 2025-05-18 | 2026-03-14
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1720003060/IF/22012035463671 — JGSA 2025 Dag vell Rechargh Stroctur Anil | Physically Completed | 23899.46 | 21710.95 | 2025-05-18 | 2026-03-14
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1720003060/IF/22012035463684 — JGSA 2025 Dag vell Rechargh Stroctur kundan | Physically Completed | 23899.46 | 21732 | 2025-05-18 | 2026-04-24
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1720003060/IF/22012035463692 — JGSA 2025 Dag vell Rechargh Stroctur mukul | Physically Completed | 23899.46 | 21188.95 | 2025-05-18 | 2026-03-14
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-borewellrecharge for Indiv / Construction of Sand filter for Borewell recharge for Individual | Well Recharge | 1720003060/IF/22012035463715 — JGSA 202Dag vell Rechargh Stroctur Sekhar | Physically Completed | 23899.46 | 22232.95 | 2025-05-18 | 2026-03-14
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003060/IF/22012035588994 — Ek Bagiya Maa Ke Name Shyamu Bai Sharma | Ongoing | 266657.04 | 93058 | 2025-09-05
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Boundary Plantation / Boundary Block Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1720003060/IF/9993671829 — NANDAN FALODHYAN SUMITRA RAMESH | Completed | 98000 | 159 | 2015-08-22 | 2017-07-19
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Bunding / Construction of Earthen peripheral/farm/field Bund for Individuals | Construction of Bund | 1720003060/IF/9993696173 — MED BANDHAN SUNITRABAI RAMESHCHANDRA | Deleted | 41600 | 0 | 2015-12-15
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993699970 — medmandhan jagdish shaligrama | Completed | 41600 | 38955 | 2015-12-28 | 2016-05-16
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Land Development / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993699976 — MEDBNDHAN PRVATIBAI | Completed | 41600 | 38319 | 2015-12-28 | 2016-05-16
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993699977 — medbandhan rameshvar ramchandr | Deleted | 41600 | 0 | 2015-12-28
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Horticulture / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003060/IF/9993699982 — medbandhan babita bai pavan | Completed | 41600 | 26286 | 2016-03-17 | 2016-05-22
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993699986 — medbanhdan rahul kianhyalal | Deleted | 41600 | 0 | 2015-12-28
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993699990 — medbandhan iandra bai kailash | Completed | 94400 | 24026 | 2016-03-17 | 2016-05-16
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste/Fallow Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993699992 — medbandhan santosh | Deleted | 0 | 0 | 2015-04-14
DEWAS / DEWAS | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993702928 — nadeb harinarayan | Completed | 12500 | 159 | 2016-01-19 | 2017-07-19
DEWAS / DEWAS | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993703610 — BOI GEAS bhagvan motiram | Completed | 27000 | 2067 | 2016-01-11 | 2017-07-19
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703615 — BOI GEAS RAMCHANDR MOTIRAM | Completed | 27000 | 159 | 2016-01-11 | 2017-07-19
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703616 — BOI GEASharinarayan shivjiram | Completed | 27000 | 159 | 2016-01-19 | 2017-07-19
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703618 — BOI GEAS lxminarayan nanuram | Deleted | 27000 | 0 | 2015-10-02
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703620 — BOI GEAS GHANSHYAM KANHYALAL | Deleted | 27000 | 159 | 2016-01-11
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703625 — BOI SANJAY OMPRKASH | Deleted | 27000 | 0 | 2016-01-11
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703627 — BOI GEAS stish shivjiram | Deleted | 27000 | 0 | 2015-10-02
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703630 — BOI GEAS santosh kanhyalal | Deleted | 27000 | 0 | 2015-10-02
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703632 — BOI GEASrameshvar liladhar | Deleted | 27000 | 0 | 2015-10-02
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703634 — BOI GEAS shohan gendalal | Deleted | 27000 | 0 | 2016-01-11
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Bio Drainage / Block Plantation of Biodrainage Trees in Fields for Individuals | Other Works | 1720003060/IF/9993703635 — BOI GAES SCHIN VISHNU | Deleted | 27000 | 0 | 2016-01-11
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993703637 — nadeb jagdish | Deleted | 12500 | 0 | 2017-08-27
DEWAS / DEWAS | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993703639 — nadeb kundan | Completed | 12500 | 159 | 2016-01-11 | 2017-07-19
DEWAS / DEWAS | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993703640 — nadeb bhagvan | Completed | 12500 | 12997 | 2016-01-11 | 2017-03-18
DEWAS / DEWAS | 2015-2016 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993705791 — nadebsantoshharinarayan | Completed | 12500 | 2497 | 2016-01-19 | 2017-10-12
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720003060/IF/9993705949 — harinarayan shivajiram pashu sed | Deleted | 11200000000 | 0 | 2016-04-02
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720003060/IF/9993705953 — sntosh harinarayan pashu sed | Completed | 11200000000 | 8444 | 2016-03-17 | 2016-09-02
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993706006 — nadebrajmalbapuji | Completed | 12500 | 12838 | 2017-02-04 | 2017-03-18
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | NADEP Composting / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003060/IF/9993707057 — nadeb gattulal ramratan | Completed | 12600 | 12504 | 2017-02-04 | 2017-03-18
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734506 — medbandhan harinarayan shivajiram | Completed | 88000 | 55444 | 2016-04-18 | 2016-05-23
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734513 — medbandhan shohan gendalal | Completed | 88000 | 71643 | 2016-04-18 | 2016-06-16
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734515 — medbandhan vishnu dolatram | Deleted | 0 | 0 | 2016-01-26
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734521 — medbandanhan anil ramrat | Deleted | 0 | 0 | 2016-01-26
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734523 — medbandhan pavan gopal | Deleted | 0 | 0 | 2016-01-26
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734556 — medbandhan sornambai babulal | Deleted | 0 | 0 | 2016-01-26
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734558 — medbandhan manohar babulal | Deleted | 0 | 0 | 2016-01-26
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734559 — medbandhan vishnu bapuji | Completed | 39000 | 33066 | 2016-04-18 | 2016-06-22
DEWAS / DEWAS | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Development of Waste Land / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1720003060/IF/9993734560 — medbandhan mahesh kantilal | Deleted | 0 | 0 | 2016-01-26
DEWAS / DEWAS | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/3677451 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100558305 | Approved | 23490 | 0 | 2022-04-29
DEWAS / DEWAS | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/4187431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP111433387 | Completed | 18360 | 17952 | 2022-07-29 | 2023-09-11
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/443976 — Construction of IAY House -IAY REG. NO. MP1497892 | Completed | 15030 | 15450 | 2017-03-25 | 2018-04-05
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/4933662 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100558291 | Completed | 23490 | 23490 | 2025-04-04 | 2025-08-31
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/4940995 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113484551 | Completed | 23490 | 23490 | 2025-04-04 | 2026-05-30
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/4940996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113484608 | Completed | 23490 | 23490 | 2025-04-04 | 2026-05-30
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/4948512 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117282869 | Completed | 23490 | 23490 | 2025-04-04 | 2025-08-31
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/4948513 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117282942 | Physically Completed | 23490 | 23490 | 2025-04-04 | 2026-02-18
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/537105 — Construction of IAY House -IAY REG. NO. MP2987062 | Completed | 15030 | 15450 | 2017-03-25 | 2018-04-05
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/5375785 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100558276 | Completed | 23490 | 21402 | 2025-05-24 | 2026-05-30
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/5379173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118145634 | Completed | 23490 | 23490 | 2025-08-12 | 2025-10-03
DEWAS / DEWAS | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/6066385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100558285 | Approved | 23490 | 0 | 2025-02-15
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/69529 — Construction of IAY House -IAY REG. NO. MP-20-003-060-001/17 | Completed | 14310 | 14028 | 2016-04-13 | 2017-03-01
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/69530 — Construction of IAY House -IAY REG. NO. MP-20-003-060-002/33 | Completed | 14310 | 14028 | 2016-04-13 | 2017-03-01
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/69531 — Construction of IAY House -IAY REG. NO. MP-20-003-060-002/37 | Completed | 14310 | 14028 | 2016-05-17 | 2017-03-01
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/69532 — Construction of IAY House -IAY REG. NO. MP-20-003-060-002/45 | Completed | 14310 | 14028 | 2016-04-13 | 2017-03-01
DEWAS / DEWAS | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003060/IF/IAY/69533 — Construction of IAY House -IAY REG. NO. MP-20-003-060-002/53 | Completed | 14310 | 14028 | 2016-04-13 | 2017-04-01
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1720003060/LD/22012034302295 — शांतिधाम निर्माण कार्य पर्वतीपुरा | Completed | 180000 | 179038 | 2017-03-02 | 2019-12-21
DEWAS / DEWAS | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1720003060/LD/22012034540967 — med bandan rahul | Completed | 74071.78 | 45984 | 2021-02-26 | 2022-10-05
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1720003060/LD/22012034939946 — Percolation Tank on Forest Land TC | Approved | 0 | 0 | 2024-05-24
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1720003060/LD/22012034941021 — samudaik vraksharopan parwatipura | Approved | 0 | 0 | 2024-06-15
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799392436 — Med Bandhan Kesarsingh shivjiram | Deleted | 36700 | 0 | 2013-06-02
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1720003060/LD/3799392438 — Med Bandhan Rupsingh Ambaram | Deleted | 36700 | 0 | 2013-06-02
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1720003060/LD/3799395020 — Sunil Kantilal | Completed | 36700 | 3504 | 2013-06-12 | 2014-06-25
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1720003060/LD/3799395023 — Med Bandhan Bhagwanta Badrilal | Completed | 36700 | 14892 | 2013-06-12 | 2013-12-23
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799407935 — Med Banthan Satish Shivjiram | Completed | 36700 | 15353 | 2013-10-01 | 2014-10-15
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799407942 — Med Bandhan Balmukund Chogalal | Completed | 36700 | 33262 | 2013-10-01 | 2014-10-15
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799407948 — Med Bandhan Vishnu Ambaram | Completed | 36700 | 292 | 2013-10-01 | 2014-06-25
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799407954 — Med Badhan Bhadar Ambaram | Completed | 36700 | 292 | 2013-10-01 | 2014-06-25
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799407960 — Med Badhan Ambaram Bapu | Completed | 36700 | 292 | 2013-10-01 | 2014-06-25
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799407965 — Med Badhan Bherulal Ramchandra | Completed | 36700 | 292 | 2013-10-01 | 2014-06-25
DEWAS / DEWAS | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003060/LD/3799408551 — Gramin Khel Medan Parvatipura | Completed | 191000 | 181455 | 2013-10-03 | 2016-09-02
DEWAS / DEWAS | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1720003060/RC/143 — GREVAL ROAD TIGARIYA SE JHANJHARVADI | Completed | 0 | 9282 | 2009-08-20 | 2013-02-28
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034180463 — PPCC dulichand ke ghR SE eamesh ji ke ghar tak 13- | Completed | 190000 | 184014 | 2013-09-05 | 2015-02-24
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034181183 — PPCC Anganwadi Bhavan se Mangilal ke ghar tak 13-1 | Completed | 140000 | 96522 | 2013-09-09 | 2014-02-25
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003060/RC/22012034204526 — SUDUR GRAM SADAK MAIN ROAD SE BABULAL THAVAR KE KH | Completed | 1383000 | 1460 | 2014-02-16 | 2023-08-28
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003060/RC/22012034208406 — SHANTIDHAM GREVAL ROAD TIGRIYA CHHOTA | Completed | 727000 | 213340 | 2014-02-26 | 2016-09-02
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034210842 — PPCC RAMESHCHANDRA KE GHAR SE BABULAL KE GHAR TAK | Completed | 191000 | 178062 | 2014-03-04 | 2014-06-22
DEWAS / DEWAS | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034297182 — cement kankrit nali nirman tigriya chota | Completed | 5500000000 | 54378 | 2016-03-17 | 2016-05-16
DEWAS / DEWAS | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034311414 — cc road tigriya chapari mrg se hajarilal ke ghar tak | Deleted | 0 | 0 | 2016-01-26
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034331291 — सी सी. रोड व नाली निर्माण | Completed | 267750 | 39678 | 2017-03-16 | 2017-05-20
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003060/RC/22012034339260 — sudur sadak hukum shingh khet se chapri rode | Completed | 1500000 | 1346276 | 2017-05-26 | 2021-09-07
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034366412 — nali nirman hukam mistari ke ghar se mnohar ke ghar tak gram tigriya | Completed | 9000 | 6216 | 2017-11-18 | 2019-08-01
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034366413 — nali nirman hukam mistari ke ghar se mnohar ke ghar tak gram tigriya | Deleted | 0 | 0 | 2017-10-02
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034368251 — cc road kumariya men rod se santidam | Completed | 124000 | 116368 | 2017-12-19 | 2018-09-25
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034368252 — cc road kundan ke ghar se sunil shmara ke ghar tak | Completed | 94000 | 79572 | 2017-11-28 | 2018-09-25
DEWAS / DEWAS | 2016-2017 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003060/RC/22012034373197 — sudur sadak main road se kailash ke khet tak | Deleted | 0 | 0 | 2017-01-26
DEWAS / DEWAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034395258 — santosh ke gar se murarilal ke gar tak cc road | Deleted | 0 | 0 | 2018-05-15
DEWAS / DEWAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034395265 — shree ram mandeer se kelash ke gar tak c.c.rode | Completed | 7400 | 7308 | 2018-12-24 | 2019-08-01
DEWAS / DEWAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034395267 — shreeram mandeer chok c.c.rode | Completed | 45000 | 44316 | 2018-12-24 | 2019-08-01
DEWAS / DEWAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034395269 — CC ROAD vakil sab ke gar se men rod takc | Completed | 4700 | 5220 | 2018-12-24 | 2019-08-01
DEWAS / DEWAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034395270 — CC ROAD subhash ke gar se puliya takc.c.rode | Completed | 62000 | 57804 | 2018-12-24 | 2019-08-01
DEWAS / DEWAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034395271 — CC Road ramratan ke gar se dulichand ke gar tak | Completed | 28000 | 27444 | 2019-01-03 | 2019-12-17
DEWAS / DEWAS | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034395272 — cc rOAD men rode se kelash ke gar tak | Completed | 20500 | 19008 | 2019-12-12 | 2020-06-18
DEWAS / DEWAS | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034397094 — CC ROAD SANTOSH KE GHAR SE MURARILAL KE GHAR TAK | Completed | 39000 | 39048 | 2018-12-24 | 2019-08-01
DEWAS / DEWAS | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034472631 — c.c.rode mangilal ke gar se c.c.rode tak | Completed | 4000 | 3696 | 2019-09-04 | 2019-12-17
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034608510 — nali niman ambaram ke gar se up swasth kendra | Closed | 0 | 0 | 2022-02-26
DEWAS / DEWAS | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/22012034652204 — C.C.RODE NIRMAN PANCHAYAT BHAVAN SE TANKI TAK | Completed | 51000 | 49742 | 2023-09-19 | 2024-02-15
DEWAS / DEWAS | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/35 — सी.सी.रोड प्राथ्मीक स्कूल् | Completed | 0 | 76600 | 2009-06-01 | 2009-08-30
DEWAS / DEWAS | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/439 — सी सी रोड पंचपरमेश्‍वर 1 भादर के घर से दुलीचन्‍द के घर तक | Completed | 94000 | 93596 | 2013-01-30 | 2013-02-28
DEWAS / DEWAS | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003060/RC/461 — PPCC Ghanshyam fouji ke ghar se Hanuman mandir tak | Completed | 112500 | 109168 | 2012-05-05 | 2013-12-23
DEWAS / DEWAS | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1720003060/RC/ग्रेवल रोड टि‍गरि‍या छोटा (टि‍गरि‍या — ग्रेवल रोड टि‍गरि‍या छोटा (टि‍गरि‍या छोटा) | Completed | 1585000 | 347537 | 2008-03-03 | 2012-12-31
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034341371 — शोचालय निर्माण अम्बाराम नाथू | Completed | 9800 | 9693 | 2017-05-27 | 2017-07-10
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034341391 — शोचालय निर्माण विक्रम अम्बाराम | Completed | 9800 | 9693 | 2017-05-27 | 2017-07-10
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034341394 — शोचालय निर्माण राकेश राजारम | Completed | 9800 | 9693 | 2017-05-27 | 2017-07-10
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034355590 — सोचालय निर्माण बालाराम पिता सालगराम | Completed | 9800 | 9693 | 2017-06-28 | 2017-10-12
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034355596 — सोचालय निर्माण शेखर भगवानलाल | Completed | 9800 | 2064 | 2017-06-28 | 2018-08-03
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034355598 — सोचालय निर्माण रामचरण मोतीराम | Completed | 9800 | 2064 | 2017-06-28 | 2018-08-03
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034355606 — सोचालय राहुल कन्हेंयालाल | Completed | 9800 | 9693 | 2017-06-28 | 2017-10-12
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034355607 — सोचालय निर्माण धर्मागज बाबूलाल | Closed | 9800 | 0 | 2017-06-27
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034369584 — शोचालय निर्माण चम्पालाल chhogalal | Closed | 9800 | 0 | 2017-06-27
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1720003060/RS/22012034387329 — sochalay nirman mukut babulal | Closed | 0 | 0 | 2017-10-02
DEWAS / DEWAS | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720003060/RS/22012034497985 — Samudayik Swachta Parisar Parwatipura | Completed | 44000 | 43510 | 2020-09-29 | 2021-08-10
DEWAS / DEWAS | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720003060/RS/22012034645600 — nali niman ambaram ke gar se up swasth kendra | Completed | 32000 | 31824 | 2022-04-08 | 2022-07-08
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720003060/RS/22012034645603 — samudaik swachta parisar tigriya chhota | Closed | 0 | 0 | 2022-01-24
DEWAS / DEWAS | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1720003060/RS/22012034645604 — samudaik swachta parisar tigriya chhota | Completed | 44000 | 43860 | 2022-04-01 | 2022-09-09
DEWAS / DEWAS | 2013-2014 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1720003060/SK/2352 — Bharat Nirman Rajeev Gandhi Sewa Kendra,TIGRIYA CHOTA | Completed | 1285000 | 988232 | 2014-02-25 | 2016-04-02
DEWAS / DEWAS | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012034444735 — डबरी निर्माण इस्तारिया नाले के पास | Deleted | 91400 | 1056 | 2020-02-28
DEWAS / DEWAS | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012034444745 — डबरी निर्माण ग्राम पर्वातिपुरा | Closed | 91400 | 0 | 2019-01-26
DEWAS / DEWAS | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720003060/WC/22012034475574 — roof water harvesting panchayat bhavan | Closed | 0 | 0 | 2019-07-17
DEWAS / DEWAS | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720003060/WC/22012034475576 — roof water harvesting up swasth kendra | Closed | 0 | 0 | 2019-07-17
DEWAS / DEWAS | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720003060/WC/22012034485114 — sok pit nirman madyamik schhol | Closed | 13427.22 | 0 | 2019-08-17
DEWAS / DEWAS | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012034518400 — डबरी निर्माण टिगरिया छोटा (दिनेश-कालूजी) | Completed | 101997.1 | 80280 | 2020-02-13 | 2022-02-15
DEWAS / DEWAS | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1720003060/WC/22012034617572 — gebiyan sarachna rode ke pass nale par | Closed | 0 | 0 | 2021-01-23
DEWAS / DEWAS | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1720003060/WC/22012034617576 — gebiyan sarachna murli nale par | Closed | 0 | 0 | 2021-01-23
DEWAS / DEWAS | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Wire crate (gabion) Spur for Comm / Construction of Wire crate (gabion) Spur for Community | Constr of Gabion | 1720003060/WC/22012034617578 — gebiyan sarachna rajesh ke khet ke pass nale par | Closed | 0 | 0 | 2021-01-23
DEWAS / DEWAS | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012034617647 — parkolesan tenk shohan ramesh | Completed | 332962.02 | 117614 | 2021-02-26 | 2022-04-07
DEWAS / DEWAS | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012034622687 — percolation tenk ranchod | Completed | 332962.02 | 108854 | 2021-03-13 | 2022-10-10
DEWAS / DEWAS | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012034622696 — percolation tenk ramcharan | Completed | 332962.02 | 115612 | 2021-03-13 | 2023-07-12
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720003060/WC/22012034645442 — drenej chenal dharmshala ke pass tigriya chhota | Completed | 257764.42 | 182015 | 2021-04-29 | 2022-04-26
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1720003060/WC/22012034645445 — dreneg chenal talab ke pass tigriya chhota | Completed | 245928.7 | 115800 | 2021-04-29 | 2021-12-10
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Renovation of Flood/ Diversion Channel for Comm / Renovation of Flood/ Diversion Channel for Community | Terracing | 1720003060/WC/22012034645446 — dreneg chenal talab ke pass tigriya chhota | Closed | 0 | 0 | 2021-04-01
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012034649379 — Dyke nirman shantidam ke pass nale par | Completed | 67000.38 | 40530 | 2021-05-06 | 2022-05-17
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720003060/WC/22012034772407 — Ruff wattar harvestingh prathmik vidyalay t.chhota | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720003060/WC/22012034772414 — Ruff wattar harvestingh madhyamik vidyalay t.chhota | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720003060/WC/22012034772417 — Ruff wattar harvestingh prathmik vidyalay parwatipura | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720003060/WC/22012034812331 — shree ram mandir gali me sok pit nirman parwatipura | Completed | 35028.05 | 33471 | 2021-09-28 | 2022-04-07
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720003060/WC/22012034853271 — sok pit nirman babulal ke makan vali gali me | Completed | 35157.78 | 32313 | 2021-10-26 | 2022-07-08
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720003060/WC/22012034853273 — samudaik sok pit nirman school ke pass | Closed | 0 | 0 | 2021-10-05
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720003060/WC/22012034853274 — samudaik sok pit nirman narayan ki dukan ke pass | Completed | 120009.48 | 108955 | 2021-11-02 | 2022-07-08
DEWAS / DEWAS | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720003060/WC/22012034936731 — dreneg chenal jagdish ke khet se samsan tak | Completed | 274320.83 | 151776 | 2022-05-01 | 2022-10-20
DEWAS / DEWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012034978537 — daik nirman arvind ke ket ke pass | Closed | 0 | 0 | 2022-04-29
DEWAS / DEWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012034978543 — ddaik nirman gashiram ke ket ke pass parwatipura | Closed | 0 | 0 | 2022-04-29
DEWAS / DEWAS | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Repair & Maint of Flood/Diversion Channel for Comm / Repair and Maintenance of Flood/ Diversion Channel for Community | Repair & maint of Water Harvesting Structures | 1720003060/WC/22012034997354 — drenej chenal puliya se subhash ke khet tak | Completed | 201962.4 | 172278 | 2022-10-16 | 2023-07-26
DEWAS / DEWAS | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720003060/WC/22012035013949 — Drenej Chenal Parwatipura Rapat se nale ki or | Completed | 187037.6 | 161993 | 2023-06-09 | 2023-11-12
DEWAS / DEWAS | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720003060/WC/22012035119259 — DRENEJ CHENAL GHANSHYAM KE KHET SE PAHADI KI OR | Closed | 228799.92 | 0 | 2023-08-15
DEWAS / DEWAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720003060/WC/22012035138997 — DRENEJ CHENAL GHANSHYAM KE KHET SE PAHADI KI OR | Completed | 228799.92 | 198647 | 2023-10-08 | 2024-08-16
DEWAS / DEWAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720003060/WC/22012035149039 — drenej chenal parwatipura puliya se ghasiram ke khet tak | Completed | 86830.73 | 73372 | 2023-12-27 | 2024-08-16
DEWAS / DEWAS | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720003060/WC/22012035186013 — Gopilal ke ket se pahadi ki or | Closed | 65446.58 | 0 | 2024-02-25
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720003060/WC/22012035216930 — Parkolesan Tenk Forest Lend | Completed | 793070.61 | 774029.75 | 2024-09-11 | 2025-07-05
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720003060/WC/22012035216942 — Jal Avsosan Khanti TChhota | Approved | 0 | 0 | 2024-05-08
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1720003060/WC/22012035217143 — Jal Avsosan Khanti Parwatipura | Approved | 0 | 0 | 2024-05-08
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Stone graded Bund for Community / Construction of Stone graded Bund for Community | Construction of Bund | 1720003060/WC/22012035224287 — Gebiyan nirman Hanuman Mandeer Tigriya chhota | Approved | 0 | 0 | 2024-08-16
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012035224303 — Daik Nirman Tigriya Chhota Mukul Ke Khet Ke pass | Physically Completed | 47076.95 | 39270.96 | 2025-06-19 | 2026-04-24
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012035225110 — Daik Niramn Swachta Parisar Ke Pass | Physically Completed | 45704.69 | 37093.04 | 2025-04-17 | 2026-04-24
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720003060/WC/22012035235609 — Boldar Chek Dem Dharmshala Ke Pass Nale Par Tigriya Chhota | Approved | 0 | 0 | 2024-10-02
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012035259897 — Percolation Tank Forest Lend 1 | Approved | 199327.86 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012035259906 — Percolation Tank Forest Lend 2 | Approved | 199327.86 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012035259907 — Percolation Tank Forest Lend 3 | Approved | 199327.86 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1720003060/WC/22012035259908 — Percolation Tank Forest Lend 4 | Approved | 199327.86 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012035259910 — Dayik Nirman Dam Ke Pass Nale Par t.chhota | Approved | 49563.46 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012035259914 — Dayik Nirman Dam Ke Pass Nale Par t.chhota 2 | Approved | 0 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720003060/WC/22012035259930 — Boldar Chek Dam Dharmshla Ke Pass Nale Par Tchhota | Approved | 49952.83 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720003060/WC/22012035259936 — Boldar Chek Dam Samsan Ke Pass Nale Par Tchhota | Approved | 49952.83 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1720003060/WC/22012035314943 — Dykes Nirman Pahadi ki or Nale Par TChhota | Approved | 0 | 0 | 2025-06-01
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720003060/WC/22012035318440 — Contour Trench Nirman Forest lend 1 | New | 0 | 0 | 2025-04-14
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720003060/WC/22012035318441 — Contour Trench Nirman Forest lend | Approved | 0 | 0 | 2025-04-14
DEWAS / DEWAS | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1720003060/WC/58 — TAALAB GEHRIKARAN | Completed | 0 | 34398 | 2009-02-18 | 2009-06-22
DEWAS / DEWAS | 2017-2018 | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1720003060/WH/19960810 — तालाब पाल सूदडीकरण ग्राम टिगरिया छोटा | Completed | 270000 | 224514 | 2017-05-24 | 2017-10-12
DEWAS / DEWAS | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1720003060/WH/22012034439766 — शोकता गद्दा निर्माण प्रायमरी स्कूल टिगरिया छोटा | Completed | 11040.29 | 8448 | 2020-02-27 | 2022-02-15
DEWAS / DEWAS | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1720003060/WH/22012034449610 — drenej chenal ratanlal ke gar se dharmshala tak | Closed | 0 | 0 | 2021-06-14
DEWAS / DEWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1720003060/WH/22012034930221 — Talab pal sudrikaran t.chhota | Completed | 260180.7 | 215832 | 2022-05-26 | 2022-10-20