## Work List
District / Block / Panchayat | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Start / completed date
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1720003089/AV/116 — Aanganbadi Bhavan Nirman Sewa Kendra,DEWAS | Deleted | 500000 | 0 | 2013-04-01 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1720003089/AV/22012034538448 — BOUNDRYWALL NIRMAN SCHOOL EVM PANCHAYAT PARISAR | Closed | 49800 | 0 | 2020-04-14 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1720003089/AV/22012034593241 — Daining Table | Closed | 0 | 0 | 2021-08-15 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1720003089/AV/22012034620616 — नाली निर्माण किशोर पंडित के मकान से नाले तक | Completed | 49000 | 32940 | 2022-09-11 - 2024-08-13
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1720003089/AV/870 — Aanganbadi Bhavan Nirman Sewa Kendra,DEWAS | Completed | 570000 | 179972 | 2014-03-05 - 2018-06-27
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720003089/DP/22012034433445 — NEERMAL NEER MIRZAPUR | Completed | 535000 | 458374 | 2019-12-04 - 2021-12-10
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1720003089/DP/22012034544249 — मा की बगिया शाला भवन | Completed | 13707.36 | 4632 | 2022-02-07 - 2024-02-05
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1720003089/DP/22012034572610 — निर्मल नीर राजेश मंडलोई के खेत के पास | Closed | 590411.94 | 20196 | 2023-01-10 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1720003089/DP/22012034602807 — वसुधा वंदन प्लांटेशन पंचायत प्रांगण | Completed | 55847.4 | 22100 | 2023-08-26 - 2026-05-30
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720003089/IC/22012034881710 — कच्ची नाली निर्माण चोबापिपलिया रोड से तालाब तक | Completed | 133330.21 | 67854 | 2022-11-04 - 2024-08-13
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003089/IF/22012034343243 — vraksha ropan talab kinare | Completed | 335000 | 110256 | 2017-05-26 - 2021-12-30
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003089/IF/22012034343246 — vraksha ropan salabavan | Completed | 335000 | 149802 | 2017-05-26 - 2021-12-30
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720003089/IF/22012034528620 — PASHU SHED SHUSHILA SANTOSH | Closed | 0 | 0 | 2019-10-02 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720003089/IF/22012034528621 — PASHU SHED MANISHA RAJESH | Closed | 0 | 0 | 2019-10-02 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720003089/IF/22012034528622 — PASHU SHED TARA MAHADEV | Closed | 0 | 0 | 2019-10-02 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720003089/IF/22012034528623 — PASHU SHED MANISHA VIKRAM | Closed | 0 | 0 | 2019-10-02 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1720003089/IF/22012034528625 — PASHU SHED MAYA SHRIRAM | Closed | 0 | 0 | 2019-10-02 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720003089/IF/22012034529991 — कपिल धारा किशोर रामसिंह | Closed | 0 | 0 | 2019-10-02 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720003089/IF/22012034534911 — कपिल धारा जगदीश | Completed | 234458.57 | 184630 | 2020-05-19 - 2021-03-15
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720003089/IF/22012034554401 — KHET TALAB DAMODAR BHAGIRATH | Completed | 108814.67 | 56883 | 2020-05-17 - 2022-05-04
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720003089/IF/22012034554541 — KHET TALAB MANGESH HAJARILAL | Closed | 0 | 0 | 2020-04-14 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1720003089/IF/22012034876104 — सोकपिट गड्डा केदार सुखराम | Closed | 21068.14 | 0 | 2021-08-16 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1720003089/IF/22012034876121 — सोकपिट गड्डा जालम शिव नारायण | Closed | 0 | 0 | 2021-08-16 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of NADEP Compost structure for Individual / Construction of NADEP Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1720003089/IF/22012034876129 — नाडेफ जालम शिवनारायण | Closed | 14006.51 | 0 | 2021-08-16 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003089/IF/22012034889441 — vyaktigat sokhpit 5 pawasa | Ongoing | 91916.92 | 4632 | 2021-11-30 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003089/IF/22012034889445 — vyaktigat sokhpit 5 | Ongoing | 81942.49 | 3474 | 2021-11-30 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003089/IF/22012034889464 — vyaktigat soakpit 2 | Closed | 0 | 0 | 2021-08-16 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720003089/IF/22012035323139 — खेत तालाब विनोद बाबूलाल चौधरी | New | 0 | 0 | 2025-04-01 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720003089/IF/22012035323187 — खेत तालाब विनोद बाबूलाल चौधरी | New | 0 | 0 | 2025-04-01 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720003089/IF/22012035324768 — खेत तालाब विनोद बाबूलाल चौधरी | Ongoing | 137797.86 | 41825.88 | 2025-04-16 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720003089/IF/22012035533572 — JGSA 2025 Dugwell Recharge Rajesh Choudhary | Approved | 0 | 0 | 2025-04-14 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003089/IF/22012035594953 — Ek Bagiya Ma ke Naam Sagar bai Mirzapur | Ongoing | 270531.65 | 104040.08 | 2025-09-12 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003089/IF/22012035619975 — EK BAGIYA MA KE NAAM RIKKA GOPAL CHOUDHARY | Approved | 0 | 0 | 2025-09-01 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1720003089/IF/22012035620032 — EK BAGIYA MA KE NAAM KRISHNA BAI DINESH CHOUDHARY | Approved | 0 | 0 | 2025-09-01 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720003089/IF/33 — KAPILDHARA MOHAN BAPUJI | Completed | 0 | 237555 | 2007-12-16 - 2011-08-27
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Well / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720003089/IF/34 — KOOP NIRMAN TEJU BAI AMAR SINGH | Completed | 0 | 285895 | 2009-02-26 - 2011-08-22
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1642297 — Construction of IAY House -IAY REG. NO. MP1393261 | Completed | 15660 | 14616 | 2018-05-04 - 2019-01-09
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1879873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4274662 | Completed | 15660 | 14616 | 2018-07-19 - 2019-01-09
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1879975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4308969 | Completed | 15660 | 14616 | 2018-07-23 - 2019-02-13
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1880632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4473659 | Completed | 15660 | 15684 | 2018-08-19 - 2019-04-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1880665 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4473741 | Completed | 15660 | 14616 | 2018-07-31 - 2019-01-09
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4899475 | Completed | 15660 | 14616 | 2018-07-31 - 2019-01-09
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881058 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4899726 | Completed | 15660 | 14664 | 2018-07-31 - 2019-06-02
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4913850 | Completed | 15660 | 14616 | 2018-07-19 - 2019-01-09
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5000941 | Completed | 15660 | 15532 | 2018-07-23 - 2019-05-22
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881165 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5002277 | Completed | 15660 | 14640 | 2018-07-19 - 2019-04-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881172 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5006728 | Completed | 15660 | 14640 | 2018-07-19 - 2019-04-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5049436 | Completed | 15660 | 14616 | 2018-07-19 - 2019-03-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881440 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5040948 | Completed | 15660 | 15684 | 2018-07-19 - 2019-04-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881472 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4999672 | Completed | 15660 | 15684 | 2018-07-28 - 2019-04-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1881695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5419068 | Completed | 15660 | 15684 | 2018-07-23 - 2019-04-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1901111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4308955 | Completed | 15660 | 14616 | 2018-07-19 - 2019-03-02
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/1912839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4479584 | Completed | 15660 | 14640 | 2018-07-31 - 2019-04-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/4288931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105892175 | Completed | 18360 | 14688 | 2022-07-29 - 2022-11-12
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/4291442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100872494 | Completed | 18360 | 18102 | 2022-08-04 - 2023-12-21
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/430191 — Construction of IAY House -IAY REG. NO. MP1395580 | Completed | 15030 | 15420 | 2017-02-15 - 2018-04-10
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/516465 — Construction of IAY House -IAY REG. NO. MP2474927 | Completed | 15030 | 15390 | 2017-02-15 - 2018-04-30
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/6117091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106949697 | Ongoing | 23490 | 0 | 2026-05-31 -
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/74926 — Construction of IAY House -IAY REG. NO. MP-20-003-089-002/14 | Completed | 14310 | 2064 | 2017-06-29 - 2018-05-15
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/74929 — Construction of IAY House -IAY REG. NO. MP-20-003-089-002/50 | Completed | 14310 | 2064 | 2017-06-29 - 2018-05-15
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/819032 — Construction of IAY House -IAY REG. NO. MP2135134 | Completed | 15480 | 15576 | 2017-06-29 - 2018-07-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/821069 — Construction of IAY House -IAY REG. NO. MP2324968 | Completed | 15480 | 14484 | 2017-05-17 - 2018-07-20
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/821677 — Construction of IAY House -IAY REG. NO. MP2389306 | Completed | 15480 | 17544 | 2017-05-17 - 2017-12-30
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/822007 — Construction of IAY House -IAY REG. NO. MP2427064 | Completed | 15480 | 15480 | 2017-05-17 - 2018-04-10
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/822300 — Construction of IAY House -IAY REG. NO. MP2452243 | Completed | 15480 | 14448 | 2017-05-17 - 2018-05-10
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/822613 — Construction of IAY House -IAY REG. NO. MP2508026 | Completed | 15480 | 14448 | 2017-05-17 - 2018-05-10
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/822631 — Construction of IAY House -IAY REG. NO. MP2511082 | Completed | 15480 | 15480 | 2017-05-17 - 2018-04-10
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/822919 — Construction of IAY House -IAY REG. NO. MP2559427 | Completed | 15480 | 14448 | 2017-05-17 - 2018-05-10
DEWAS / DEWAS / MIRZAPUR | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720003089/IF/IAY/828906 — Construction of IAY House -IAY REG. NO. MP3745425 | Completed | 15480 | 14310 | 2017-05-17 - 2019-01-09
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1720003089/LD/22012034313155 — SHANTIDHAM PNWASA | Completed | 180000 | 171108 | 2017-05-15 - 2019-01-19
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/22012034940938 — वृक्षारोपण शांति धाम मिर्ज़ापुर | Ongoing | 453563.17 | 31709.16 | 2024-08-18 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/3799392194 — मेड बंधान मोहन बापूजी | Completed | 36700 | 15476 | 2013-06-01 - 2013-12-10
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/3799394500 — Med Bandhan Tejubai Amarsingh | Completed | 36700 | 15476 | 2013-06-10 - 2013-12-10
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/3799404825 — Med bandhan Bhagirath Rughnaath | Completed | 36700 | 38275.92 | 2013-09-16 - 2014-11-06
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/3799404830 — med bandhan ghanshyam sewaram | Completed | 36700 | 2075.94 | 2013-09-16 - 2014-10-30
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/83 — 1720003089/LD/83 | Completed | 385000 | 150118 | 2012-05-05 - 2015-03-20
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/9926705854 — BHUMI SAMATALIKARAN DEVKARAN BHERAJI | Completed | 121400 | 44274 | 2014-06-06 - 2014-11-06
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Land Development | Reclamation of Land / Reclamation of Community Waterlogged Land | Land Development | 1720003089/LD/9926705868 — Med Bandhan Chunnilal Gangaram | Deleted | 34500 | 0 | 2014-04-01 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/9926706620 — khet samatalikaran mohan bapu | Completed | 116500 | 32970 | 2014-06-14 - 2014-11-06
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/9926706622 — khet Samatalikaran Bhaghirath rugnath | Deleted | 116500 | 0 | 2014-04-01 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1720003089/PG/22012034312136 — kel medan | Completed | 180000 | 7576 | 2017-05-26 - 2019-06-23
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/?????? ??? ?????? ?? ???????? — CC ROAD BADRILAL KE GHAR SE MUKESH KE GHAR KI AUR | Completed | 0 | 127368 | 2011-02-01 - 2024-02-05
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034164201 — सी सी रोड पंचपरमेश्‍वर 2 रामचन्‍द्रजी के मकान से ट | Completed | 112500 | 89495.7 | 2013-04-30 - 2014-03-24
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034174524 — PPCC Suresh ke makan se Shantabai ke makan tak | Completed | 49000 | 48474 | 2013-07-11 - 2014-11-11
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034181581 — PPCC Shankar ke makan se Mohanlal ke makan tak 13- | Completed | 122000 | 126106 | 2013-09-14 - 2015-03-05
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003089/RC/22012034187180 — Antrik Marg Graval Nathulal ke makan se chokidar k | Completed | 496000 | 447366 | 2013-10-04 - 2015-03-20
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034187952 — CC road Patel ke ghar se Bhagirath ke ghar tak | Completed | 43000 | 34464 | 2013-10-03 - 2014-11-11
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003089/RC/22012034202120 — SUDUR GRAM SADAK MIRJAPUR SE ANTRAKODI | Completed | 1452000 | 381354 | 2014-02-14 - 2017-01-29
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003089/RC/22012034210755 — ANTRIK MARG CHOKIDAR KE MAKAN SE BADRILAL KE MAKAN | Completed | 545700 | 429752 | 2014-03-05 - 2016-10-10
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034310539 — C.C.rod men rod se kelash nyalji ke mkan tak | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034310541 — C.C.rod hendpump se gjanand ke makan tak | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034310546 — C.C.road men road se mangila ke makan tak | Deleted | 0 | 0 | 2016-01-26 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003089/RC/22012034321312 — 14TH VITT CC ROAD ANTAR KE GHAR SE GOPAL KE GHAR TAK PART 2 | Completed | 23500 | 20220 | 2017-02-04 - 2018-04-30
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034321525 — 14TH VITT CC ROAD ANTAR KE GHAR SE GOPAL KE GHAR TAK | Completed | 41300 | 23376 | 2017-02-04 - 2018-01-01
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003089/RC/22012034329217 — SUDUR SADAK MIRJAPUR SE CHOBAPIPLYA KANKAD TAK | Completed | 1300000 | 1047032 | 2017-03-02 - 2020-05-15
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034350671 — CC ROAD BHADAR KE GHAR SE NAGJIRAM KE GHAR TAK | Completed | 18000 | 20640 | 2017-08-27 - 2018-02-20
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034350673 — CC ROAD MAIN ROAD SE AMBARAM KE GHAR TAK | Completed | 7000 | 5160 | 2017-08-27 - 2018-04-30
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034350675 — CC ROAD MAIN ROAD SE SITLA MATA MANDIR | Completed | 9000 | 4128 | 2017-08-27 - 2018-04-30
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034350677 — CC ROAD JAGDEESH KE GHAR SE HANDPUMP TAK | Completed | 8000 | 6192 | 2017-08-20 - 2018-04-30
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034350678 — CC ROAD MANU PATEL KE GHAR SE HANDPUMP TAK | Completed | 33000 | 33024 | 2017-10-12 - 2018-02-20
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034373906 — CC ROAD VISHNU KE MAKAN SE HANUMAN MANDIR TAK | Closed | 0 | 0 | 2017-10-02 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034434353 — CC ROAD MOHANLAL ATMARAM KE GHAR SE BANSHILAL KE GHAR TAK | Physically Completed | 248000 | 33408 | 2019-01-22 - 2019-03-31
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034434354 — CC ROAD MANU PATEL KE GHAR SE MUKESH KE GHAR TAK | Completed | 46000 | 33408 | 2019-01-22 - 2019-03-20
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034445928 — CC ROAD SUBHASH VEARMA KE MAKAN SE MANGU PATEL KE MAKAN TAK | Closed | 26000 | 0 | 2018-07-15 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034467167 — CC ROAD SURESH KE MAKAN SE SHREE RAM ACHARY KE MAKAN KI OR | Completed | 20000 | 18304 | 2019-06-23 - 2021-06-30
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034470242 — CC ROAD GURUCHARAN KE GHAR SE PEER MAHARAJ KE DARGAH KI AUR | Physically Completed | 58000 | 57024 | 2019-08-13 - 2019-10-15
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034470243 — CC ROAD KMAL KE MAKAN SE MANGEH KE MAKAN TAK | Physically Completed | 22000 | 24288 | 2019-08-05 - 2019-10-15
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003089/RC/22012034529893 — सुदूर सड़क पनवासा से मनोज मीणा के घर तक | Completed | 1267920.82 | 1267092 | 2020-07-18 - 2022-09-29
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034550960 — CC Road kalash patel ke ghar se Bor tak | Completed | 15600 | 21660 | 2021-01-06 - 2021-07-08
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034550964 — CC Road Ashok meena ke Bade se Rameshwar ke makan | Completed | 35700 | 22800 | 2021-01-06 - 2021-07-08
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034589302 — Cc Road बद्रीलाल के घर से मुकेश के घर की ओर | Deleted | 0 | 0 | 2021-08-16 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/22012034590074 — CC ROAD BADRILAL KE GHAR SE MUKESH KE GHAR KI AUR | Completed | 33000 | 30108 | 2021-11-02 - 2022-02-27
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720003089/RC/278 — ग्रेवल मार्ग गाव से शमशान | Completed | 423000 | 274692 | 2011-11-18 - 2013-03-06
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1720003089/RC/282 — सी सी रोड पंचपरमेश्‍वर बनवासा | Completed | 77000 | 37444 | 2012-03-16 - 2013-03-06
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Bitumen Top / Construction of Bitumen Top Roads for Community | Construction of Road and Culvert | 1720003089/RC/ग्रेवल रोड पनवासा से अमोदि‍या — ग्रेवल रोड पनवासा से अमोदि‍या | Completed | 3002000 | 3641009 | 2008-02-29 - 2014-01-24
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal Second coat / Construction of WBM Roads for Community | Construction of Road and Culvert | 1720003089/RC/ग्रेवल रोड र्मिजापुर से अखेपुर मार्ग — ग्रेवल रोड र्मिजापुर से अखेपुर मार्ग ( मिर्जापुर ) | Completed | 743000 | 984848.13 | 2008-01-14 - 2012-04-25
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1720003089/RS/22012034581030 — नाडेफ हनुमान मंदिर के पास | Closed | 0 | 0 | 2021-08-16 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1720003089/RS/22012034595784 — समुदायिक सोकपिट गड्डा पंवासा सारोला रोड की ओर | Completed | 14467.3 | 8425.01 | 2021-11-30 - 2025-05-07
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1720003089/RS/22012034595788 — सामुदायिक सोकपिट गड्डा कुंडी के पास | Completed | 14467.3 | 7264.18 | 2021-12-09 - 2025-05-07
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of NADEP Compost structure for Community / Construction of NADEP Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1720003089/RS/22012034595791 — सामुदायिक नाडेफ शमशान के पास | Closed | 0 | 0 | 2021-08-16 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | Upgradation/extension of panchayat Bhawan / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Repair & Maint of Community infrastructure | 1720003089/SK/666 — Bharat Nirman Rajeev Gandhi Sewa Kendra,MIRZAPUR | Completed | 435000 | 104640.8 | 2013-09-16 - 2017-05-15
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720003089/WC/22012034296546 — GABIYAN SANRACHANA BONDARJI KI BEED KE PAAS | Completed | 99000 | 76193 | 2016-06-18 - 2020-09-22
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1720003089/WC/22012034296548 — GABIYAN BHAGIRATH MANDALOI | Completed | 99000 | 48228 | 2016-06-18 - 2021-03-06
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble contour Bund for Community / Construction of Pebble contour Bund for Community | Construction of Bund | 1720003089/WC/22012034890054 — Box trench nale me | Completed | 62411.25 | 29808 | 2022-02-21 - 2024-02-15
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Continuous Contour Trench for Comm / Construction of Continuous Contour Trench for Community | Construction of Trench | 1720003089/WC/22012034890060 — Box trench nale me 2 | Completed | 66553.18 | 37968 | 2022-03-02 - 2024-09-06
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720003089/WC/22012035032775 — बोक्स टेंच श्मशान वाले नाले में | Closed | 0 | 0 | 2022-08-15 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1720003089/WC/22012035032778 — बोक्स टेंच मेंन रोड पुलिया वाले नाले में | Closed | 0 | 0 | 2022-08-15 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720003089/WC/22012035035106 — ड्रेनेज लाइन बशन्तिलाल के खेत से कैलाश के खेत तक | Completed | 136842.9 | 103753 | 2023-02-12 - 2024-09-06
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720003089/WC/22012035245747 — Construction of water conservation Pond | Ongoing | 407912.45 | 123221.02 | 2025-03-04 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1720003089/WC/22012035314780 — JGSA 2025 BORWEL RECHARHGE PANCHAYAT PARISAR | Approved | 20493.25 | 0 | 2025-04-14 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1720003089/WC/22012035314781 — BORWEL RECHARGE PANI KI TANKI KE PAAS | Approved | 0 | 0 | 2025-04-14 -
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1720003089/WH/19961471 — talab jirnodvar | Completed | 16000 | 9288 | 2017-05-26 - 2018-05-15
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1720003089/WH/19963778 — TALAB JIRNODHAR PANWASA MIRJAPUR | Completed | 5500 | 4128 | 2017-06-15 - 2018-05-15
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1720003089/WH/22012034445859 — Percolation tank mata ji tekri par | Completed | 137907.2 | 147060 | 2021-02-08 - 2021-09-23
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1720003089/WH/22012034446626 — Percolation tank talab | Completed | 1197099.06 | 842766 | 2021-04-06 - 2024-01-21
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1720003089/WH/22012034447506 — Percolation tank talab west | Closed | 1046323.83 | 0 | 2021-04-01 -
DEWAS / DEWAS / MIRZAPUR | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1720003089/WH/22012034930556 — तालाब नवनिकरण पनवासा | Physically Completed | 790130.4 | 467076 | 2023-05-31 - 2026-04-24
DEWAS / DEWAS / MIRZAPUR | D--RURAL INFRASTUCTURE / Renovation of traditional water bodies | Strengthening of Embankment / Construction of Embankment for community | Renovation of traditional water bodies | 1720003089/WH/TALAB JIRNODHAR MIRJAPUR — TALAB JIRNODHAR MIRJAPUR | Completed | 0 | 203763 | 2009-02-16 - 2014-03-24