## Work List
Exported on: 2026-10-14 13:53:45
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: MIRZAPUR
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / DEWAS | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Constr of Sand filter - openwell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Dug Well for Community | Well Recharge | 1720003089/DP/22012034572610 — निर्मल नीर राजेश मंडलोई के खेत के पास | Ongoing | 590411.94 | 0 | 2023-01-10
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003089/IF/22012034889441 — vyaktigat sokhpit 5 pawasa | Ongoing | 91916.92 | 0 | 2021-11-30
DEWAS / DEWAS | 2021-2022 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Construction of Soak Pit for Individual / Construction of Soak Pit for Individual | Solid and Liquid Waste Management | 1720003089/IF/22012034889445 — vyaktigat sokhpit 5 | Ongoing | 81942.49 | 0 | 2021-11-30
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720003089/IF/22012035323139 — खेत तालाब विनोद बाबूलाल चौधरी | New | 0 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720003089/IF/22012035323187 — खेत तालाब विनोद बाबूलाल चौधरी | New | 0 | 0 | 2025-04-01
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1720003089/IF/22012035324768 — खेत तालाब विनोद बाबूलाल चौधरी | Physically Completed | 137797.86 | 0 | 2025-04-16 | 2026-08-07
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1720003089/IF/22012035533572 — JGSA 2025 Dugwell Recharge Rajesh Choudhary | Approved | 0 | 0 | 2025-04-14
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720003089/IF/22012035594953 — Ek Bagiya Ma ke Naam Sagar bai Mirzapur | Ongoing | 270531.65 | 1800 | 2025-09-12
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720003089/IF/22012035619975 — EK BAGIYA MA KE NAAM RIKKA GOPAL CHOUDHARY | Approved | 0 | 0 | 2025-09-01
DEWAS / DEWAS | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720003089/IF/22012035620032 — EK BAGIYA MA KE NAAM KRISHNA BAI DINESH CHOUDHARY | Approved | 0 | 0 | 2025-09-01
DEWAS / DEWAS | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720003089/IF/IAY/6117091 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106949697 | Physically Completed | 27000 | 4200 | 2026-05-31 | 2026-10-08
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Levelling/shaping of Wasteland Land for Community / Levelling/shaping of Wasteland Land for Community | Land Development | 1720003089/LD/22012034940938 — वृक्षारोपण शांति धाम मिर्ज़ापुर | Ongoing | 453563.17 | 0 | 2024-08-18
DEWAS / DEWAS | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1720003089/WC/22012035245747 — Construction of water conservation Pond | Physically Completed | 407912.45 | 0 | 2025-03-04 | 2026-08-07
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1720003089/WC/22012035314780 — JGSA 2025 BORWEL RECHARHGE PANCHAYAT PARISAR | Approved | 20493.25 | 0 | 2025-04-14
DEWAS / DEWAS | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand-Filled Groundwater Recharge in Borewell for Community | Well Recharge | 1720003089/WC/22012035314781 — BORWEL RECHARGE PANI KI TANKI KE PAAS | Approved | 0 | 0 | 2025-04-14