## Work List
Exported on: 2026-09-13 11:06:27
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BAMNIBUJURG
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / KANNOD | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720004052/IF/22012034474833 — खेत तालाब योगेश पिता कान्हेयालाल | Ongoing | 239000 | 0 | 2019-06-15
DEWAS / KANNOD | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004052/IF/22012034664906 — KAPILDHARA GAJRAJ PITA CHUNNILAL | Ongoing | 246126.86 | 0 | 2021-03-07
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004052/IF/22012035288241 — KAPIL DHARA NIRMAN ANKUWRBAI RAHUL BAMNIBUJURG | Ongoing | 298432.46 | 0 | 2025-04-13
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004052/IF/22012035288255 — KAPIL DHARA NIRMAN GAYATRI AMARSINGH BAMNIBUJURG | Ongoing | 298277.01 | 0 | 2025-05-30
DEWAS / KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720004052/IF/22012035288263 — KHET TALAB NIRMAN MAMTA RAMADHAR BAMNIBUJURG | Approved | 383892.97 | 0 | 2024-11-15
DEWAS / KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720004052/IF/22012035288271 — KHAT TALAB NIRMAN GOVIND NARMDAPRASAD BAMNIBUJURG | Approved | 383892.97 | 0 | 2024-11-15
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720004052/IF/22012035310102 — KAPIL DHARA NIRMAN TOHID ANWAR KHAN GHUDIYA BAMNIBUJURG | Ongoing | 332901.55 | 0 | 2025-05-18
DEWAS / KANNOD | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720004052/IF/22012035310108 — KHET TALAB NIRMAN SANTOSH DURGAPRASAD BAMNIBUJURG | Approved | 417178.35 | 0 | 2025-01-26
DEWAS / KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1720004052/IF/22012035397739 — DUGWELL RECHARGE PIT Sadhna pati rajesh Bamnibujurg | Approved | 25899.46 | 0 | 2025-04-01
DEWAS / KANNOD | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720004052/IF/22012035449146 — DUGWELL RECHARGE PIT mulchand ramprasad bamnibujurg | Approved | 25899.46 | 0 | 2025-04-01
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004052/IF/22012035591366 — EK BAGIYA MAA KE NAAM BANO BEE RAMJAN 300 GHUDIYA | Ongoing | 283221.89 | 8400 | 2025-08-27
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004052/IF/22012035591402 — EK BAGIYA MAA KE NAAM NANNI BEE HANIF 278 GHUDIYA | Ongoing | 283221.89 | 8400 | 2025-09-07
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004052/IF/22012035591993 — EK BAGIYA MAA KE NAAM AYSHA HABEEB 56 GHUDIYA | Ongoing | 266577.25 | 8400 | 2025-09-07
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720004052/IF/22012035592250 — EK BAGIYA MAA KE NAAM SARIFAN BEE PIR 86 A GHUDIYA | Ongoing | 266577.25 | 8400 | 2025-11-01
DEWAS / KANNOD | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/4036707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105902047 | Approved | 27000 | 0 | 2022-05-10
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/5352301 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113993094 | Ongoing | 27000 | 0 | 2025-04-21
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/5565670 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105243599 | Ongoing | 27000 | 0 | 2025-05-12
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/5659926 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105246499 | Approved | 27000 | 0 | 2025-05-19
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6111951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105030432 | Completed | 23490 | 0 | 2026-04-22 | 2026-07-29
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6112176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120670706 | Completed | 23490 | 0 | 2026-04-16 | 2026-07-29
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6112207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103429087 | Approved | 27000 | 0 | 2026-02-24
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6112370 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103496691 | Ongoing | 27000 | 7800 | 2026-05-08
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6112538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103132465 | Ongoing | 27000 | 0 | 2026-05-22
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6112737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124230119 | Ongoing | 27000 | 13554 | 2026-04-16
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6112845 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103132679 | Ongoing | 27000 | 0 | 2026-09-02
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6113189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105243309 | Completed | 23490 | 0 | 2026-04-22 | 2026-07-29
DEWAS / KANNOD | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6113469 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105246547 | Approved | 27000 | 0 | 2026-02-24
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6114113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126638424 | Ongoing | 27000 | 0 | 2026-04-16
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6114209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120666526 | Completed | 23490 | 0 | 2026-04-16 | 2026-07-29
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6114555 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120590547 | Completed | 23490 | 0 | 2026-04-16 | 2026-07-29
DEWAS / KANNOD | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720004052/IF/IAY/6114944 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120664478 | Ongoing | 27000 | 8400 | 2026-04-16
DEWAS / KANNOD | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1720004052/WC/22012035235403 — COMMUNITY DUGOUT POND SURVEY NO 95 BAMNIBUJURG | Approved | 0 | 0 | 2024-08-01
DEWAS / KANNOD | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1720004052/WC/VB/22012035329904 — ROOF WATER HARVESTING PANCHAYAT BHAVAN | Approved | 0 | 0 | 2026-07-20