## Work List
Exported on: 2026-10-02 00:03:26
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: BANDI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / KHATEGAON | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1720006012/DP/22012034575655 — निर्मलनीर कूप निर्माण ग्राम काकड़कुई | Ongoing | 537251.35 | 117127 | 2023-06-16
DEWAS / KHATEGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720006012/DP/22012034583709 — वृक्षारोपण कार्य शा.मा.वि. परिसर ग्राम काकडकुई | Ongoing | 427106.07 | 13800 | 2023-09-26
DEWAS / KHATEGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1720006012/IF/22012034906789 — कपिलधारा निर्माण कार्य-लक्ष्मीबाई पति दीपचन्द जाट | Ongoing | 252665.32 | 0 | 2021-12-04
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006012/IF/22012035387852 — खेत तालाब निर्माण बलराम पिता प्रह्लाद ग्राम बंडी | Approved | 0 | 0 | 2025-04-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006012/IF/22012035388423 — खेत तालाब निर्माण रितु पति दीपक ग्राम काकड़कुई | New | 0 | 0 | 2025-04-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006012/IF/22012035411606 — खेत तालाब निर्माण आनन्द पिता बद्री ग्राम काकड़ कुई | New | 0 | 0 | 2025-04-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006012/IF/22012035413020 — खेत तालाब निर्माण गेंदालाल पिता सीताराम ग्राम बंडी | Approved | 0 | 0 | 2025-04-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006012/IF/22012035469584 — खेत तालाब निर्माण रितु पति दीपक ग्राम कांकड़कुई | Ongoing | 448514.1 | 0 | 2025-05-18
DEWAS / KHATEGAON | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1720006012/IF/22012035530325 — डगवेल रिचार्ज पीट देव बाई पति भागीरथ ग्राम करोंदबुजुर्ग | New | 0 | 0 | 2025-04-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006012/IF/22012035541786 — खेत तालाब निर्माण आनन्द पिता बद्री ग्राम काकडकुई | Approved | 450885.64 | 0 | 2025-04-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006012/IF/22012035554566 — खेत तालाब निर्माण आनन्द पिता बद्री ग्राम काकडकुई | Approved | 450885.64 | 0 | 2025-04-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006012/IF/22012035588734 — Ek Bagiya Maa ke Naam Kripa bai Lodhwal MP-20-006-012-003/34-C 243/1 | Ongoing | 263510.03 | 0 | 2025-09-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006012/IF/22012035588761 — Ek Bagiya Maa ke Naam Sushila kumare MP-20-006-012-001/407-D 75/1/1 | Approved | 0 | 0 | 2025-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006012/IF/22012035596989 — Ek Bagiya Maa ke Naam Radha bai MP-20-006-012-001/408-A 135/2 | Approved | 0 | 0 | 2025-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006012/IF/22012035597018 — Ek Bagiya Maa ke Naam Rameti Bai MP-20-006-012-004/130-A 204 | Approved | 0 | 0 | 2025-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006012/IF/22012035622391 — Ek Bagiya Maa ke Naam SHARDA LODVAL MP-20-006-012-001/409-B 32/6 | Approved | 0 | 0 | 2025-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006012/IF/22012035622400 — Ek Bagiya Maa ke Naam ANUSUIYA BAI MP-20-006-012-001/409-A 6/1 | Approved | 0 | 0 | 2025-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006012/IF/22012035622407 — Ek Bagiya Maa ke Naam BASU KAKODIYA MP-20-006-012-001/410-A 85 | Ongoing | 268739.2 | 3600 | 2026-01-14
DEWAS / KHATEGAON | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/3227080 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2112656 | Approved | 27000 | 0 | 2021-06-29
DEWAS / KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/40818 — Construction of IAY House -IAY REG. NO. MP-20-006-012-001/24 | Approved | 27000 | 0 | 2015-11-24
DEWAS / KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/40822 — Construction of IAY House -IAY REG. NO. MP-20-006-012-004/35 | Approved | 27000 | 0 | 2015-11-24
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/4738388 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105248646 | Physically Completed | 23490 | 0 | 2024-11-29 | 2026-08-06
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/4738681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191055 | Physically Completed | 23490 | 0 | 2025-03-02 | 2026-08-04
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/4738682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191230 | Ongoing | 27000 | 0 | 2025-01-16
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/4738683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106191600 | Physically Completed | 23490 | 0 | 2025-01-13 | 2026-08-06
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/4738689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192177 | Ongoing | 27000 | 300 | 2025-01-25
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/4738695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106192602 | Physically Completed | 23490 | 0 | 2025-01-13 | 2026-08-06
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/4739374 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105529467 | Ongoing | 27000 | 0 | 2024-11-29
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/5877257 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106190135 | Approved | 27000 | 0 | 2025-03-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/5877288 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106246539 | Approved | 27000 | 0 | 2025-05-19
DEWAS / KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006012/IF/IAY/75139 — Construction of IAY House -IAY REG. NO. MP-20-006-012-001/033 | Approved | 27000 | 0 | 2016-01-05
DEWAS / KHATEGAON | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1720006012/RC/22012034835910 — सुदूर सडक निर्माण संतोष पटेल के खेत से नाले तक (सातागांव मार्ग) ग्राम बंडी | Approved | 0 | 0 | 2024-10-02
DEWAS / KHATEGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720006012/RS/22012034691309 — नाली निर्माण सरकारी कुआ से गुठान तक लम्बाई 125 मी. ग्राम करोंदखुर्द | Ongoing | 36600 | 0 | 2023-06-16
DEWAS / KHATEGAON | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720/DP/22012034548809 — Bamboo plantation Kankadkui | Ongoing | 2896000 | 0 | 2022-05-11