## Work List
Exported on: 2026-10-12 03:01:03
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: SAWASADA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / KHATEGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1720006056/DP/22012034603981 — वसुधा वंदन (अमृत वाटिका) पंचायत भवन परिसर में 75 पोधे ग्राम सवासडा | Ongoing | 55847.4 | 0 | 2023-08-31
DEWAS / KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1720006056/DP/22012034605137 — वृक्षारोपण कार्य राहुल गुर्जर के खेत से जागेश्वर के खेत तक ग्राम सवासडा | Ongoing | 309689.07 | 0 | 2024-08-22
DEWAS / KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1720006056/DP/22012034605142 — वृक्षारोपण कार्य व्रजधाम कॉलोनी से हल्दिया तालाब तक ग्राम सवासडा | Ongoing | 309689.07 | 0 | 2024-08-24
DEWAS / KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1720006056/DP/22012034626603 — वृक्षारोपण कार्य हल्दिया मार्ग के दोनो साइड ग्राम सवासड़ा | Approved | 0 | 0 | 2024-07-21
DEWAS / KHATEGAON | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Road Line Plantation of Forestry Trees for Comm / Avenue Plantation for Community | Plantation | 1720006056/DP/22012034626605 — वृक्षारोपण कार्य तुलसीराम गुर्जर के खेत के पास से जागेश्वर के खेत की तरफ दोनो ग्राम सवासाड़ा | Approved | 0 | 0 | 2024-07-21
DEWAS / KHATEGAON | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006056/IF/22012034350859 — व़क्षारोपण कार्य (DPR) सवासडा से क़ष्‍णनगर रास्‍ता ग्राम सवासडा | Ongoing | 335000 | 0 | 2017-06-28
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006056/IF/22012035592360 — Ek Bagiya Maa Ke Naam SARASVATI BAI KOGE MP-20-006-056-001/247 48/1 | Ongoing | 263511.37 | 0 | 2025-12-29
DEWAS / KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/40952 — Construction of IAY House -IAY REG. NO. MP-20-006-056-001/65 | Approved | 27000 | 0 | 2015-11-24
DEWAS / KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/40953 — Construction of IAY House -IAY REG. NO. MP-20-006-056-001/69 | Approved | 27000 | 0 | 2015-11-24
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4734654 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102217700 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4735093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102353787 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4735925 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103942130 | Ongoing | 27000 | 1044 | 2024-12-05
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4736210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104921304 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4737522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101134758 | Completed | 27000 | 0 | 2024-12-05 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4754545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118025900 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4755720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117840210 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4759229 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118337808 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4759233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118338626 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4759409 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118639943 | Ongoing | 27000 | 0 | 2025-02-17
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4760479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120267864 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4760499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120273884 | Completed | 23490 | 0 | 2025-02-17 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4760501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120274196 | Ongoing | 27000 | 0 | 2025-02-17
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4775470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122741119 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4790508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141271101 | Completed | 23490 | 0 | 2024-12-05 | 2026-09-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4790511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141271798 | Completed | 27000 | 0 | 2024-12-20 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4790514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141273260 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4790516 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141274515 | Approved | 27000 | 0 | 2024-09-16
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4790521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141276483 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4800951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149936124 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4801376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150591715 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4861462 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103127777 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4861841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113846126 | Physically Completed | 27000 | 0 | 2025-02-17 | 2026-10-01
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4861931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102227728 | Completed | 23490 | 0 | 2025-01-05 | 2026-09-09
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4862351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115427585 | Ongoing | 27000 | 0 | 2026-09-01
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4863891 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122014633 | Ongoing | 27000 | 261 | 2025-02-17
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4863892 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122015339 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4864321 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120273654 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/4889445 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118640036 | Completed | 27000 | 0 | 2025-02-17 | 2026-10-07
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5152021 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102449451 | Physically Completed | 27000 | 1044 | 2025-09-15 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5162883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120275209 | Ongoing | 27000 | 783 | 2025-11-04
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5165446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149933929 | Ongoing | 27000 | 2871 | 2026-09-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5165912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118640008 | Ongoing | 27000 | 0 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5166303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115414099 | Ongoing | 27000 | 0 | 2025-11-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5167231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141273992 | Ongoing | 27000 | 0 | 2025-08-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5167844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839052 | Completed | 27000 | 0 | 2025-07-29 | 2026-09-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5176833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103942020 | Physically Completed | 27000 | 0 | 2025-07-29 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5177934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126149712 | Ongoing | 27000 | 0 | 2025-11-04
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5181113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141269480 | Completed | 27000 | 0 | 2025-08-23 | 2026-09-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5186518 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122741474 | Physically Completed | 27000 | 2871 | 2025-10-15 | 2026-09-27
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5192622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120274454 | Ongoing | 27000 | 0 | 2026-09-23
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5192627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141272774 | Ongoing | 27000 | 10179 | 2026-02-25
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5193253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141276299 | Ongoing | 27000 | 0 | 2025-08-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5193832 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141272181 | Physically Completed | 27000 | 0 | 2025-08-13 | 2026-09-27
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5195630 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118639728 | Approved | 27000 | 0 | 2025-02-21
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5197466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141270958 | Ongoing | 27000 | 0 | 2025-08-23
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5198676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141265158 | Completed | 23490 | 0 | 2025-08-23 | 2026-09-09
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5202389 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117838850 | Ongoing | 27000 | 0 | 2026-05-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5208170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105588585 | Physically Completed | 27000 | 0 | 2025-09-15 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5210556 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120271335 | Physically Completed | 27000 | 1044 | 2025-11-06 | 2026-10-01
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5211830 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150552297 | Approved | 27000 | 0 | 2025-02-27
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5212373 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141276638 | Ongoing | 27000 | 6288 | 2026-03-07
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5217112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122001388 | Completed | 27000 | 0 | 2025-08-13 | 2026-09-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5221061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141270845 | Ongoing | 27000 | 0 | 2025-10-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5221267 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103949603 | Physically Completed | 27000 | 1044 | 2025-09-15 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5233055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103948906 | Ongoing | 27000 | 0 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5234589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141264695 | Ongoing | 27000 | 7359 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5235787 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151111492 | Completed | 23490 | 0 | 2025-08-23 | 2026-09-09
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5237123 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102219167 | Physically Completed | 27000 | 0 | 2025-07-29 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5244996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839286 | Ongoing | 27000 | 2349 | 2025-07-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5257888 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115423798 | Ongoing | 27000 | 783 | 2025-07-30
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5278537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102627762 | Ongoing | 27000 | 0 | 2026-06-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5287444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141265119 | Ongoing | 27000 | 2871 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5306677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100671632 | Ongoing | 27000 | 0 | 2025-09-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5391382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106195682 | Completed | 23490 | 0 | 2025-09-15 | 2026-09-09
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5392796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117838977 | Completed | 27000 | 0 | 2025-11-05 | 2026-09-30
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5392797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839429 | Ongoing | 27000 | 0 | 2026-07-27
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5402908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102433469 | Ongoing | 27000 | 783 | 2025-09-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5404464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120268141 | Physically Completed | 27000 | 3705 | 2025-08-13 | 2026-10-01
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5408657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120273384 | Ongoing | 27000 | 0 | 2026-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5441538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141275449 | Physically Completed | 27000 | 2871 | 2026-02-12 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5441539 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141276777 | Ongoing | 27000 | 1044 | 2025-08-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5441703 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115414022 | Physically Completed | 27000 | 0 | 2025-11-06 | 2026-09-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5442545 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839927 | Physically Completed | 27000 | 2871 | 2026-02-12 | 2026-09-27
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5442784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103941047 | Ongoing | 27000 | 0 | 2025-09-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5443896 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120265587 | Approved | 27000 | 0 | 2025-04-07
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5444056 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122155057 | Physically Completed | 27000 | 0 | 2025-11-06 | 2026-09-27
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5444515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120271621 | Ongoing | 27000 | 3393 | 2025-11-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5445319 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102348894 | Ongoing | 27000 | 0 | 2025-12-24
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5445690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106194601 | Ongoing | 27000 | 1305 | 2025-07-29
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5446107 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120274716 | Ongoing | 27000 | 0 | 2026-09-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5446704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115413840 | Physically Completed | 27000 | 2871 | 2026-02-12 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5447747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122154256 | Physically Completed | 27000 | 0 | 2025-11-04 | 2026-09-27
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5447881 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115413209 | Ongoing | 27000 | 10701 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5449783 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103465123 | Ongoing | 27000 | 5742 | 2025-07-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5450720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120275459 | Ongoing | 27000 | 3393 | 2025-10-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5604270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151124783 | Physically Completed | 27000 | 0 | 2025-08-23 | 2026-09-06
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5604876 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102213647 | Physically Completed | 27000 | 0 | 2025-07-30 | 2026-09-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5632821 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115413603 | Completed | 27000 | 0 | 2026-02-12 | 2026-09-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5632822 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115414059 | Physically Completed | 27000 | 2871 | 2026-02-12 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5632826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117839539 | Ongoing | 27000 | 783 | 2025-11-06
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5632827 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118337319 | Physically Completed | 27000 | 0 | 2025-12-05 | 2026-09-13
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5632931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118340452 | Ongoing | 27000 | 8613 | 2026-03-24
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5632980 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118640197 | Ongoing | 27000 | 5871 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5633055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102125164 | Ongoing | 27000 | 0 | 2025-07-30
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5633061 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141272449 | Ongoing | 27000 | 2871 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5633168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151276584 | Ongoing | 27000 | 1305 | 2025-11-06
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5633508 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151287003 | Approved | 27000 | 0 | 2025-05-19
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5633608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102318551 | Physically Completed | 27000 | 0 | 2025-11-04 | 2026-09-27
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5633722 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115413977 | Ongoing | 27000 | 0 | 2025-10-15
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686160 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102325436 | Ongoing | 27000 | 0 | 2026-06-04
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141264730 | Ongoing | 27000 | 8613 | 2026-02-12
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686168 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141267048 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686169 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141267423 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141273719 | Ongoing | 27000 | 0 | 2025-08-23
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103128234 | Ongoing | 27000 | 0 | 2025-07-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686244 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141265616 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686247 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141269246 | Ongoing | 27000 | 0 | 2026-09-08
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120273087 | Ongoing | 27000 | 0 | 2025-12-05
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686269 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102440274 | Ongoing | 27000 | 0 | 2025-07-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106195110 | Physically Completed | 27000 | 0 | 2025-07-29 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686295 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120264971 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125911121 | Ongoing | 27000 | 2871 | 2025-11-04
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102435814 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686337 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120267580 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118640121 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686342 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118640143 | Physically Completed | 27000 | 0 | 2025-07-30 | 2026-09-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115423848 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686362 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115413168 | Ongoing | 27000 | 0 | 2026-04-23
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686363 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115413251 | Ongoing | 27000 | 6525 | 2026-02-12
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5686364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115413754 | Ongoing | 27000 | 11613 | 2026-06-04
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5721657 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102438041 | Approved | 27000 | 0 | 2025-05-26
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5726197 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141265806 | Ongoing | 27000 | 783 | 2025-11-06
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5729652 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141268089 | Ongoing | 27000 | 0 | 2026-09-08
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5730734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117840129 | Physically Completed | 27000 | 0 | 2025-11-05 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5852748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118045050 | Physically Completed | 27000 | 3915 | 2025-12-05 | 2026-10-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5853000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141265089 | Physically Completed | 27000 | 2871 | 2025-12-27 | 2026-10-01
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5853001 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141275996 | Approved | 27000 | 0 | 2025-02-27
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/5873756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141273838 | Approved | 27000 | 0 | 2025-05-19
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/6254661 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117838800 | Approved | 27000 | 0 | 2026-02-28
DEWAS / KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/75160 — Construction of IAY House -IAY REG. NO. MP-20-006-056-001/62 | Approved | 27000 | 0 | 2016-01-05
DEWAS / KHATEGAON | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1720006056/IF/IAY/75161 — Construction of IAY House -IAY REG. NO. MP-20-006-056-001/70 | Approved | 27000 | 0 | 2016-01-05
DEWAS / KHATEGAON | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1720006056/RC/22012034629038 — सी.सी.रोड निर्माण राजेश पंवार के घर से हाई स्कूल की ओर लम्बाई 65 मी. ग्राम सवासडा | Ongoing | 35000 | 0 | 2023-05-13
DEWAS / KHATEGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1720006056/WC/22012034955007 — ड्रेनेज चैनल निर्माण ब्रजधाम से कमल सिंह के खेत तक हल्दिया मार्ग के दोनों ओर ग्राम सवासडा | Ongoing | 259335 | 0 | 2022-12-26