## Work List
Exported on: 2026-10-02 00:03:27
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: DUDWAS
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DEWAS / KHATEGAON | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1720006063/DP/22012034604281 — वसुधा वंदन (अमृत वाटिका) बेहड़ी आंगनबाडी भवन के पास 75 पोधे ग्राम रंथा | Ongoing | 55847.4 | 0 | 2023-10-05
DEWAS / KHATEGAON | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006063/IF/22012034599352 — वृक्षारोपण कार्य उद्यानिकी सुरेश पिता रामदीन | Ongoing | 142431.49 | 0 | 2020-09-25
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1720006063/IF/22012035433564 — खेत तालाब निर्माण मुकेश पिता रामभरोस ग्राम रंथा | Ongoing | 450885.64 | 0 | 2025-05-02
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006063/IF/22012035588921 — Ek Bagiya Maa Ke Naam Chhama MP-20-006-063-001/120 156 | Approved | 270874.55 | 0 | 2025-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006063/IF/22012035588962 — Ek Bagiya Maa Ke Naam Sushla Bai MP-20-006-063-001/144 158 | Approved | 0 | 0 | 2025-08-01
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006063/IF/22012035588981 — Ek Bagiya Maa Ke Naam Kamal Bai MP-20-006-063-001/22 22/1 | Ongoing | 263510.03 | 7500 | 2025-09-05
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006063/IF/22012035589029 — Ek Bagiya Maa Ke Naam Sunita Prjapat MP-20-006-063-001/58 105 | Ongoing | 266577.25 | 5400 | 2025-12-07
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1720006063/IF/22012035589090 — Ek Bagiya Maa Ke Naam Imarti Bai MP-20-006-063-001/43 135/1 | Ongoing | 277227.39 | 6300 | 2025-09-01
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4546584 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106965818 | Completed | 23490 | 0 | 2025-02-03 | 2026-08-13
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4548889 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106404192 | Completed | 23490 | 0 | 2024-11-16 | 2026-08-13
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4554309 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114737187 | Completed | 23490 | 0 | 2025-01-03 | 2026-08-13
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4605559 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124764537 | Completed | 23490 | 0 | 2024-11-16 | 2026-08-13
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4611857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125473278 | Completed | 23490 | 0 | 2025-01-22 | 2026-08-13
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4766334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122809987 | Physically Completed | 23490 | 0 | 2025-01-03 | 2026-08-09
DEWAS / KHATEGAON | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4766994 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123504883 | Completed | 23490 | 0 | 2024-11-28 | 2026-08-13
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/4888000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122554812 | Physically Completed | 23490 | 0 | 2025-08-19 | 2026-08-23
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/5157250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122704040 | Physically Completed | 27000 | 0 | 2025-07-09 | 2026-09-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/5163975 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125324714 | Completed | 23490 | 0 | 2025-05-31 | 2026-08-13
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/5204699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123432996 | Completed | 23490 | 0 | 2025-05-04 | 2026-08-13
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/5220953 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127744449 | Ongoing | 27000 | 2100 | 2025-05-14
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/5393105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124847969 | Ongoing | 27000 | 1800 | 2025-07-28
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/5587862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127334239 | Physically Completed | 27000 | 0 | 2025-05-18 | 2026-09-29
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/5790066 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125342080 | Ongoing | 27000 | 0 | 2025-09-05
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6102287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105887410 | Ongoing | 27000 | 0 | 2026-07-10
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6102634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123531860 | Ongoing | 27000 | 0 | 2026-07-10
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6102873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122548348 | Ongoing | 27000 | 0 | 2026-06-09
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6103624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124771352 | Ongoing | 27000 | 11700 | 2026-06-04
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6104574 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127327960 | Ongoing | 27000 | 0 | 2026-06-22
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6104907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121621141 | Ongoing | 27000 | 4200 | 2026-04-17
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6105596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124078846 | Ongoing | 27000 | 8400 | 2026-05-07
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6106049 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123526278 | Ongoing | 27000 | 0 | 2026-07-15
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6106378 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124831045 | Ongoing | 27000 | 3300 | 2026-08-25
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6106598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124768386 | Ongoing | 27000 | 11700 | 2026-06-04
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6107117 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117850643 | Ongoing | 27000 | 12600 | 2026-06-04
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6107878 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114736150 | Ongoing | 27000 | 4200 | 2026-04-17
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6107981 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122714319 | Approved | 27000 | 0 | 2026-02-26
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6108032 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114734815 | Ongoing | 27000 | 4200 | 2026-04-17
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6108052 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123059027 | Ongoing | 27000 | 10500 | 2026-05-07
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6108055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121620318 | Ongoing | 27000 | 0 | 2026-06-09
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6108348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118305622 | Ongoing | 27000 | 0 | 2026-04-17
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6108499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123991763 | Ongoing | 27000 | 0 | 2026-07-24
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6108685 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126901861 | Approved | 27000 | 0 | 2026-02-26
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6108707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121564054 | Ongoing | 27000 | 0 | 2026-06-21
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6109477 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121986630 | Ongoing | 27000 | 0 | 2026-06-04
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6148333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125341598 | Ongoing | 27000 | 0 | 2026-07-15
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6156036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123527550 | Ongoing | 27000 | 0 | 2026-07-15
DEWAS / KHATEGAON | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6168509 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122751632 | Approved | 27000 | 0 | 2026-03-02
DEWAS / KHATEGAON | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1720006063/IF/IAY/6170466 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124836997 | Ongoing | 27000 | 15900 | 2026-07-10
DEWAS / KHATEGAON | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1720006063/RS/22012034648905 — नाली निर्माण चौपाटी से गोपाल के घर तक लम्बाई 280 मी. ग्राम दुद्वास | Physically Completed | 35000 | 0 | 2022-04-02 | 2026-08-14