## Work List
Exported on: 2026-09-13 16:30:53
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: GHUNGHASA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
ALIRAJPUR / ALIRAJPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1721010026/AV/22012034664317 — PULIYA NIRMAN KARYA SINDHI FALIYA GP GHUNGSHA | Approved | 76000 | 0 | 2024-08-15
ALIRAJPUR / ALIRAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1721010026/DP/22012034539778 — SARVJANIK KUP NIRMAN PATEL FALIYA GHOGNSA -2021-22 | Ongoing | 478796.2 | 0 | 2021-11-24
ALIRAJPUR / ALIRAJPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1721010026/DP/22012034561095 — AMRAT SAROWAR PLANTATION 100 TAD FALIYA GP GHUNGHASA 2022-23 | Ongoing | 128831.88 | 0 | 2022-09-06
ALIRAJPUR / ALIRAJPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Block Plantation of Horticulture Trees in fields for Community | Plantation | 1721010026/DP/22012034561097 — AMRAT SAROWAR PLANTATION 100 TALAB FALIYA GP GHONGSHA 2022-23 | Ongoing | 128831.88 | 0 | 2022-09-06
ALIRAJPUR / ALIRAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721010026/IF/22012034899770 — KAPIL DHARA KUP NIRMAN JHIGLI -SARDAR | Ongoing | 250732.62 | 0 | 2022-03-07
ALIRAJPUR / ALIRAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721010026/IF/22012034906324 — KAPIL DHAR KUP NIRMAN JARLI- KUSIYA GHOGNSA -2021-22 | Ongoing | 250732.62 | 0 | 2021-11-24
ALIRAJPUR / ALIRAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721010026/IF/22012034906334 — KAPIL DHARA KUPNIRMAN - RAMABAI- IDALA GHOGNSA -2021-22 | Ongoing | 250732.62 | 0 | 2021-12-04
ALIRAJPUR / ALIRAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721010026/IF/22012034906342 — KAPIL DHARA KUP NIRMAN JHALU- KUVARSINGH - GHGNSAA -2021-22 | Ongoing | 250732.62 | 6900 | 2022-02-28
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035248489 — NANDAN FALOUDYAN MAHESH DEVESINGH GP GHOGNSHA 2024/25 | Ongoing | 148282.63 | 0 | 2024-07-31
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035248548 — NANDAN FALOUDYAN PARTAP JAGLA GP GHOGNSHA 2024/25 | Ongoing | 148282.63 | 0 | 2024-07-31
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035248552 — NANDAN FALOUDYAN GOPAL SARDAR GP GHOGNSHA 2024/25 | Ongoing | 148282.63 | 0 | 2024-07-31
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035248577 — NANDAN FALOUDYAN DASHARI BAHADUR GP GHOGNSHA 2024/25 | Ongoing | 148282.63 | 0 | 2024-07-31
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035255249 — NANDAN FLOUDYAN DINESH BHERLA GHOGNSA 2024/25 | Ongoing | 149482.63 | 0 | 2024-10-15
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035255252 — NANDAN FLOUDYAN DESINGH SUKLIYA GHOGNSHA 2024/25 | Ongoing | 149482.63 | 0 | 2024-10-15
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035255253 — NANDAN FLOUDYAN NANLA CHAGAN GHOGNSA 2024/25 | Ongoing | 149482.63 | 0 | 2024-10-15
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035255261 — NANDAN FLOUDYAN SURTAN IDALA GHOGNSA 2024/25 | Ongoing | 148282.63 | 0 | 2025-07-03
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Farm Forstry-Individual / Wastelands Block Plantation of Farm Forestry Trees for Individuals | Plantation | 1721010026/IF/22012035256327 — NANDAN FLOUDYAN RELU SUKLIYA GHOGNSHA 2024/25 | Ongoing | 149482.63 | 0 | 2024-10-15
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721010026/IF/22012035292345 — KAIPL DAHRA KUP NIRMAN MAHESH KADAM GHOGNSHA 2024/25 | New | 0 | 0 | 2024-10-02
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1721010026/IF/22012035292351 — KAIPL DAHRA KUP NIRMAN MAHESH KADAM GHOGNSHA 2024/25 | Approved | 0 | 0 | 2024-10-02
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1721010026/IF/22012035333023 — JGSA 2025 KHET TALAB NIRMAN MAHESH DEVISINGH PATEL FALIYA GP GHUNGHASA | Ongoing | 78270.64 | 0 | 2025-04-26
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1721010026/IF/22012035333044 — JGSA 2025 KHET TALAB NIRMAN SAJJANSINGH HARSINH JAMRA FALIYA GP GHUNGHASA | New | 0 | 0 | 2025-04-08
ALIRAJPUR / ALIRAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1721010026/IF/22012035364323 — JGSA 2025 RECHARGE STRUCTURE AT KAPIL DHRA KUP DHULSINGH JEMLA PATEL FALIYA GHOGNSA | New | 0 | 0 | 2025-04-01
ALIRAJPUR / ALIRAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1721010026/IF/22012035577127 — JGSA 2025 RECHARGE STRUCTURE AT KAPIL DHARA KUP KAILASH BHANTA GP GHONGSHA | Approved | 25899.46 | 0 | 2025-05-02
ALIRAJPUR / ALIRAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1721010026/IF/22012035577129 — JGSA 2025 RECHARGE STRUCTURE AT KAPIL DHARA KUP JUWANSINGH SUMARIYA GP GHONGSHA | Approved | 24899.46 | 0 | 2025-05-02
ALIRAJPUR / ALIRAJPUR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/314186 — Construction of IAY House -IAY REG. NO. MP1056798 | Approved | 27000 | 0 | 2017-01-03
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/4716189 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127619728 | Physically Completed | 23490 | 0 | 2025-03-26 | 2026-08-09
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/4826015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124145738 | Ongoing | 27000 | 0 | 2025-03-26
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/4826748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124586334 | Ongoing | 27000 | 0 | 2024-12-24
ALIRAJPUR / ALIRAJPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/4865372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126163708 | Ongoing | 27000 | 0 | 2025-03-26
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/4911022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126321127 | Ongoing | 27000 | 0 | 2025-04-09
ALIRAJPUR / ALIRAJPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/50701 — Construction of IAY House -IAY REG. NO. MP-21-010-026-002/3596 | Approved | 27000 | 0 | 2015-10-18
ALIRAJPUR / ALIRAJPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/50702 — Construction of IAY House -IAY REG. NO. MP-21-010-026-002/3572 | Approved | 27000 | 0 | 2015-10-18
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/5085997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127616049 | Physically Completed | 23490 | 0 | 2025-09-17 | 2026-08-09
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/5274704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124571119 | Ongoing | 27000 | 0 | 2025-05-29
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/5470553 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123306992 | Completed | 23490 | 0 | 2025-11-21 | 2026-09-01
ALIRAJPUR / ALIRAJPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/5471240 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126196717 | Ongoing | 27000 | 0 | 2025-05-22
ALIRAJPUR / ALIRAJPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/69983 — Construction of IAY House -IAY REG. NO. MP-21-010-026-002/3595 | Ongoing | 27000 | 0 | 2026-05-15
ALIRAJPUR / ALIRAJPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/882598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1897952 | Ongoing | 27000 | 0 | 2021-12-14
ALIRAJPUR / ALIRAJPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1721010026/IF/IAY/96253 — Construction of IAY House -IAY REG. NO. MP-21-010-026-002/3610 | Approved | 27000 | 0 | 2015-09-18
ALIRAJPUR / ALIRAJPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1721010026/RC/22012034830913 — PCC ROAD CHAMAR FALIYA GHOGNSHA 2024 /2025 | Ongoing | 117000 | 0 | 2025-02-25
ALIRAJPUR / ALIRAJPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1721010026/WC/22012034682686 — CTR LOOSE BOLDER2 GHOG NSA CHEK DEM PATEL FALIYA PART - (20 ) -2021-22 | Ongoing | 267972.42 | 0 | 2021-06-16
ALIRAJPUR / ALIRAJPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1721010026/WC/22012034682691 — CTR LOOSE BOLDERCHEKDEM BAWDI FALIYA GHOG NSA (20 ) -2021-22 | Ongoing | 257856.1 | 0 | 2021-12-01
ALIRAJPUR / ALIRAJPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1721010026/WC/22012034682706 — CTR LOOSE BOLDER CHEK DEM JAMRA FALIYA GHOGNSA (20) -2021-22 | Ongoing | 270749.32 | 0 | 2021-06-03
ALIRAJPUR / ALIRAJPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1721010026/WH/22012034445024 — BAWDI RENOVATION PATEL FALIYA GHONGHSA 2020-21 | Ongoing | 191078.12 | 0 | 2020-09-02
ALIRAJPUR / ALIRAJPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1721010026/WH/22012034945159 — JGSA BAWADI JIRNODHAR KARYA SINDHI FALIYA GHONGSHA 2025 | Approved | 100560.56 | 0 | 2025-04-04