## Work List
Exported on: 2026-08-14 12:07:56
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Khutpala
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / SARDARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002016/IF/22012034587212 — varksharopan hanuman mandir ke pass | Ongoing | 390826.48 | 0 | 2020-08-16
DHAR / SARDARPUR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722002016/IF/22012034656712 — kapil dhara kup saman bai hira | Ongoing | 246126.86 | 0 | 2021-11-23
DHAR / SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1722002016/IF/22012035069002 — kapil dhara kup jatan bai soma | Ongoing | 250129.18 | 0 | 2023-05-08
DHAR / SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Boulder Check Dam for Individuals / Construction of Boulder Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1722002016/IF/22012035090064 — kapil dhara kup nirman mansingh bheru | Ongoing | 250082.8 | 0 | 2023-07-19
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1722002016/IF/22012035221991 — kapil dhara kup nirman galiya kanji | Ongoing | 250603.32 | 0 | 2025-05-10
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Earthen Check Dam for Individuals / Construction of Earthen Anicut Check Dam for Individuals | Construction of Check Dam/Stop Dam | 1722002016/IF/22012035430501 — khet talab bhagirath nathu | Ongoing | 55865.38 | 0 | 2025-05-09
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Mini Percolation Tank for Individuals / Construction of Mini Percolation Tank for Individuals | Construction of Percolation Tank | 1722002016/IF/22012035465399 — Khet talab Rajkumar goma | Ongoing | 55865.38 | 0 | 2025-05-14
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722002016/IF/22012035477090 — jal ganga savardhan dugwell recharge mansingh bheru | Approved | 25899.46 | 0 | 2025-04-14
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722002016/IF/22012035477099 — jal ganga savardhan dugwell recharge galu kanji | Approved | 25899.46 | 0 | 2025-04-14
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722002016/IF/22012035491036 — Jal ganga sanvardhan dugwell ramchandra kodu | Approved | 25899.46 | 0 | 2025-04-14
DHAR / SARDARPUR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/1147292 — Construction of IAY House -IAY REG. NO. MP1691893 | Approved | 23490 | 0 | 2017-05-25
DHAR / SARDARPUR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/2403442 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4480423 | Approved | 23490 | 0 | 2020-04-29
DHAR / SARDARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/3650873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1703372 | Ongoing | 23490 | 0 | 2023-05-02
DHAR / SARDARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/3684250 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106565518 | Ongoing | 23490 | 0 | 2023-08-07
DHAR / SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4195910 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122803931 | Ongoing | 23490 | 0 | 2022-06-23
DHAR / SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4244334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116449520 | Approved | 23490 | 0 | 2022-06-21
DHAR / SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4360773 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116449504 | Approved | 23490 | 0 | 2022-07-02
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4684156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102937626 | Completed | 23490 | 0 | 2024-11-21 | 2026-07-29
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4686991 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105998307 | Approved | 23490 | 0 | 2024-09-20
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4687428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106433397 | Ongoing | 23490 | 0 | 2026-04-24
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4687756 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105853607 | Completed | 23490 | 0 | 2024-12-24 | 2026-07-29
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4689589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106406619 | Approved | 23490 | 0 | 2024-09-20
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4697394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117899077 | Approved | 23490 | 0 | 2024-09-20
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4700376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118166983 | Ongoing | 23490 | 0 | 2024-12-13
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4706941 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123795782 | Approved | 23490 | 0 | 2024-09-20
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4706971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123171038 | Ongoing | 23490 | 0 | 2024-10-30
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4739352 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105515031 | Approved | 23490 | 0 | 2024-10-01
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4740041 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106408298 | Ongoing | 23490 | 7200 | 2026-05-05
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4740152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106433431 | Ongoing | 23490 | 3600 | 2026-04-24
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4742933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113751950 | Ongoing | 23490 | 0 | 2025-05-21
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4753305 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118156971 | Completed | 23490 | 0 | 2026-03-11 | 2026-08-11
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4767612 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123339128 | Approved | 23490 | 0 | 2024-09-27
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/4777564 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126760164 | Ongoing | 23490 | 0 | 2026-07-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5412290 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104027421 | Ongoing | 23490 | 0 | 2025-05-08
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5412386 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP148537493 | Ongoing | 23490 | 6600 | 2026-05-05
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5412686 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120551500 | Ongoing | 23490 | 0 | 2026-07-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5412857 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106409692 | Completed | 23490 | 0 | 2026-01-22 | 2026-08-11
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5413043 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123038593 | Ongoing | 23490 | 0 | 2025-06-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5413238 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100508461 | Completed | 23490 | 0 | 2025-04-22 | 2026-08-11
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5413592 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121614129 | Completed | 23490 | 0 | 2025-06-01 | 2026-07-29
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5413627 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105835259 | Ongoing | 23490 | 3300 | 2025-10-06
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5413797 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114745490 | Approved | 23490 | 0 | 2025-03-04
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5413799 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113754485 | Ongoing | 23490 | 0 | 2026-07-22
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5413971 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP104901519 | Approved | 23490 | 0 | 2025-03-03
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5414029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113786379 | Ongoing | 23490 | 0 | 2025-06-18
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5414291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126761264 | Ongoing | 23490 | 0 | 2026-07-22
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5414405 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123526718 | Approved | 23490 | 0 | 2025-03-04
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5414642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106421863 | Ongoing | 23490 | 0 | 2025-06-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5414724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105510694 | Ongoing | 23490 | 0 | 2025-10-06
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5414738 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123536603 | Ongoing | 23490 | 0 | 2025-10-06
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5414831 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102668657 | Ongoing | 23490 | 0 | 2025-05-08
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5415069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113656047 | Ongoing | 23490 | 0 | 2026-07-22
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5415220 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106277646 | Ongoing | 23490 | 0 | 2026-07-22
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5415249 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126762062 | Ongoing | 23490 | 0 | 2026-07-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5415303 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105467962 | Completed | 23490 | 0 | 2025-06-18 | 2026-07-29
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5415357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105525181 | Completed | 23490 | 0 | 2025-05-21 | 2026-07-29
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5415557 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113727477 | Ongoing | 23490 | 0 | 2026-08-05
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5416008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105876152 | Completed | 23490 | 0 | 2025-04-22 | 2026-07-29
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5416136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118045354 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5416190 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116449615 | Ongoing | 23490 | 3300 | 2026-06-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5416291 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105702768 | Ongoing | 23490 | 0 | 2025-06-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5497826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102937591 | Ongoing | 23490 | 0 | 2025-07-02
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5509276 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103539317 | Ongoing | 23490 | 0 | 2025-05-21
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5511156 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103632081 | Ongoing | 23490 | 0 | 2025-08-12
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5596485 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106004913 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5712569 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103129700 | Ongoing | 23490 | 0 | 2025-08-12
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5712826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124178740 | Ongoing | 23490 | 6600 | 2025-08-31
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5725507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114146264 | Ongoing | 23490 | 0 | 2025-08-12
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5728435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118203511 | Approved | 23490 | 0 | 2025-06-13
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5833479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116448078 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5833501 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113754370 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5833549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120549953 | Ongoing | 23490 | 0 | 2026-01-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5833681 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113633192 | Completed | 23490 | 0 | 2026-01-23 | 2026-07-29
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5833736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106564782 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5834016 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114749637 | Ongoing | 23490 | 0 | 2025-11-27
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5834031 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122042230 | Approved | 23490 | 0 | 2025-03-18
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5834110 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131436109 | Approved | 23490 | 0 | 2025-03-03
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5834351 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116645048 | Ongoing | 23490 | 0 | 2025-12-23
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5835158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113675729 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5835626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106547644 | Approved | 23490 | 0 | 2025-03-12
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5835844 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126006567 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5836537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116310396 | Approved | 23490 | 0 | 2025-03-03
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002016/IF/IAY/5836784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105996872 | Approved | 23490 | 0 | 2025-02-22
DHAR / SARDARPUR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722002016/RC/22012034843781 — sudur sadak nirman majra amkundiya se chandhodiya pradhanmantri sadak tak | Approved | 0 | 0 | 2025-04-14
DHAR / SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Underground Dykes for Community / Construction of Underground Dykes for Community | Underground Dyke for Ground Water Recharge | 1722002016/WC/22012035247044 — NISTAR TALAB NIRMAN RUNDA WALA NALE PER KHUTPALA | Ongoing | 1482890.72 | 0 | 2025-02-18
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722002016/WC/22012035301226 — jal ganga savardhan dugwell recharge samudayik kup retikhodra | Approved | 25899.46 | 0 | 2025-04-14
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012035164671 — Jitendra Prabhulal Gp Khuntpala Horti.Plantation | Ongoing | 231000 | 0 | 2024-06-13
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722002/IF/22012035257765 — Dhana Kodar Horti plant Gp khutpala | Ongoing | 191848 | 0 | 2025-02-06
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722002/WC/22012035311660 — Nistar talab Nirman Kary semalkhedi | Ongoing | 3877000 | 0 | 2025-06-07
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722002/WC/22012035311662 — Nistar Talab Nirman Kary Retikhodara | Ongoing | 3849000 | 0 | 2025-06-07