## Work List
Exported on: 2026-09-25 17:29:37
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Hatod
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / SARDARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1722002069/AV/22012034658971 — PULIYA NIRMAN KARYA HENDPUMP KE PAS HATOD | Approved | 21000 | 0 | 2024-06-01
DHAR / SARDARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1722002069/AV/22012034664115 — नाली निर्माण सुखराम नरसिंह के घर से भेरु जी मंदिर तक | Approved | 58000 | 0 | 2025-01-28
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722002069/IF/22012035479918 — JSGA khet talab narayan narsingh hatod ke khet pr | Ongoing | 447404.04 | 0 | 2025-05-09
DHAR / SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/128667 — Construction of IAY House -IAY REG. NO. MP-22-002-069-001/029 | Approved | 27000 | 0 | 2016-01-30
DHAR / SARDARPUR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/3813913 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118063344 | Ongoing | 27000 | 0 | 2022-07-22
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4561245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115625588 | Ongoing | 27000 | 0 | 2024-09-23
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4561298 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115632755 | Ongoing | 27000 | 0 | 2024-10-23
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4561590 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115429525 | Ongoing | 27000 | 1305 | 2024-09-23
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4561620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115609045 | Ongoing | 27000 | 0 | 2024-10-08
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4576709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117765029 | Ongoing | 27000 | 0 | 2024-10-08
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4578230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118120412 | Ongoing | 27000 | 0 | 2024-10-08
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4596231 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121974185 | Ongoing | 27000 | 0 | 2024-10-08
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4692658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115625260 | Ongoing | 27000 | 0 | 2024-10-08
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4694161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115738863 | Ongoing | 27000 | 0 | 2024-10-08
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4694209 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115753066 | Ongoing | 27000 | 0 | 2024-11-04
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4700839 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118055014 | Ongoing | 27000 | 0 | 2024-12-02
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/4753237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118137892 | Ongoing | 27000 | 0 | 2024-11-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5267460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115755501 | Ongoing | 27000 | 0 | 2025-04-14
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5273494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115613942 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5303075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115631567 | Completed | 23490 | 0 | 2025-04-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5307495 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122013655 | Completed | 23490 | 0 | 2025-05-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5317701 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115747779 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5318586 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115749394 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5329029 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117599398 | Completed | 23490 | 0 | 2025-04-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5331121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116480844 | Completed | 23490 | 0 | 2025-05-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5339401 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115617480 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5344045 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115422888 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5344341 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115750097 | Completed | 23490 | 0 | 2025-05-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5345546 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115403729 | Physically Completed | 23490 | 7830 | 2025-05-29 | 2026-08-19
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5345780 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115644013 | Physically Completed | 23490 | 3915 | 2025-06-05 | 2026-08-19
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5346174 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126039324 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5346237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117271552 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5346266 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117595922 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5346480 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118039690 | Completed | 23490 | 0 | 2025-04-17 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5346716 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115744325 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5347431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115609115 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5347439 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115616725 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5347465 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115622369 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5347476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115646539 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5347619 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115651954 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-25
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5347795 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117486271 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5347796 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117487879 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5348393 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117482395 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5348946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115742904 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5349144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124398850 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5349690 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115635787 | Completed | 23490 | 0 | 2025-06-05 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5350261 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116401634 | Completed | 23490 | 0 | 2025-06-05 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5350486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115645939 | Completed | 23490 | 0 | 2025-04-14 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5350596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115428669 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5350601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115641152 | Completed | 23490 | 0 | 2025-04-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5350734 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115624642 | Completed | 23490 | 0 | 2025-04-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5350748 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115405146 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5351084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115742003 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5351575 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115638372 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5352162 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115629534 | Completed | 23490 | 0 | 2025-04-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5352782 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119536434 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5353848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118052072 | Completed | 23490 | 0 | 2025-05-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5354311 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115398787 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5354312 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115398918 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5354417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106636838 | Completed | 23490 | 0 | 2025-04-29 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5355436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115276864 | Completed | 23490 | 0 | 2025-04-14 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5489595 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118140844 | Completed | 23490 | 0 | 2025-06-05 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5490367 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114180986 | Ongoing | 27000 | 11745 | 2025-06-05
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5492873 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115400123 | Ongoing | 27000 | 10245 | 2025-06-05
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5493460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115640007 | Completed | 23490 | 0 | 2025-06-05 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5494201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116470060 | Physically Completed | 23490 | 3915 | 2025-06-05 | 2026-08-19
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5495054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115636560 | Ongoing | 27000 | 11745 | 2025-06-05
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5495243 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115609056 | Ongoing | 27000 | 15660 | 2025-06-05
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5626867 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115642869 | Completed | 23490 | 0 | 2025-06-05 | 2026-07-23
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5829908 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120552723 | Approved | 27000 | 0 | 2025-02-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5829950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119618845 | Completed | 23490 | 0 | 2025-10-04 | 2026-08-20
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830070 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117489386 | Approved | 27000 | 0 | 2025-02-21
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830073 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115426241 | Ongoing | 27000 | 11745 | 2025-10-24
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119602307 | Ongoing | 27000 | 11745 | 2026-02-17
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830121 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117592035 | Approved | 27000 | 0 | 2025-03-10
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830163 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145509849 | Approved | 27000 | 0 | 2025-03-10
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115424467 | Completed | 23490 | 0 | 2025-10-04 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830435 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116479801 | Completed | 23490 | 0 | 2025-10-04 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830436 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118053049 | Completed | 23490 | 0 | 2025-10-04 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830478 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115650235 | Completed | 23490 | 0 | 2025-10-04 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116455016 | Ongoing | 27000 | 11745 | 2026-02-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115427237 | Completed | 23490 | 0 | 2025-10-04 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830596 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116456127 | Approved | 27000 | 0 | 2025-04-14
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830603 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117765016 | Physically Completed | 23490 | 7830 | 2025-10-04 | 2026-08-19
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115647102 | Ongoing | 27000 | 11745 | 2026-02-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830633 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115651282 | Completed | 23490 | 0 | 2025-10-04 | 2026-07-23
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115735683 | Ongoing | 27000 | 11745 | 2026-02-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830635 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115752326 | Completed | 23490 | 0 | 2025-10-04 | 2026-07-25
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830658 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118065978 | Ongoing | 27000 | 0 | 2025-12-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123167654 | Physically Completed | 27000 | 11250 | 2025-10-24 | 2026-09-04
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115634391 | Completed | 23490 | 0 | 2026-02-17 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830912 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117491486 | Completed | 23490 | 0 | 2025-10-04 | 2026-07-25
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116467572 | Completed | 23490 | 0 | 2025-10-04 | 2026-07-25
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5830961 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119614775 | Completed | 23490 | 0 | 2026-02-17 | 2026-08-20
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5831013 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115396424 | Ongoing | 27000 | 9000 | 2026-02-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5831017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121978143 | Ongoing | 27000 | 11745 | 2026-02-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/5831059 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118046850 | Ongoing | 27000 | 9000 | 2026-02-17
DHAR / SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/82418 — Construction of IAY House -IAY REG. NO. MP-22-002-069-001/46 | Approved | 27000 | 0 | 2015-10-31
DHAR / SARDARPUR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722002069/IF/IAY/82419 — Construction of IAY House -IAY REG. NO. MP-22-002-069-001/50 | Approved | 27000 | 0 | 2015-10-31
DHAR / SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722002069/WC/22012035163570 — Parcoletion Tank | New | 0 | 0 | 2024-01-08
DHAR / SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722002069/WC/22012035221334 — परकोलेसन टेंक मोवड़ा खोदरी निर्मलनीर के ऊपर हातोद | Approved | 0 | 0 | 2024-08-16
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722002/WC/22012035325839 — NISTAR TALAB NIRMAN KARY NIRMAL NEER KE UPER WALA NALA | Ongoing | 3959000 | 0 | 2026-03-08