## Work List
Exported on: 2026-10-21 20:31:05
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Nayapura
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / SARDARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pit for Individual | Construction of Recharge Pits | 1722002084/IF/22012034718405 — kapildhara kup nirman mohan bada nayapura | Ongoing | 250732.62 | 0 | 2022-05-27
DHAR / SARDARPUR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722002084/IF/22012034925927 — KAPIL DHARA KUP NIRMAN BHUWAN KERU AJANMAL | Ongoing | 250732.62 | 0 | 2022-05-18
DHAR / SARDARPUR | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/22012035104928 — Construction of PMAY-G House for IndividualsPMAY-G REG. NO. -MP115922836 | Ongoing | 18360 | 0 | 2023-06-16
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002084/IF/22012035475988 — khet talab nirman kary kekdiya k khet nayapura | Ongoing | 147621.16 | 0 | 2025-05-16
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002084/IF/22012035476087 — khet talab nirman kary makna k khet nayapura | Approved | 147621.16 | 0 | 2025-04-14
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722002084/IF/22012035476176 — khet talab nirman kary somla mangliya k khet anjanmaal | Approved | 147621.16 | 0 | 2025-04-14
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4562507 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115670265 | Completed | 23490 | 0 | 2024-12-16 | 2026-08-17
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4563253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115922145 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-31
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4564230 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116083377 | Completed | 23490 | 0 | 2024-12-16 | 2026-08-01
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4596486 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123121842 | Completed | 23490 | 0 | 2025-01-14 | 2026-08-01
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4603560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124666150 | Completed | 23490 | 0 | 2024-12-16 | 2026-08-01
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4618669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126492932 | Completed | 27000 | 0 | 2024-12-16 | 2026-09-04
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4641343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP136182052 | Physically Completed | 27000 | 0 | 2025-08-11 | 2026-10-18
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4648514 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP142979692 | Ongoing | 27000 | 0 | 2025-12-02
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4691922 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115390273 | Completed | 23490 | 0 | 2024-12-31 | 2026-08-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4693893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116425054 | Ongoing | 27000 | 0 | 2025-12-03
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4751582 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116917056 | Completed | 23490 | 0 | 2024-12-16 | 2026-08-01
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4765696 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764139 | Ongoing | 27000 | 4200 | 2025-01-01
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4765697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764210 | Approved | 27000 | 0 | 2024-09-29
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4765812 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115782180 | Completed | 23490 | 0 | 2025-02-12 | 2026-08-01
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4765814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115782323 | Completed | 27000 | 0 | 2024-12-16 | 2026-09-04
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4765815 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115782367 | Completed | 23490 | 0 | 2025-03-26 | 2026-08-01
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4773733 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122643962 | Completed | 23490 | 0 | 2024-12-16 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/4775608 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125440706 | Ongoing | 27000 | 0 | 2025-05-27
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5344345 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115782158 | Completed | 23490 | 0 | 2025-08-11 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5344431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114735161 | Completed | 23490 | 0 | 2025-09-11 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5344954 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118308445 | Completed | 23490 | 0 | 2025-11-04 | 2026-08-31
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5345099 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120811753 | Ongoing | 27000 | 0 | 2025-05-27
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5345100 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120812746 | Ongoing | 27000 | 4200 | 2025-09-10
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5345101 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120812880 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5345283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118348864 | Completed | 23490 | 0 | 2025-05-05 | 2026-08-17
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5346054 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126397727 | Ongoing | 27000 | 0 | 2026-10-12
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5346055 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126400899 | Approved | 27000 | 0 | 2025-03-08
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5346719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764080 | Completed | 23490 | 0 | 2025-05-05 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5347183 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116430534 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5347219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115050019 | Completed | 27000 | 4200 | 2025-12-03 | 2026-10-14
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5347694 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121584989 | Completed | 23490 | 0 | 2025-08-11 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5347695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121585517 | Completed | 23490 | 0 | 2025-08-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5347697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121586056 | Completed | 23490 | 0 | 2025-08-11 | 2026-08-31
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5348535 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123127276 | Completed | 27000 | 0 | 2025-10-10 | 2026-10-14
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5348536 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123129274 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5349858 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120813230 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5350210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115670278 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5350357 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123119453 | Completed | 23490 | 0 | 2025-05-06 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5350358 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123122472 | Completed | 23490 | 4200 | 2025-08-11 | 2026-09-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5350587 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123128533 | Completed | 23490 | 2400 | 2025-08-27 | 2026-09-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5350682 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115106023 | Completed | 23490 | 9000 | 2025-05-05 | 2026-09-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5351223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116422601 | Completed | 23490 | 300 | 2025-05-27 | 2026-09-22
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5351531 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115922954 | Ongoing | 27000 | 0 | 2025-10-10
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5351560 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115921730 | Completed | 27000 | 0 | 2025-08-11 | 2026-09-04
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5351561 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115921933 | Completed | 23490 | 0 | 2025-05-05 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5351562 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115921993 | Completed | 27000 | 0 | 2025-05-05 | 2026-09-04
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5352150 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115389634 | Completed | 27000 | 0 | 2025-05-05 | 2026-09-04
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5352588 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764164 | Completed | 23490 | 0 | 2025-07-25 | 2026-08-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5353114 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121583175 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5354074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116931966 | Completed | 23490 | 8400 | 2025-08-06 | 2026-08-31
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5354157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119500290 | Completed | 27000 | 0 | 2025-07-25 | 2026-10-14
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5354158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119500305 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5354173 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121584011 | Completed | 23490 | 0 | 2025-05-05 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5354397 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133803093 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5354398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP133803470 | Completed | 23490 | 0 | 2025-05-05 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5355460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116624120 | Completed | 23490 | 0 | 2025-05-05 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5355852 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122645136 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5356017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126545635 | Ongoing | 27000 | 0 | 2025-05-27
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5553270 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118349027 | Completed | 23490 | 0 | 2025-07-25 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5558624 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115105665 | Physically Completed | 27000 | 0 | 2025-08-11 | 2026-10-18
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5560348 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123128313 | Completed | 23490 | 0 | 2025-05-27 | 2026-08-17
DHAR / SARDARPUR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5562027 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116432417 | Ongoing | 27000 | 0 | 2026-10-12
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5563151 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115389583 | Completed | 23490 | 0 | 2025-05-05 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5599494 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123127485 | Physically Completed | 27000 | 0 | 2025-12-24 | 2026-10-18
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5606784 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123119069 | Completed | 23490 | 0 | 2025-11-04 | 2026-08-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5607111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116646878 | Completed | 23490 | 0 | 2025-09-24 | 2026-08-01
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5712410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121640835 | Ongoing | 27000 | 0 | 2025-10-10
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5712791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115389408 | Ongoing | 27000 | 4200 | 2025-10-10
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5732126 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115349585 | Completed | 23490 | 0 | 2025-11-04 | 2026-08-17
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5833580 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128008484 | Approved | 27000 | 0 | 2025-03-05
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5833669 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121638080 | Ongoing | 27000 | 0 | 2025-10-10
DHAR / SARDARPUR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5835460 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118320520 | Approved | 27000 | 0 | 2025-03-03
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5835949 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123131756 | Completed | 23490 | 0 | 2025-11-04 | 2026-08-17
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5836479 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116650253 | Ongoing | 27000 | 0 | 2026-02-04
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5836803 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115782257 | Completed | 27000 | 0 | 2025-10-10 | 2026-10-14
DHAR / SARDARPUR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722002084/IF/IAY/5836804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120812535 | Ongoing | 27000 | 0 | 2025-11-04
DHAR / SARDARPUR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Kharanja (brick/stone) Roads for Comm / Construction of Kharanja Road for Community | Construction of Road and Culvert | 1722002084/RC/22012034824938 — Vikram k ghar pichhe se veeru somji k ghar tak cement conkret rode nirman posiya | New | 0 | 0 | 2024-05-10
DHAR / SARDARPUR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722002084/WC/22012034523363 — samudayak kup nirman khalavali baydi k pass nayapura | Ongoing | 567610.07 | 0 | 2020-09-28
DHAR / SARDARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722002084/WC/22012034638118 — CTRA parcolation tank posiya | Ongoing | 588461.07 | 0 | 2021-06-06
DHAR / SARDARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Gabion Anicut for Community / Construction of Gabion Check Dam for Community | Constr of Gabion | 1722002084/WC/22012034660581 — CTRA Gabion nirman bhag 1 taraghati | Ongoing | 69044.26 | 0 | 2021-05-26
DHAR / SARDARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722002084/WC/22012034668967 — samudayik kup nirman kundiya nayapura | Ongoing | 577784.48 | 7200 | 2021-12-04
DHAR / SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722002084/WC/22012035135306 — percoletion tank nirman Sursingh k khet k pass taraghati | Ongoing | 1498743.18 | 0 | 2023-10-08
DHAR / SARDARPUR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722002084/WC/22012035135319 — percoletion tank nirman kamdar k khet k pass taraghati | Ongoing | 1402855.02 | 0 | 2025-01-21
DHAR / SARDARPUR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722002084/WC/22012035164473 — Percolation tank nirman | New | 0 | 0 | 2024-01-08
DHAR / SARDARPUR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722002084/WC/22012035297288 — khet talab nirman kary kekdiya k khet nayapura | Approved | 55865.38 | 0 | 2025-04-14
DHAR / SARDARPUR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722002/RC/22012034542608 — SUDUR SADAK POSHIYA SHAMSHAN GHAT SE MEHARSINGH KE GHAR TAK | Ongoing | 2978000 | 0 | 2020-09-28
DHAR / SARDARPUR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1722002/WC/22012034588030 — NISTAR TALAB NIRMAN SAMARIYYA WALA NALA NAYAPURA | Ongoing | 4736000 | 0 | 2021-04-28