## Work List
Exported on: 2026-10-09 23:36:50
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Chandwada
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1722003005/DP/22012034624988 — पोधा रोपण कार्य मढ़ी परिसर सिंदोडी ग्राम में ग्राम पंचायत चंदवाड़ा | Approved | 458563.17 | 0 | 2024-07-01
DHAR / TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003005/IF/22012035238806 — Khet talab nirman karya kailash jawarchand gram panchayat chandwada | New | 0 | 0 | 2024-06-10
DHAR / TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003005/IF/22012035259789 — khet talab nirman kary Vijay Rama gram chandwada gram panchayat chandwada | Approved | 416459.67 | 0 | 2024-09-01
DHAR / TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Agro Forestry Block Plantation for Individual | Plantation | 1722003005/IF/22012035305138 — khet talab bhagwansingh Tulsiram gram shindoda gram panchayat chandwada | Approved | 354161.48 | 0 | 2025-01-01
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003005/IF/22012035402550 — JGSA के अन्तर्गत खेत तालाब गोपाल मनीराम के खेत पर ग्राम पंचायत चंदवाड़ा | Approved | 147621.16 | 0 | 2025-04-15
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722003005/IF/22012035429377 — जल गंगा संवर्धन के अन्तर्गत खेत तालाब गोपाल मनीराम के खेत पर ग्राम चांदवाड़ा | New | 0 | 0 | 2025-04-05
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722003005/IF/22012035600869 — एक बगिया मॉ के नाम समूह जय मॉ हितग्राही - तुलसीबाई | Ongoing | 283052.3 | 0 | 2025-09-22
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722003005/IF/22012035600881 — एक बगिया मॉ के नाम समूह न्‍यू हितग्राही - शकुंतलाबाई | Ongoing | 283043.38 | 18899.46 | 2025-09-19
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722003005/IF/22012035600888 — एक बगिया मॉ के नाम समूह नारी शक्ति हितग्राही - लीलाबाई | Ongoing | 283489.62 | 41997.95 | 2026-01-27
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/199888 — Construction of IAY House -IAY REG. NO. MP-22-003-005-003/13 | Completed | 23490 | 0 | 2025-08-21 | 2026-07-25
DHAR / TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/4543354 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105336820 | Completed | 27000 | 4800 | 2024-11-10 | 2026-09-17
DHAR / TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/4615198 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126054371 | Completed | 23490 | 0 | 2024-10-21 | 2026-07-25
DHAR / TIRLA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/4863014 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105333089 | Completed | 23490 | 4176 | 2025-01-29 | 2026-09-17
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5488746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106442488 | Completed | 23490 | 0 | 2025-04-20 | 2026-07-22
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5489214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105471879 | Completed | 23490 | 1305 | 2025-04-20 | 2026-09-17
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5728538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106450963 | Completed | 23490 | 1305 | 2025-08-13 | 2026-09-17
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5807161 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106077472 | Completed | 23490 | 0 | 2025-11-13 | 2026-07-25
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5807391 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106199784 | Completed | 23490 | 1305 | 2025-10-27 | 2026-09-17
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5807727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146811776 | Physically Completed | 23490 | 0 | 2025-10-11 | 2026-07-29
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5808034 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105333239 | Completed | 23490 | 0 | 2025-10-11 | 2026-07-25
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5808676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP107069872 | Completed | 23490 | 0 | 2026-02-24 | 2026-09-17
DHAR / TIRLA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722003005/IF/IAY/5808678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102450538 | Completed | 23490 | 0 | 2025-10-11 | 2026-07-25
DHAR / TIRLA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Construction of Roof Top Rain Water Harvesting Structure for Community | Roof Water Harvesting on gov/panchayat bldg | 1722003005/WC/22012034684899 — CTRA Roof water harvesting Anganwadi Bhavan Sindoda | Ongoing | 5400 | 0 | 2022-06-28
DHAR / TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003005/WC/22012035200231 — Nammami gange talab jirnodhar kary samsan ke pass gram panchayat chandwada | Approved | 0 | 0 | 2024-06-02
DHAR / TIRLA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722003005/WC/22012035252114 — nala trenching kary purane. stop dam ke pass gram panchayat chandwada | Approved | 355601.97 | 0 | 2025-01-01