## Work List
Exported on: 2026-10-25 09:36:27
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: ANTRAI
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035329215 — KHET TALAB ARABALI IBRAHIM MUSAWADA | Physically Completed | 414268.99 | 398250.9 | 2025-04-16 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035428030 — KHET TALAB BABU SAMSER MUSAWDA | Physically Completed | 147621.16 | 134898 | 2025-04-29 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035436557 — KHET TALAB JAID SHEKH SAGIR | Physically Completed | 450885.64 | 439099 | 2025-04-30 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035436581 — KHET TALAB USMAN MAJID | Physically Completed | 450885.64 | 437794 | 2025-04-30 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035436597 — KHET TALAB CHOTE KHAN IMAMI KNHA | Physically Completed | 147621.16 | 134376 | 2025-04-30 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035436613 — KHET TALB JARDAR SHABIR | Physically Completed | 450885.64 | 435184 | 2025-04-30 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035456546 — KHET TALAB SHABAB KHAN MUSTUFA | Physically Completed | 55865.38 | 50194 | 2025-05-04 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004004/IF/22012035456568 — KHET TALAB ANWAR ABBAS | Physically Completed | 147621.16 | 134898 | 2025-05-04 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004004/IF/22012035575739 — KHET TALAB MUSTAFA MHAN YASIN KHAN | Physically Completed | 450884.72 | 361242 | 2026-02-15 | 2026-07-30
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004004/IF/IAY/3796683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105113699 | Physically Completed | 18360 | 0 | 2022-07-16 | 2024-11-21
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004004/IF/IAY/4033129 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149998485 | Physically Completed | 18360 | 0 | 2022-07-16 | 2024-11-27
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004004/IF/IAY/4652714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145812906 | Physically Completed | 23490 | 18531 | 2025-01-24 | 2026-05-16
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004004/IF/IAY/5230202 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145700628 | Physically Completed | 23490 | 21663 | 2025-09-24 | 2026-05-16
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004004/RC/22012034339736 — Khet road Noshad ke khet se Chhoyu ke khet tak | Physically Completed | 1500000 | 1486493.41 | 2017-06-01 | 2019-10-08
DHAR / DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004004/RC/22012034512235 — Approach road Pradhanmantri Road se Kavrasthan tak | Physically Completed | 229614.04 | 2112 | 2020-03-14 | 2020-04-01
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004004/RC/22012034523146 — Gravel Road Four lane se Shamshan marg tak | Physically Completed | 2271000 | 2261223.11 | 2020-05-25 | 2021-11-22
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004004/RC/22012034561535 — Gravel Sadak Antrai Se Rampur Marg Antrai | Physically Completed | 1759141.82 | 1761005.36 | 2021-03-20 | 2026-06-12
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034841682 — CC ROAD PRADHAN MANTRI ROAD SE SAMSAN GHAT MUSAVADA | Physically Completed | 18000 | 16704 | 2025-04-13 | 2026-07-30
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034841683 — CC ROAD HOLY TEKRA SE RAZAK KE GHAR TAK MUSAVDA | Physically Completed | 21000 | 19314 | 2025-04-13 | 2026-07-21
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034846447 — CC ROAD BANESING KE GHAR SE MEHMUD KE GHAR TAK | Physically Completed | 96000 | 93879 | 2025-07-23 | 2026-07-30
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004004/RS/22012034542723 — Nali Nirman Pulia se Muharam Chok Tak anyrai | Physically Completed | 104000 | 103255 | 2021-08-25 | 2026-06-12
DHAR / DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034890154 — ramsingh niji khet plantation | Physically Completed | 206310 | 189267.4 | 2021-11-16 | 2026-06-06
DHAR / DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034890174 — Dinesh niji khet plantation | Physically Completed | 412620 | 408220.72 | 2021-11-16 | 2026-06-06
DHAR / DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034890198 — Rakesh niji khet plantation | Physically Completed | 412620 | 403460.94 | 2022-02-28 | 2026-06-06