## Work List
Exported on: 2026-10-22 13:00:14
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: ANTRAI
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1722004004/AV/22012034657500 — mukhya nala safai gram panchayat antrai | New | 0 | 0 | 2024-06-22
DHAR / DHAR | 2026-2027 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Play field for Community / Construction of Play Ground for Government School for Community | Construction of Play field | 1722004004/AV/VB/YD/22012034670065 — Construction of Play field at primary School antrai | New | 0 | 0 | 2026-04-14
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Works for Flood Control and Protection | 1722004004/FP/22012034638083 — Nala tranching | New | 0 | 0 | 2024-01-24
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004004/IF/22012035575739 — KHET TALAB MUSTAFA MHAN YASIN KHAN | Physically Completed | 450884.72 | 16200 | 2026-02-15 | 2026-07-30
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/22012035600925 — EK BAGIYA MA KE NAM PLANTATION WORK RAJJU BEE | Ongoing | 269386.03 | 0 | 2025-09-01
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/22012035600931 — EK BAGIYA MA KE NAM PLANTATION WORK MERAJ BEE | Ongoing | 269386.03 | 0 | 2025-09-01
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/22012035600960 — EK BAGIYA MA KE NAM PLANTATION WORK SABINA BEE | Ongoing | 269386.03 | 300 | 2025-09-01
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/22012035603318 — ek bagiya maa ke naam KHWAJA GARIB NAWAZ AAJIVIKA SHG NAFISA BI | Ongoing | 269386.03 | 600 | 2025-09-09
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/22012035603325 — ek bagiya maa ke naam shg SHAHANSHAH AAJIVIKA SHG SHAMSHAD BI | New | 0 | 0 | 2025-08-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/22012035604856 — Ek BAGIYA MA KE NAAM SHG shahanshah aajivika shamshad | Ongoing | 269386.03 | 0 | 2025-09-09
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004004/IF/22012035657535 — Niji khet talab subhan pita jassu | Approved | 0 | 0 | 2025-12-26
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004004/IF/22012035657544 — Niji khet talab sattar pita imami | Approved | 0 | 0 | 2025-12-26
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/198178 — Construction of IAY House -IAY REG. NO. MP-22-004-004-001/76 | Approved | 27000 | 0 | 2016-03-11
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4542901 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105669134 | Completed | 23490 | 0 | 2025-01-24 | 2026-08-03
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4543521 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105369526 | Approved | 27000 | 0 | 2024-09-13
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4649907 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145708031 | Completed | 23490 | 0 | 2026-06-14 | 2026-07-19
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4651203 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145714039 | Completed | 23490 | 0 | 2025-01-24 | 2026-08-03
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4657008 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147755390 | Completed | 23490 | 0 | 2026-06-14 | 2026-07-19
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4664502 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151003189 | Completed | 23490 | 0 | 2026-06-14 | 2026-07-19
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4664520 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151009806 | Completed | 23490 | 0 | 2026-06-14 | 2026-07-19
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4665096 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151044484 | Approved | 27000 | 0 | 2024-09-16
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4802324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150127386 | Completed | 23490 | 0 | 2025-03-24 | 2026-08-03
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/4862996 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105249869 | Completed | 27000 | 4200 | 2025-03-06 | 2026-10-18
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5148946 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105268461 | Approved | 27000 | 0 | 2025-02-20
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5156088 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145790395 | Ongoing | 27000 | 10800 | 2026-07-07
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5210287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105363839 | Approved | 27000 | 0 | 2025-03-15
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5243387 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105364913 | Completed | 23490 | 0 | 2026-06-14 | 2026-07-19
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5245210 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145701291 | Completed | 23490 | 0 | 2026-03-24 | 2026-08-03
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5517376 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145703832 | Approved | 27000 | 0 | 2025-03-12
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5524167 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147761640 | Completed | 23490 | 0 | 2026-06-14 | 2026-07-19
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004004/IF/IAY/5658084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105248148 | Completed | 23490 | 0 | 2026-03-24 | 2026-08-03
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035663662 — Ek BAGIYA MA KE NAAM SHG hajrat bilal bhuri bi | New | 0 | 0 | 2026-08-01
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664170 — Ek Bagiya ma ke naam bhuri bi Aaka husen SHG | Ongoing | 289911.82 | 38700 | 2026-08-11
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664171 — Ek Bagiya ma ke naam Bismilla bi hazrat bilal SHG | Ongoing | 288876.82 | 38700 | 2026-08-11
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664175 — Ek Bagiya ma ke naam Aaka husen SHG jenab bi | Approved | 0 | 0 | 2026-08-05
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664177 — Ek Bagiya ma ke naam khawaja garib nawaj SHG kallo bi | Approved | 0 | 0 | 2026-08-05
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664398 — Ek Bagiya ma ke naam sai aajivika SHG naphisa bi | Approved | 0 | 0 | 2026-08-05
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664399 — Ek bagiya ma ke naam sabana bi aaka husen SHG | Approved | 0 | 0 | 2026-08-05
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664400 — Ek bagiya ma ke naam koshar be hazrat bilal SHG | Approved | 0 | 0 | 2026-08-05
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004004/IF/VB/22012035664401 — Ek bagiya ma ke naam naragish be shahanshah aajivika SHG | Approved | 0 | 0 | 2026-08-05
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034819272 — cc road nali nirman bilu singh ke ghar se gordhan ke ghr ki aur | Approved | 0 | 0 | 2024-06-13
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034819273 — cc road nali nirman badri k ghr se tejram k ghr ki aur | Approved | 0 | 0 | 2024-06-13
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034841682 — CC ROAD PRADHAN MANTRI ROAD SE SAMSAN GHAT MUSAVADA | Physically Completed | 18000 | 0 | 2025-04-13 | 2026-07-30
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034841683 — CC ROAD HOLY TEKRA SE RAZAK KE GHAR TAK MUSAVDA | Physically Completed | 21000 | 0 | 2025-04-13 | 2026-07-21
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034846447 — CC ROAD BANESING KE GHAR SE MEHMUD KE GHAR TAK | Physically Completed | 96000 | 5400 | 2025-07-23 | 2026-07-30
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004004/RC/22012034847482 — C C ROAD MANJUR KHAN KE GHAR SE AAABID KHAN KE GHAR TAK MUSAWDA | Approved | 51000 | 0 | 2025-04-15
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004004/RS/22012035130681 — CC nalli nirman badri ke ghar se tej ram ke ghar ki aur 2 sides | Approved | 0 | 0 | 2024-08-26
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004004/RS/22012035130682 — RCC nani nirman anvar patel ke ghar se munna kha ke ghar ki aur | Approved | 0 | 0 | 2024-08-26
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004004/RS/22012035133480 — rcc nali nirman mohammad ke ghar se mukhya naale ki or | Approved | 0 | 0 | 2024-11-03
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722004004/WC/22012035225665 — water harvesting pond nijauddin ke khet ke pas | New | 0 | 0 | 2024-11-03
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722004004/WC/22012035225666 — water harvesting pond nijauddin ke khet ke pas | Approved | 0 | 0 | 2024-11-03
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722004004/WC/22012035225667 — water stablijation pond aslam ke khet ke pass vaale naale par | Approved | 0 | 0 | 2024-11-03
DHAR / DHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722004004/WC/22012035259877 — SANKANPOND | Approved | 0 | 0 | 2025-04-01