## Work List
Exported on: 2026-10-03 04:38:54
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: KHAIROD
Status: Physically Completed
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Centre Building for Community | Constr of Aganwadi | 1722004005/AV/22012034649113 — shantidham kherod gram panchyat | Physically Completed | 226381.46 | 0 | 2023-12-09 | 2026-07-21
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004005/RC/22012034841041 — CC ROAD RANJIT KE MAKAN SE ANUP KE MAKAN TAK | Physically Completed | 32000 | 0 | 2025-04-23 | 2026-07-21
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004005/RC/22012034841042 — CC ROAD PUNA DEVDA KE MAKAN SE MUNNA DEVDA KE MAKAN TAK | Physically Completed | 26000 | 0 | 2025-04-23 | 2026-07-21
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004005/RC/22012034847488 — CC ROAD DANGI DHARMSHALA SE CHARAT KE MAKAN TAK | Physically Completed | 28000 | 21300 | 2025-11-15 | 2026-09-06
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004005/RS/22012035127017 — nali nirman pradhanmantri puliya sw rameshwar gadi ke ghar ki aur | Physically Completed | 118000 | 0 | 2024-03-15 | 2026-07-21
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004005/RS/22012035136938 — NALI NIRMAN SANJAY KE MAKAN SE TALAB KI OR | Physically Completed | 21000 | 0 | 2025-07-02 | 2026-07-21
DHAR / DHAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004005/RS/22012035136939 — NALI NIRMAN HANUMAN MANDIR SE TALAB KI OR | Physically Completed | 15000 | 0 | 2026-06-13 | 2026-07-21