## Work List
Exported on: 2026-10-18 20:17:51
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: ANARAD
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Crematorium for Community / Construction of Crematorium for Community | Construction of Crematorium | 1722004024/AV/22012034401199 — Prathana sabha Kabrasthan par | Deleted | 200000 | 0 | 2019-03-11
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004024/AV/22012034515065 — Nali nirman Indra aawas Colony Se School tak Anarad | Completed | 212000 | 211600 | 2020-11-23 | 2021-12-11
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1722004024/AV/22012034564407 — Bondary wall Anarad | Deleted | 226319.83 | 0 | 2021-01-21
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of drain for coastal protection for Comm. / Construction of Storm Water drain for coastal protection for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004024/AV/22012034564408 — Roof Top water Harbesting | Deleted | 0 | 0 | 2021-01-21
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1722004024/AV/22012034565806 — Bouaradndary wall Nirman M S Anarad | Completed | 280249.76 | 271967 | 2021-05-25 | 2022-05-30
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1722004024/AV/22012034576340 — Dining Hall मिडिल स्कूल अनारद | Closed | 21925.39 | 0 | 2021-06-01
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1722004024/AV/22012034603327 — Dining Hall मिडिल स्कूल 2 अनारद | Deleted | 0 | 0 | 2021-06-01
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1722004024/AV/22012034603328 — डाइनिंग हाल मिडिल स्कूल 2 अनारद | Completed | 31669.14 | 25756 | 2021-10-29 | 2021-12-08
DHAR / DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Land Development / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004024/DP/ — dfgfdg | Deleted | 10100000 | 0 | 2006-10-16
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Sericulture- in Fields-Community / Block Plantation of Sericulture Trees in fields for Community | Plantation | 1722004024/DP/22012034584459 — Vasudha Vandan Plantation School Campus Anarad | Ongoing | 54564.94 | 27859 | 2023-08-24
DHAR / DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1722004024/DP/9926688946 — र्नि‍मल वाटि‍का 17 हि‍तग्राही अनारद | Completed | 3800 | 8490 | 2011-01-11 | 2010-08-02
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Flood Control and Protection | Drainage in Water Logged Areas / Drainage of Community Waterlogged Land | Works for Flood Control and Protection | 1722004024/FP/22012034202888 — drainage in water logged area | Completed | 49000 | 48795 | 2015-10-27 | 2017-03-03
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1822 — निर्मल वाटिका दिनेश रामचंद्र | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1823 — निर्मल वाटिका फूलीबाई पाहडसिह | Completed | 4280 | 1327.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1824 — निर्मल वाटिका रमेश वरदीचंद | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1825 — निर्मल वाटिका मुकेश भेरू | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1826 — निर्मल वाटिका कमल तोलाराम | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1827 — निर्मल वाटिका रामकुवरबाई राजाराम | Completed | 4280 | 1327.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1828 — निर्मल वाटिका कमलाबाई भगवान | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1829 — निर्मल वाटिका नारायण गणपत | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1830 — निर्मल वाटिका बद्री नानुराम | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1831 — निर्मल वाटिका नवाबशाह रोशनशाह | Completed | 4280 | 1327.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1832 — निर्मल वाटिका गोबाजी धूलाजी | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1833 — निर्मल वाटिका सुखराम गणपत | Completed | 4280 | 1327.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1834 — निर्मल वाटिका रणजीत बोन्‍दा | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1835 — निर्मल वाटिका शाबीर सुलेमान | Completed | 4280 | 1327.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1836 — निर्मल वाटिका अम्‍बाराम कालु | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1837 — निर्मल वाटिका नारायण गोबाजी | Completed | 4280 | 1327.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1838 — निर्मल वाटिका सोभाबाई कालु | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1839 — निर्मल वाटिका कैलाश नानुराम | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2012-2013 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/IF/1840 — निर्मल वाटिका नन्‍दकिशोर रामरतन | Completed | 4280 | 2911.58 | 2012-10-30 | 2012-12-08
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004024/IF/22012034355611 — वरक्षारोपन समुदायिक शासकीय विघालय प्रांगण अनारद | Completed | 335000 | 331912.6 | 2017-06-30 | 2022-11-22
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004024/IF/22012034355613 — Vrakchharopan | Deleted | 335000 | 0 | 2017-06-23
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004024/IF/22012035364047 — indivisual khet talab nirman sumitrabai dhansingh | Ongoing | 450885.64 | 434505 | 2025-04-25
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004024/IF/22012035451518 — indivisual khet talab nirman aashish pita ratanlal anarad | New | 0 | 0 | 2025-04-14
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004024/IF/22012035451522 — indivisual khet talab nirman aashish pita ratanlal anarad | Ongoing | 450885.64 | 422874 | 2025-05-03
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722004024/IF/22012035582451 — Construction of Demo Khet Talab | Approved | 359000 | 0 | 2025-04-01
DHAR / DHAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Cattle Shed / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722004024/IF/9926715943 — पशु निर्माण श्‍ेाड कालु भेराजी | Deleted | 72000 | 0 | 2014-01-26
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993681175 — Indra AAwas Mana bai_Munna lal | Deleted | 0 | 0 | 2015-08-15
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/9993681789 — Indra aawas mana bai munna lal | Deleted | 14310 | 0 | 2015-10-18
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/9993681791 — Indra aawas kamla bai | Deleted | 14310 | 0 | 2015-08-18
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/9993681929 — indra aawas amvaram dhul ji | Deleted | 14310 | 0 | 2015-10-20
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993693286 — C m aawas badri RAnchod | Deleted | 14310 | 0 | 2015-12-05
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993693289 — C M aawas santosh madan lal | Completed | 14310 | 14191 | 2015-12-19 | 2016-08-20
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993693291 — C M AAwas Sanjay Rameshwar | Deleted | 14310 | 0 | 2015-12-05
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993693292 — C M AAwas MAhendra AmarSeeng | Deleted | 14310 | 0 | 2015-12-05
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993693293 — C M AAwas RAmkanya Ratan lal | Completed | 14310 | 14191 | 2015-12-20 | 2016-07-22
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993693297 — C M aawas GUlab seeng baje seeng | Completed | 14310 | 14120 | 2015-12-20 | 2016-07-22
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/9993720028 — इन्दिरा आवास कमला बाई भगवान ग्राम पंचायत अनारद | Completed | 14310 | 14028 | 2016-05-28 | 2016-12-01
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/9993720035 — इन्दिरा आवास माना बाई मुन्नालाल ग्राम पंचायत अनारद | Completed | 14310 | 13827.6 | 2016-05-28 | 2017-02-02
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/9993720037 — इन्दिरा आवास गोबाजी धूल जी ग्राम पंचायत अनारद | Completed | 14310 | 14028 | 2016-11-03 | 2017-01-10
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743325 — c M Aawas Mukesh Manohar | Deleted | 14310 | 0 | 2016-05-27
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743328 — मुख्यमंत्री ग्रामीण आवास मिशन कैलाश भेराजी ग्राम पंचायत अनारद | Completed | 14310 | 14028 | 2016-07-14 | 2017-02-02
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743330 — मुख्यमंत्री ग्रामीण आवास मिशन रतनलाल रामजी ग्राम पंचायत अनारद | Completed | 14310 | 13026 | 2016-06-09 | 2017-06-05
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743332 — मुख्यमंत्री ग्रामीण आवास मिशन मुकेश कालु ग्राम पंचायत अनारद | Completed | 14310 | 14028 | 2016-06-09 | 2017-02-02
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743334 — मुख्यमंत्री ग्रामीण आवास गेंदालाल घीसाजी ग्राम पंचायत अनारद | Completed | 14310 | 14028 | 2016-06-09 | 2016-12-01
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743336 — c M Aawas Tola Ram bhera ji | Completed | 14310 | 14448 | 2017-05-15 | 2018-01-18
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743338 — मुख्यमंत्री ग्रामीण आवास मिशन कालु भेराजी ग्राम पंचायत अनारद | Completed | 14310 | 14028 | 2016-06-09 | 2016-12-01
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004024/IF/9993743340 — c M Aawasbabu lal Gheesa ji | Deleted | 14310 | 0 | 2016-05-25
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/197942 — Construction of IAY House -IAY REG. NO. MP-22-004-024-001/88 | Approved | 27000 | 0 | 2016-03-11
DHAR / DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/2590236 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4318237 | Completed | 17100 | 17100 | 2020-06-24 | 2021-01-26
DHAR / DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/2590719 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4984362 | Completed | 17100 | 17100 | 2020-06-24 | 2021-01-20
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/3701723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113534496 | Completed | 18360 | 18360 | 2022-05-24 | 2022-11-28
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/370296 — Construction of IAY House -IAY REG. NO. MP1223550 | Completed | 15030 | 14460 | 2017-01-25 | 2017-09-01
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/370788 — Construction of IAY House -IAY REG. NO. MP1232066 | Completed | 15030 | 15300 | 2017-02-09 | 2018-01-10
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/371623 — Construction of IAY House -IAY REG. NO. MP1252468 | Completed | 15030 | 15325 | 2017-02-09 | 2018-01-10
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/373081 — Construction of IAY House -IAY REG. NO. MP1309822 | Completed | 15030 | 15574 | 2017-01-25 | 2017-08-09
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/3786757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125164009 | Completed | 18360 | 18156 | 2022-05-24 | 2022-11-25
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/3798157 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113763355 | Completed | 18360 | 18360 | 2022-08-14 | 2022-12-14
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/3881152 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129754591 | Completed | 18360 | 18360 | 2022-05-24 | 2022-11-28
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/4241048 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103962089 | Completed | 18360 | 16116 | 2022-07-15 | 2023-07-06
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/4255761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138911854 | Completed | 18360 | 18360 | 2022-08-10 | 2022-11-28
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/4543324 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105066481 | Completed | 23490 | 21177 | 2024-09-28 | 2026-02-16
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/4544375 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105074646 | Completed | 21870 | 21855 | 2024-09-28 | 2025-04-04
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/4573296 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117203329 | Completed | 23490 | 21384 | 2024-09-28 | 2026-02-17
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/511211 — Construction of IAY House -IAY REG. NO. MP2395594 | Completed | 15030 | 15128 | 2017-02-09 | 2017-09-20
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/513831 — Construction of IAY House -IAY REG. NO. MP2427043 | Completed | 15030 | 17536 | 2017-02-09 | 2017-09-21
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/514022 — Construction of IAY House -IAY REG. NO. MP2429681 | Completed | 15030 | 15183 | 2017-02-09 | 2018-03-31
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/515147 — Construction of IAY House -IAY REG. NO. MP2451070 | Completed | 15030 | 15128 | 2017-02-09 | 2017-09-10
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5154804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129758104 | Physically Completed | 23490 | 20358 | 2025-05-23 | 2026-05-22
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5155159 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106255454 | Physically Completed | 23490 | 22446 | 2025-08-21 | 2026-06-02
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5158429 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117203122 | Physically Completed | 23490 | 22968 | 2025-04-12 | 2026-06-22
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/516121 — Construction of IAY House -IAY REG. NO. MP2469213 | Completed | 15030 | 16242 | 2017-02-09 | 2017-08-08
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5162196 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP131034946 | Ongoing | 27000 | 16792 | 2025-08-05
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5162757 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125163002 | Completed | 23490 | 22968 | 2025-05-23 | 2026-02-17
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5166937 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105067353 | Physically Completed | 23490 | 6786 | 2025-04-12 | 2026-05-22
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5168540 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113763512 | Completed | 23490 | 17226 | 2025-04-19 | 2026-07-26
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5168966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138911752 | Approved | 27000 | 0 | 2025-02-16
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5172394 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117206227 | Approved | 27000 | 0 | 2025-02-17
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5176765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138911782 | Approved | 27000 | 0 | 2025-02-16
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5178835 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP125149075 | Completed | 27000 | 23409 | 2025-05-23 | 2026-09-28
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5179306 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117204160 | Completed | 27000 | 13806 | 2025-04-12 | 2026-09-28
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5181826 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117203916 | Completed | 23490 | 15138 | 2026-01-22 | 2026-07-26
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5184062 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP138911812 | Completed | 27000 | 20226 | 2025-04-12 | 2026-09-29
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5185137 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP140411184 | Completed | 23490 | 23490 | 2025-04-12 | 2025-10-29
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5186767 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118384864 | Completed | 27000 | 23616 | 2026-05-24 | 2026-09-28
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5187364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113764652 | Physically Completed | 23490 | 21924 | 2025-08-05 | 2026-02-14
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5188765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105065948 | Approved | 27000 | 0 | 2025-02-18
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5197704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106535729 | Approved | 27000 | 0 | 2025-02-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5198877 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP122798194 | Physically Completed | 23490 | 13833 | 2025-09-26 | 2026-06-21
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5201289 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106535715 | Completed | 23490 | 15108 | 2026-05-24 | 2026-10-13
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5203017 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP141350322 | Approved | 27000 | 0 | 2025-02-17
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5205333 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113764306 | Physically Completed | 23490 | 23229 | 2025-08-21 | 2026-06-02
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5205736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106535549 | Physically Completed | 23490 | 17226 | 2025-05-23 | 2026-05-22
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5205772 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129755172 | Approved | 27000 | 0 | 2025-02-19
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5206025 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130555323 | Approved | 27000 | 0 | 2025-02-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5207988 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103955341 | Physically Completed | 23490 | 21924 | 2025-12-22 | 2026-04-19
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5209432 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117205574 | Completed | 27000 | 21708 | 2026-05-24 | 2026-10-13
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5212423 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129757183 | Approved | 27000 | 0 | 2025-02-19
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5213632 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP129754943 | Completed | 23490 | 23229 | 2025-04-12 | 2025-10-29
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5217499 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113763685 | Approved | 27000 | 0 | 2025-02-17
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5217931 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP100803978 | Ongoing | 27000 | 10464 | 2025-04-12
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5227180 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117551788 | Approved | 27000 | 0 | 2025-02-18
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5228862 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117204550 | Approved | 27000 | 0 | 2025-02-16
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5229283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113763990 | Completed | 23490 | 23490 | 2025-05-23 | 2026-02-23
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5230067 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105066810 | Completed | 23490 | 22707 | 2025-04-19 | 2026-07-26
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5234671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117206258 | Approved | 27000 | 0 | 2025-02-19
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5236933 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105063175 | Physically Completed | 23490 | 21924 | 2025-08-05 | 2026-05-22
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5239144 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117206194 | Approved | 27000 | 0 | 2025-02-18
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5239255 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105062730 | Approved | 27000 | 0 | 2025-02-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5239747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106535603 | Ongoing | 27000 | 14616 | 2025-12-22
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5244529 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105064845 | Approved | 27000 | 0 | 2025-02-28
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/5245072 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117203598 | Physically Completed | 23490 | 16965 | 2025-05-23 | 2026-03-29
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5859492 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105065386 | Completed | 23490 | 5700 | 2026-06-03 | 2026-09-28
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/5881350 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106535340 | Completed | 27000 | 22908 | 2026-05-24 | 2026-10-13
DHAR / DHAR | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/6167737 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106535401 | Completed | 27000 | 21708 | 2026-05-24 | 2026-10-13
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/747547 — Construction of IAY House -IAY REG. NO. MP2454203 | Completed | 15030 | 14448 | 2017-08-28 | 2018-02-10
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004024/IF/IAY/748709 — Construction of IAY House -IAY REG. NO. MP2490687 | Approved | 27000 | 0 | 2017-03-21
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/748710 — Construction of IAY House -IAY REG. NO. MP2490733 | Completed | 15030 | 15308 | 2017-05-15 | 2018-01-10
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/748840 — Construction of IAY House -IAY REG. NO. MP2497090 | Completed | 15030 | 14792 | 2017-04-29 | 2018-02-10
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/749016 — Construction of IAY House -IAY REG. NO. MP2504033 | Completed | 15030 | 14448 | 2017-09-05 | 2018-01-10
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004024/IF/IAY/776671 — Construction of IAY House -IAY REG. NO. MP3774960 | Completed | 15030 | 15136 | 2017-07-25 | 2017-11-25
DHAR / DHAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004024/LD/22012034241211 — शा . माध्यमिक विध्यालय एवं आंगनवाड़ी के सामने मैदान समतलीकरण | Completed | 449000 | 224113 | 2015-12-06 | 2017-03-30
DHAR / DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722004024/LD/22012034294559 — शमशान मैदान समतलीकरण अनारद | Deleted | 82000 | 0 | 2016-12-06
DHAR / DHAR | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Land Leveling / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004024/LD/22012034304988 — shamshan maidan samtali karan | Deleted | 82000 | 0 | 2017-03-06
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722004024/LD/22012034519637 — Goushala | Deleted | 0 | 0 | 2020-04-14
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722004024/LD/22012034523777 — Bhumi samtalikaran Uchit mulya ki Socity k pas Anarad | Deleted | 0 | 0 | 2020-04-14
DHAR / DHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004024/LD/59 — ग्रामीण कीडांगन खैल मैदान समतलीकरण प्रामा अनारद | Completed | 402000 | 394740 | 2012-01-13 | 2012-07-13
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/ — Road Construction | Deleted | 500000 | 0 | 2006-12-08
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Metal First coat / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/1 — road construction | Completed | 500000 | 0 | 2006-10-02 | 2013-10-31
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004024/RC/2 — अर्थवर्क | Completed | 378000 | 184 | 2006-11-02 | 2013-10-31
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034182228 — सीमेन्‍ट कांक्रीट आंतरिक मार्ग मुख्‍य मार्ग से कन्‍हैया के घर तक एवं महेन्‍द्र सौलंकी के घर तक अनारद | Completed | 147000 | 146924 | 2013-09-14 | 2013-12-10
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034190848 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण मुख्‍य मार्ग | Deleted | 156000 | 0 | 2013-08-15
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034190877 — सीमेन्‍ट क्राकीट आंतरीक मार्ग बालु के धर से मुख्‍य | Completed | 207000 | 207042 | 2013-11-14 | 2014-03-05
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034190882 — सीमेंन्‍ट क्राकीट आंतरीक मार्ग निर्माण बालु के धर | Deleted | 207300 | 0 | 2013-05-15
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034203776 — cement concrete interanl road mukh marg se balu ke | Completed | 156000 | 155577 | 2014-02-13 | 2014-03-26
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034204629 — cement concrete interanal road munni ke ghar se ah | Completed | 90000 | 90312 | 2014-03-06 | 2014-03-26
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034206884 — मुक्ति धाम रोड | Completed | 100000 | 100626 | 2014-03-06 | 2014-10-29
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034212167 — सिमेट कक्रिट आन्त् रिक मार्ग राम मन्दिर से बालु | Completed | 64000 | 63642 | 2014-03-06 | 2014-09-26
DHAR / DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034217605 — सिमेन्‍ट काक्रीट अम्‍बाराम के घर से हुसैना के घर त | Completed | 29000 | 28956 | 2014-05-08 | 2014-05-14
DHAR / DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034229081 — सीमेन्ट क्रार्कीट आं.मा.(रजाककेघरसेकैलाशघरतक) | Completed | 140000 | 140109 | 2014-09-27 | 2014-11-07
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034266186 — cement conrete panchat ke samne | Completed | 105000 | 104280 | 2015-06-12 | 2017-04-17
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/22012034300714 — Khet road | Deleted | 0 | 0 | 2016-01-26
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034324529 — c c road | Deleted | 0 | 0 | 2017-04-01
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034339997 — सी सी रोड कैलाश के घर से शमशान की और (परफारमेंट ग्रांट व मनरेगा ) | Completed | 197000 | 196676 | 2018-01-29 | 2020-07-02
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/22012034371340 — khet sadak | Deleted | 0 | 0 | 2017-10-02
DHAR / DHAR | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/22012034377341 — khet road Ratlam main road se narayan ke khet tak | Deleted | 224000 | 0 | 2019-04-04
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/22012034528924 — Khet road Yasin kha k khet se Mangu bai k khet tak Anarad | Completed | 1417725.38 | 1412636.28 | 2020-08-06 | 2023-07-06
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034582729 — C c road nirman up swasthya kendra se jamat khane tak | Closed | 51000 | 0 | 2022-12-08
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/22012034606544 — Khet Sadak | Deleted | 0 | 0 | 2022-01-01
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Interlocking block/tiles Roads for Comm / Construction of Inter-locking cement block/tiles Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034622390 — Cement Concrete Paver Road Primary School se Aaganwadi Cluster Bhavan Tak Anarad | Completed | 11000 | 10608 | 2022-12-06 | 2024-05-21
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034665719 — सीमेन्‍ट कांक्रीट रोड निर्माण आंगनवाडी भवन क्र.-1 से जमातखाने तक अनारद | Completed | 36000 | 33775 | 2023-10-09 | 2024-06-11
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034833226 — C C ROAD NIYAY KHA KE GHAR SE RAKESH KANJI KE GHAR TAK INDIRA AWASH COLONY | Deleted | 72000 | 0 | 2024-08-15
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034833477 — indira awas basti me niyaj khan ke ghar se rakesh kanaji ke ghar tak cc road | Completed | 72000 | 71999.4 | 2025-01-13 | 2025-02-11
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034835878 — cc road sah nali nirman indira awas basti me rakesh ke ghar se tolaram ke ghar tak | Completed | 20000 | 18711 | 2025-02-10 | 2026-10-16
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034846809 — Construction of Demo Cement Concrete Road | Approved | 6283 | 0 | 2025-04-01
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004024/RC/22012034846850 — Construction of Cement Concret Raod For Demo | Approved | 6300 | 0 | 2025-04-01
DHAR / DHAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004024/RC/25378 — ग्रेवल मार्ग गांव से शमशानघाट अनारद | Completed | 0 | 300128 | 2009-05-21 | 2009-09-25
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/25416 — गेवल मार्ग | Deleted | 0 | 0 | 2006-04-14
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/25417 — गेवल मार्ग | Deleted | 0 | 0 | 2006-04-14
DHAR / DHAR | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004024/RC/25542 — मुरम सडक निर्माण आदिवासी मोहल्‍ले से गरडावद मार्ग भाग 2 अनारद | Completed | 380000 | 330830 | 2010-04-05 | 2010-04-05
DHAR / DHAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004024/RC/25610 — आंतरिक मुरम सडक निर्माण मुख्‍य मार्ग से बद्री पटेल के खेत तक अनारद | Completed | 243000 | 216240 | 2011-06-19 | 2012-05-18
DHAR / DHAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004024/RC/25709 — आंतरिक मुरम सडक मुरम सडक से जुझार जी तक अनारद | Deleted | 252000 | 0 | 2011-08-02
DHAR / DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004024/RC/25763 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण भेरू के घर से सीताराम के घर तक अनारद | Completed | 120000 | 43236 | 2012-12-25 | 2013-03-28
DHAR / DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/25798 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण शंकर मंदिर से घनश्‍याम पटेल के घर तक अनारद | Completed | 190000 | 74448 | 2013-01-10 | 2013-03-28
DHAR / DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004024/RC/25799 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण शंकर मंदिर से घनश्‍याम पटेल के घर तक भाग 2 अनारद | Completed | 48000 | 38268 | 2013-01-03 | 2013-03-28
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004024/RC/43 — ग्रेवल रोड अनारद | Completed | 200000 | 326120 | 2006-04-10 | 2007-02-15
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004024/RC/804 — ग्रेवल मार्ग अनारद II | Completed | 500000 | 81000 | 2006-12-26 | 2008-03-01
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004024/RS/22012034253398 — निर्मल भारत अन्‍तर्गत 10 शौचालय निर्माण 71,123,12- | Deleted | 54000 | 0 | 2014-01-26
DHAR / DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004024/RS/22012034257393 — निर्मल भारत अन्‍तर्गत10 शौचालय निर्माण 2 | Deleted | 54000 | 0 | 2014-04-14
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722004024/RS/22012034508521 — Covering of drain Anarad | Deleted | 0 | 0 | 2021-01-21
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722004024/RS/22012034536710 — SBM SCP Samudayik composed pit ANARAD | Closed | 47000.06 | 0 | 2021-06-01
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034536737 — SBM SSP Samudayik SOAK pit 10 ANARAD | Closed | 60000.77 | 0 | 2021-06-01
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034575228 — नाली निर्माण अगनवाड़ी भवन से मिडिल स्कूल तक अनारद | Deleted | 0 | 0 | 2021-04-25
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034586124 — nali nirman aaganwadi bhavan se midil school tak anarad | Completed | 143000 | 141855 | 2021-11-08 | 2022-03-14
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722004024/RS/22012034634263 — Construction of Samudaik Swachhata Parisar Talai Anarad | Completed | 44000 | 43853 | 2022-05-10 | 2022-09-30
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034674970 — Cement Concrete Nali Niram Purani Panchayat Bhavan se Kalabai Lalji ke Ghar tak Anarad | Closed | 0 | 0 | 2022-09-01
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034674971 — Cement Concrete Nali Niram Purani Panchayat Bhavan se Kalabai Lalji ke Ghar tak Anarad | Ongoing | 12000 | 9792 | 2022-11-29
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034674972 — Cement Concrete Nali Niram Yatri Pratikshalay se Pradhan Mantri Road ki Nali tak Anarad | Completed | 9000 | 8976 | 2022-11-25 | 2023-07-24
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034674973 — Cement Concrete Nali Niram Nand Kishore ke Ghar se Dhar Ratlan Main Road tak Anarad | Completed | 9000 | 8568 | 2022-11-29 | 2023-07-24
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034690368 — R.C.C. Nali Nirman Mohan Thakur Ke Ghar Se Hiralal Yadav ke Plot Tak Anarad | Deleted | 0 | 0 | 2023-01-25
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034690369 — R.C.C. Nali Nirman Mohan Thakur Ke Ghar Se Hiralal Yadav ke Plot Tak Anarad | Physically Completed | 36000 | 27642 | 2023-02-27 | 2026-06-22
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034701225 — R.C.C. Nali Nirman Hiralal Yadav ke Plot se Akalim Kha ke Ghar Tak Anarad | Completed | 55000 | 54145 | 2023-09-01 | 2023-11-29
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012034701229 — R.C.C. Pipe Drainage Nirman Madhymik Vidhyalaya ke Corner se Masjjit wale Nale Tak Anarad | Completed | 68000 | 67842 | 2023-09-08 | 2024-07-09
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012035122764 — Rcc Nali Nirman | Deleted | 0 | 0 | 2024-01-25
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004024/RS/22012035125063 — आर सी सी नाली निर्माण विक्रम यादव के घर से दिलीप डोड के प्‍लाट तक अनारद | Completed | 64000 | 63948 | 2024-03-14 | 2024-06-23
DHAR / DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Bharat Nirman Sewa Kendra | New Construction / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722004024/SK/3111 — Bharat Nirman Rajeev Gandhi Sewa Kendra,ANARAD | Completed | 1485000 | 999857.5 | 2014-06-28 | 2015-12-03
DHAR / DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/100 — नि‍स्‍तार तालाब | Deleted | 0 | 0 | 2006-04-05
DHAR / DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/101 — Nistari Talab | Deleted | 0 | 0 | 2006-05-02
DHAR / DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/22012034355459 — Bori bandhan pachalana road ke pas | Deleted | 16000 | 0 | 2017-09-15
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/WC/22012034381998 — bhu sankalan pond | Deleted | 0 | 0 | 2017-10-02
DHAR / DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004024/WC/22012034438031 — Bhu sankalan | Deleted | 0 | 0 | 2019-01-26
DHAR / DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Repair & maint of Mini Percolation Tank for Comm / Repair and maintenance of Mini Percolation Tank for Community | Repair & maint of Percolation Tank | 1722004024/WC/22012034441789 — Bhu sankalan pond Pachala road | Deleted | 288000 | 0 | 2019-01-26
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034483398 — Recharge pit School me | Completed | 5133.46 | 352 | 2019-08-23 | 2021-01-26
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034483400 — REcharge pit in shamshan | Completed | 5133.46 | 176 | 2019-08-24 | 2021-01-26
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034485262 — Recharge pit P S school Anarad | Deleted | 0 | 0 | 2019-08-15
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034485264 — Recharge pit in M S school Anarad | Completed | 5133.46 | 352 | 2019-08-23 | 2021-01-26
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034485265 — REcharge pit in Shamshan Anarad | Deleted | 0 | 0 | 2019-08-15
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034485997 — Recharge pit Nandu ke ghar ke pas | Deleted | 0 | 0 | 2019-08-15
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034485998 — recharge pit Ramesh ke ghar ke samne | Deleted | 0 | 0 | 2019-08-15
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034486000 — Recharge pit Noshad ke ghar ke samne | Completed | 5133.46 | 176 | 2019-08-24 | 2021-02-25
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034518434 — sankan pond nirman anarad | Deleted | 0 | 0 | 2019-10-02
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034543087 — Bhu sankalan pond Pachala road par 20/21 | Completed | 304239.18 | 297960 | 2021-02-16 | 2021-08-15
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034543088 — Bhu sankalan pond Pachala road par 20/21 | Deleted | 0 | 0 | 2020-04-01
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034549660 — bhu sanklan pond malgaon kaakad | Closed | 377415.75 | 0 | 2020-04-14
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/22012034619063 — checkdam cum Nala trenching | Deleted | 0 | 0 | 2021-01-21
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034619064 — Bhu sankalan pond Vhapata nursary anarad | Deleted | 0 | 0 | 2021-01-21
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/22012034619140 — Checkdam cum nala trenching Chapada nursary Anarad | Deleted | 0 | 0 | 2021-01-21
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034619143 — Bhu sankalan pond Chhapata nursary anarad | Deleted | 0 | 0 | 2021-01-21
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034634134 — CTRA Bhu sankalan Pond Chhapta Nursary Anarad | Completed | 313569.64 | 273239.2 | 2021-04-12 | 2023-09-20
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/22012034635119 — CTRA Check dam With Nala trenching Anarad | Physically Completed | 629982.37 | 5404 | 2021-04-08 | 2021-10-31
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004024/WC/22012034635891 — CTRA Nala trenching PM road se Mangu bai k khet tak anarad | Completed | 284985 | 219730.22 | 2021-04-12 | 2021-12-11
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004024/WC/22012034638220 — Roof Top water Harbestin AAnganwadi Bhavan anaradg | Closed | 5400 | 0 | 2021-04-01
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004024/WC/22012034638225 — CTRA Roof Top water Harbesting School Building Anarad | Completed | 5400 | 3667 | 2021-04-27 | 2022-04-06
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004024/WC/22012034643714 — CTRA RWH Anganwadi anarad | Deleted | 0 | 0 | 2021-04-01
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004024/WC/22012034643722 — CTRA RWH Anganwadi anarad | Completed | 5400 | 386 | 2021-04-27 | 2022-04-06
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004024/WC/22012034643744 — CTRA RWH school Bhavan anarad | Completed | 5400 | 193 | 2021-04-27 | 2022-04-06
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678826 — CTRA Recharge pit Nale me NO1 anarad | Completed | 13133.77 | 579 | 2021-05-04 | 2022-04-04
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678836 — CTRA Recharge pit Nale me no2 anarad | Completed | 13133.77 | 193 | 2021-05-04 | 2022-04-04
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678848 — CTRA Recharge pit Nale me n03 anarad | Completed | 13133.77 | 193 | 2021-05-04 | 2022-04-04
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678859 — CTRA Recharge pit Nale me No4 anarad | Physically Completed | 13133.77 | 193 | 2021-05-04 | 2021-06-18
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678868 — CTRA Recharge Pit no5 anarad | Physically Completed | 13133.77 | 193 | 2021-05-04 | 2021-06-18
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678892 — CTRA REcharge pit no 6 anarad | Closed | 13133.77 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678949 — CTRA REcharge pit no 6 anarad | Closed | 13133.77 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678960 — CTRA Recharge pit no 7 Anarad | Physically Completed | 13133.77 | 193 | 2021-05-04 | 2021-06-18
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678969 — CTRA REcharge pit Nale me no 8 anarad | Closed | 13151.82 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004024/WC/22012034678977 — CTRA Recharge pit No 9 anarad | Closed | 13422.31 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004024/WC/22012034792931 — SBM ISP UNIT- 50 ANARAD | Closed | 99999.74 | 0 | 2021-06-01
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Raising of Nursery for Community / Raising of Nursery for Community | Nursery Development | 1722004024/WC/22012034809205 — MAA KI BAGIYA M S ANARAD | Closed | 11397.42 | 0 | 2021-08-01
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004024/WC/22012034908332 — Nalha Trenching | Deleted | 0 | 0 | 2022-01-01
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034908823 — Sankan Pond Anarad | Deleted | 0 | 0 | 2022-01-01
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034908825 — Khet Talab | Deleted | 0 | 0 | 2022-01-01
DHAR / DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034943242 — Nalha Trenching of Nursury wala Nalha Anarad | Completed | 489550.58 | 232091.73 | 2022-04-19 | 2024-06-17
DHAR / DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004024/WC/22012034982423 — Sankan Pond Nirman Ramchandra Bhakar ke Khet ke Pas Anarad | Closed | 593868.73 | 0 | 2022-04-14
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004024/WC/22012035100013 — Nalha Trenching Malgaon Nursury se Pachalana Talab ki Puliya tak Anarad | Completed | 253914.72 | 224408.36 | 2023-12-18 | 2026-02-17
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pit for Community | Construction of Recharge Pits | 1722004024/WC/22012035162616 — नाला ट्रांचिंग पंचायत भवन के पीछे | New | 0 | 0 | 2024-01-25
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004024/WC/22012035221442 — नाला ट्रेंचिंग रतन डोड के खेत से प्रधानमंत्री रोड की पुलिया तक अनारद | Completed | 155944.92 | 129762 | 2024-10-09 | 2025-04-22
DHAR / DHAR | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/22012035318536 — Construction of Stap Dam For Demo | Approved | 50000 | 0 | 2025-04-01
DHAR / DHAR | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/40 — भेरू भागीरथ खेत तालाब अनारद | Completed | 0 | 0 | 2006-06-11 | 2008-02-02
DHAR / DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/4001 — तालाब गहरीकरण अनारद | Completed | 0 | 16830 | 2008-01-07 | 2008-06-03
DHAR / DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004024/WC/4067 — जल ग्रहरण संरचना कार्य अनारद | Completed | 0 | 78000 | 2010-05-07 | 2010-08-29
DHAR / DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/41 — गंगाराम धन्‍नाजी खेत तालाब अनारद | Completed | 0 | 0 | 2008-01-24 | 2008-02-02
DHAR / DHAR | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004024/WC/4179 — जल संग्रहण संरचना भाग 2 अनारद | Completed | 135000 | 127512 | 2012-06-12 | 2012-07-13
DHAR / DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004024/WC/9993621679 — जल संग्रहण संरचना अनारद | Completed | 209000 | 149748 | 2011-01-22 | 2012-07-20
DHAR / DHAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004024/WC/9993629610 — जल संग्रहण संरचना | Completed | 110000 | 91980 | 2013-06-06 | 2013-06-26
DHAR / DHAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004024/WC/9993629612 — जल संग्रहण संरचना अनारद | Completed | 146000 | 111836 | 2013-06-15 | 2013-07-25
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/WC/9993660678 — जल सग्रहना सरचना पचलाना रोड पर | Completed | 352000 | 149619 | 2015-12-05 | 2016-10-10
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004024/WC/9993667870 — Jal sangran saranchana | Deleted | 0 | 0 | 2016-01-26
DHAR / DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722004024/WH/19961245 — Repairing of Nistar talav | Completed | 391000 | 384881.2 | 2017-06-03 | 2021-12-11
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Rejuvenation of Pond for Community | Repair & maint of Pond/ Tank | 1722004024/WH/22012034939654 — Inlate Chenal Trenching Bada Talab Anarad | Deleted | 0 | 0 | 2024-06-07
DHAR / DHAR | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004025/RC/ — road cons | Deleted | 500000 | 0 | 2006-10-02