## Work List
Exported on: 2026-10-12 19:10:18
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: PIPALYA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1722004044/DP/22012034588890 — Basudha Bandhan M S Pipalya | Physically Completed | 55847.4 | 0 | 2023-08-15 | 2026-08-03
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in fields for Community | Plantation | 1722004044/DP/22012034619181 — ग्राम पिपल्‍या कब्रिस्‍तान व पिपल्‍या कालोनी कब्रिस्‍तान में संयुक्‍त वृृक्षारोपण कार्य | Ongoing | 347941.98 | 76500 | 2024-08-04
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Line Plantation of Horticulture Trees for Community | Plantation | 1722004044/DP/22012034628229 — नवीन माध्‍यमिक शाला परसिर पिपल्‍या में मॉ की बगिया निर्माण कार्य पिपल्‍या | Approved | 52985.86 | 0 | 2024-09-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004044/IF/22012035599434 — EK BAGIYA MAA SHG RAHEM AAJIVGIKA SHEHNAZ SALIM | Ongoing | 261589.03 | 16800 | 2025-08-29
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004044/IF/22012035599436 — EK BAGIYA MAA SHG RAHEM AAJIVGIKA AKOLA BEE | Ongoing | 262063.63 | 0 | 2025-08-29
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004044/IF/22012035599747 — EK BAGIYA MAA SHG RAHEM AAJIVGIKA SHEHNAZ YUNUSH | New | 0 | 0 | 2025-08-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individual | Plantation | 1722004044/IF/22012035599749 — EK BAGIYA MAA SHG RAHEM AAJIVGIKA SHEHNAZ YUNUSH | Ongoing | 262063.63 | 22230 | 2025-08-29
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722004044/IF/IAY/4944200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115806449 | Approved | 27000 | 0 | 2025-02-23
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004044/IF/IAY/693112 — Construction of IAY House -IAY REG. NO. MP1332854 | Approved | 27000 | 0 | 2017-03-21
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House for Individual | Rural Housing | 1722004044/IF/IAY/704040 — Construction of IAY House -IAY REG. NO. MP1486948 | Approved | 27000 | 0 | 2017-03-21
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004044/RC/22012034838502 — cc road nirman sah nali rammandie se ram ke ghar tak | Ongoing | 66000 | 7200 | 2025-04-15
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004044/RC/22012034838503 — cc road nirman ramsingh ke ghar se lalji ke ghar tak pipliya | Completed | 23000 | 0 | 2025-03-18 | 2026-07-26
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004044/RC/22012034847209 — cc road nirman masjid ke samne pipalya | Completed | 13000 | 0 | 2025-08-07 | 2026-07-26
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004044/RC/22012034847213 — cc road nirman raees ke ghar se gani mohhamad ke ghar tak pipalya | Completed | 52000 | 0 | 2025-08-07 | 2026-07-26
DHAR / DHAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722004044/RC/22012034853684 — cc road nirman main road se samshan ghat tak pipalya | Completed | 45000 | 0 | 2026-05-19 | 2026-07-26
DHAR / DHAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004044/RS/22012035139161 — naali nirman nat mohalla pipliya | Ongoing | 17100 | 4046 | 2026-06-17
DHAR / DHAR | 2026-2027 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Masonry Greywater Drain for Community | Solid and Liquid Waste Management | 1722004044/RS/22012035139543 — naali nirman masjid se aanganwadi tak pipalya | Completed | 13200 | 0 | 2026-05-19 | 2026-08-31
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Staggered Trench for Community / Construction of Staggered Contour Trench for Community | Construction of Trench | 1722004044/WC/22012035164032 — Bhu Sanklanpond | New | 0 | 0 | 2024-01-02
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood or Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722004044/WC/22012035164252 — Nalha Trenching | New | 0 | 0 | 2024-01-27