## Work List
Exported on: 2026-09-06 19:48:54
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: BAYKHEDA
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004039/IF/IAY/374890 — Construction of IAY House -IAY REG. NO. MP1400466 | Completed | 15030 | 14971 | 2017-02-01 | 2018-08-27
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004039/IF/IAY/506651 — Construction of IAY House -IAY REG. NO. MP2342759 | Completed | 15030 | 13635 | 2017-02-01 | 2017-12-10
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004039/IF/IAY/547931 — Construction of IAY House -IAY REG. NO. MP3301252 | Completed | 15030 | 13560 | 2017-02-01 | 2017-12-10
DHAR / DHAR | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004039/IF/IAY/561851 — Construction of IAY House -IAY REG. NO. MP3727979 | Completed | 15030 | 14323 | 2017-02-01 | 2018-10-28
DHAR / DHAR | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004039/RC/25384 — गेवल मार्ग खामला से बनेडि‍या भाग 2 बायखेडा | Completed | 0 | 437161 | 2009-04-02 | 2010-05-24
DHAR / DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Bunding / Construction of Earthen peripheral/farm/field Bund for Community | Construction of Bund | 1722004039/WC/4108 — जल क्षमता विस्‍तार कार्य खामला बायखेडा | Completed | 0 | 89700 | 2010-04-28 | 2010-12-14
DHAR / DHAR | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004039/WC/4109 — बायखेडा तालाब की जल संग्रहण क्षमता ग्रापं बायखेडा | Completed | 0 | 82400 | 2010-05-27 | 2010-12-14
DHAR / DHAR | 2007-2008 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004039/WC/807 — निस्‍तार तालाब गहरीकरण बायखेडा | Completed | 40000 | 0 | 2007-06-12 | 2008-04-02
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1722004052/AV/22012034565207 — BOUNDARY WAAL MIDDLE SCHOOL BAYKHEDA | Closed | 0 | 0 | 2021-04-01
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722004052/AV/22012034571142 — Construction Of Bench and Desk in Dining माध्यमिक विद्यालय Baykheda | Closed | 0 | 0 | 2021-04-01
DHAR / DHAR | 2022-2023 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722004052/AV/22012034621161 — AAnganwadi bhavan Khamala | Completed | 500000 | 498535 | 2022-09-23 | 2025-07-05
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | AWC / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722004052/AV/3441 — Aanganbadi/Other Rural Infrastructure,DHAR | Completed | 180000 | 180461 | 2015-08-24 | 2019-01-03
DHAR / DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722004052/DP/22012034236490 — Mukktidham Nirman | Completed | 180000 | 177222.88 | 2016-12-24 | 2018-01-25
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1722004052/DP/22012034534304 — मां की बगिया M.S.School Baykheda | Closed | 11397.42 | 0 | 2021-04-01
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1722004052/DP/22012034534754 — SBM ISP Kitchen Garden Unit 10 Bagditurk | Closed | 0 | 0 | 2021-08-15
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1722004052/DP/22012034534755 — SBM ISP Kitchen Garden Unit 10 Baykheda | Closed | 0 | 0 | 2021-08-15
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Horticulture -Community / Boundary Line Plantation of Horticulture Trees for Community | Plantation | 1722004052/DP/22012034534756 — SBM ISP Kitchen Garden Unit 10 Khamla, Baykheda | Closed | 0 | 0 | 2021-08-15
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Block Plantation of Forestry-Community / Along the coast Block Plantation of Forestry Trees for Community | Plantation | 1722004052/DP/22012034584667 — वसुधा बंधन वृक्षारोपण माध्यमिक विद्यालय बायखेड़ा 2023-2024 | Physically Completed | 54564.94 | 27846 | 2023-08-13 | 2026-06-20
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722004052/DP/22012034623845 — Plantation samshan parisar me khamla | Ongoing | 347941.98 | 53004 | 2024-08-08
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004052/IF/22012034339555 — vraksharopan karya khamala baykheda | Completed | 335000 | 309724 | 2017-06-03 | 2022-07-23
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004052/IF/22012034339818 — VrakshaRopan Ramprasad Myaram | Completed | 335000 | 264900 | 2017-06-03 | 2022-07-23
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004052/IF/22012034371702 — Varkchha Ropan Mahesh Nathu KHamla | Physically Completed | 335000 | 298364 | 2017-08-14 | 2026-02-13
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429425 — Shochalay Nirman Babusing- Jagannath | Closed | 12000 | 0 | 2018-04-14
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429426 — Shochalay Nirman Shyamubai- Tejram | Completed | 12000 | 11692 | 2019-01-30 | 2019-07-20
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429427 — Shochalay Nirman Padamsingh- Hindusingh | Completed | 12000 | 11692 | 2019-01-30 | 2019-06-22
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429429 — Shochalay Nirman Samandarsingh- Sardarsingh | Completed | 12000 | 11692 | 2019-01-30 | 2019-07-20
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429430 — Shochalay Nirman Hemgiri-Narayangiri | Completed | 12000 | 11692 | 2019-01-30 | 2019-06-22
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429432 — Shochalay Nirman Kamalsingh-Ramsingh | Completed | 12000 | 11692 | 2019-01-30 | 2019-07-20
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429537 — Shochalay Nirman Parvatsingh-Heealal | Completed | 12000 | 11692 | 2019-01-30 | 2019-07-20
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429895 — Shochalay Nirman Mitigir-Brijgir | Completed | 12000 | 11692 | 2019-01-30 | 2019-07-20
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429896 — Shochalay Nirman Lakhansingh-Ramsingh | Physically Completed | 12000 | 11692 | 2019-01-30 | 2019-10-06
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429897 — Shochalay Nirman Shivkanyabai-Jaswantsingh | Closed | 12000 | 0 | 2018-04-14
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429898 — Shochalay Nirman Banesingh-Punaji | Completed | 12000 | 11692 | 2019-01-30 | 2019-07-20
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034429899 — Shochalay Nirman Rajesh-Rameshwar | Completed | 12000 | 11692 | 2019-01-30 | 2019-07-20
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034431251 — Shochalay Nirman Ishwar-Rameshwar | Closed | 12000 | 0 | 2018-04-14
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034432414 — Shochalay Nirman Omprakash=-Vishnu | Closed | 12000 | 0 | 2018-04-14
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034432416 — Shochalay Nirman Jaydeep- Padansingh | Closed | 12000 | 0 | 2018-04-14
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034432418 — Shochalay Nirman Mahesh -Nathusingh | Closed | 12000 | 0 | 2018-04-14
DHAR / DHAR | 2018-2019 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Single Unit Toilets for Individual / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/IF/22012034439161 — Shochalay Nirman Sardar - Chhogalal | Completed | 12000 | 3132 | 2019-03-12 | 2020-04-04
DHAR / DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722004052/IF/22012034587699 — PASHU SHED ANTARSINGH RANSINGH KHAMALA | Completed | 63531.21 | 59342 | 2020-08-14 | 2021-02-11
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Vermi Compost structure for Individual / Construction of Vermi Compost structure for Individual | Construction of NADEP/Vermi Compost Pit | 1722004052/IF/22012034587987 — VERMI COMPOST ANTER SINGH RANSINGH KHAMALA | Closed | 15355.44 | 0 | 2020-07-01
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004052/IF/22012035364723 — Construction of Farm Pond JGSA Babulal Bhuvanlal on Khasra No 64 Khamla | Physically Completed | 147621.16 | 134376 | 2025-04-23 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004052/IF/22012035492638 — Construction of Farm Pond JGSA Prembai Kalyansingh Baykheda | New | 0 | 0 | 2025-04-01
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722004052/IF/22012035492640 — Construction of Farm Pond JGSA Prembai Kalyansingh Baykheda | Physically Completed | 450885.64 | 409551 | 2025-05-13 | 2026-04-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722004052/IF/22012035646426 — Construction of PMAY Satynarayan Antersingh ID MP105505395 Baykheda | Approved | 23490 | 0 | 2025-04-01
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/9993710333 — Indira Avas Savitreebai Narsingh Baikheda | Completed | 14310 | 3825 | 2016-02-09 | 2017-12-10
DHAR / DHAR | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/9993710337 — Indira Avas Nandabai Magan Baykheda | Completed | 14310 | 3173 | 2016-02-09 | 2017-12-10
DHAR / DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/2426643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4990979 | Completed | 17100 | 15960 | 2020-05-26 | 2021-03-16
DHAR / DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/2427084 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5016107 | Completed | 17100 | 16910 | 2020-06-25 | 2021-03-06
DHAR / DHAR | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/2428000 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5059109 | Completed | 17100 | 15960 | 2020-05-26 | 2021-03-16
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3664677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102088948 | Completed | 18360 | 17136 | 2022-05-24 | 2022-11-17
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3674704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105043081 | Completed | 18360 | 17561 | 2022-05-24 | 2023-07-27
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3674711 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105044284 | Completed | 18360 | 17238 | 2022-05-24 | 2023-07-19
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3674721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105045851 | Completed | 18360 | 17238 | 2022-05-24 | 2023-09-05
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3678415 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113697379 | Completed | 18360 | 17340 | 2022-05-24 | 2023-07-27
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3678446 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113699077 | Completed | 18360 | 18275 | 2022-05-24 | 2023-10-18
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3682985 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334635 | Completed | 18360 | 17136 | 2022-05-24 | 2023-06-25
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3682986 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334832 | Completed | 18360 | 17340 | 2022-05-24 | 2023-09-11
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3702334 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105491677 | Completed | 18360 | 17340 | 2022-05-24 | 2023-07-19
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3704909 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105540783 | Completed | 18360 | 17612 | 2022-05-24 | 2023-11-27
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3713355 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101138237 | Completed | 18360 | 17544 | 2022-05-24 | 2023-01-01
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3736605 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118100533 | Completed | 18360 | 17340 | 2022-05-24 | 2023-09-11
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3736607 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118100706 | Completed | 18360 | 17561 | 2022-05-24 | 2023-07-27
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/3867788 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP145097849 | Completed | 18360 | 17136 | 2022-05-24 | 2023-06-25
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4228338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121352415 | Completed | 18360 | 17544 | 2022-08-17 | 2023-08-11
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4243322 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114995276 | Completed | 18360 | 18258 | 2022-08-17 | 2023-11-20
DHAR / DHAR | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4258705 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146841161 | Completed | 18360 | 17544 | 2022-08-17 | 2023-07-27
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4533647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101250837 | Ongoing | 23490 | 17523 | 2024-11-24
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4538951 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105512237 | Ongoing | 23490 | 18180 | 2024-12-29
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4549866 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113694781 | Completed | 21870 | 21870 | 2024-11-24 | 2025-02-22
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4596464 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123114376 | Ongoing | 23490 | 17379 | 2025-01-20
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4596468 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123114952 | Physically Completed | 23490 | 21510 | 2024-12-01 | 2026-06-20
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4657677 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147921965 | Completed | 23490 | 20916 | 2025-01-22 | 2026-05-18
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4670743 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334541 | Physically Completed | 23490 | 22014 | 2024-12-01 | 2026-06-20
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/4858730 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102301239 | Ongoing | 23490 | 17397 | 2024-11-24
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5151598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102078286 | Physically Completed | 23490 | 21924 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5154372 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105040403 | Ongoing | 23490 | 15921 | 2025-04-12
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5156724 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102335369 | Ongoing | 23490 | 12789 | 2025-04-12
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5163093 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102106094 | Ongoing | 23490 | 13050 | 2025-04-12
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5177602 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102301179 | Ongoing | 23490 | 13311 | 2025-04-12
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5178914 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102300918 | Physically Completed | 23490 | 21924 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5180759 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334329 | Ongoing | 23490 | 15138 | 2025-04-12
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5183271 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334458 | Completed | 23490 | 21504 | 2025-04-12 | 2026-05-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5189310 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105045598 | Physically Completed | 23490 | 20097 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5191199 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP101136495 | Physically Completed | 23490 | 21924 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5192744 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105518815 | Completed | 23490 | 21141 | 2025-04-12 | 2026-05-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5199689 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123113623 | Physically Completed | 23490 | 21663 | 2025-06-04 | 2026-03-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5201687 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146920968 | Physically Completed | 23490 | 9135 | 2025-04-12 | 2026-03-15
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5202934 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146940985 | Physically Completed | 23490 | 20097 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5204515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118100282 | Ongoing | 23490 | 3654 | 2025-04-12
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5209820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102104667 | Physically Completed | 23490 | 21924 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5210416 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334766 | Ongoing | 23490 | 15399 | 2025-04-12
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5210676 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114998426 | Physically Completed | 23490 | 20097 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5216950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118090418 | Physically Completed | 23490 | 20097 | 2025-04-12 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5218648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105544660 | Completed | 23490 | 21924 | 2025-09-11 | 2026-05-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5234286 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105549935 | Physically Completed | 23490 | 20358 | 2025-04-12 | 2026-05-31
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5516671 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123113851 | Completed | 23490 | 21663 | 2025-06-04 | 2026-05-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5518647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105042277 | Completed | 23490 | 21924 | 2025-09-11 | 2026-05-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5520194 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114994671 | Physically Completed | 23490 | 16182 | 2025-06-04 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5520843 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP123114116 | Physically Completed | 23490 | 5220 | 2025-06-04 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5521848 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146910102 | Completed | 23490 | 23490 | 2025-09-11 | 2025-11-03
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5522074 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114995494 | Physically Completed | 23490 | 3654 | 2025-06-04 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5529570 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP146913028 | Physically Completed | 23490 | 21663 | 2025-06-04 | 2026-05-03
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5530476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105498401 | Completed | 23490 | 21924 | 2025-06-04 | 2026-05-18
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5553283 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102334953 | Physically Completed | 23490 | 10962 | 2025-06-04 | 2026-06-20
DHAR / DHAR | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5563487 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105046195 | Completed | 23490 | 21924 | 2025-09-11 | 2026-05-18
DHAR / DHAR | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/5881105 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118090799 | Approved | 23490 | 0 | 2025-02-20
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/743962 — Construction of IAY House -IAY REG. NO. MP2344662 | Completed | 15030 | 15528 | 2017-05-26 | 2018-08-10
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/748087 — Construction of IAY House -IAY REG. NO. MP2470064 | Completed | 15030 | 13500 | 2017-07-05 | 2019-01-03
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/750618 — Construction of IAY House -IAY REG. NO. MP2563994 | Completed | 15030 | 13464 | 2017-05-26 | 2018-10-28
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/751107 — Construction of IAY House -IAY REG. NO. MP2582733 | Completed | 15030 | 14224 | 2017-05-26 | 2019-08-20
DHAR / DHAR | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722004052/IF/IAY/751154 — Construction of IAY House -IAY REG. NO. MP2584422 | Completed | 15030 | 13440 | 2017-05-26 | 2018-10-28
DHAR / DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722004052/LD/22012034294889 — Maidan Samatalikaran Work | Completed | 80000 | 77876.5 | 2017-03-05 | 2018-07-06
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722004052/LD/22012034543613 — KHEL MAIDAN MIDDLE SCHOOL BAYKHEDA | Closed | 0 | 0 | 2021-03-03
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722004052/LD/22012034545899 — KHEL MEDAN MAVI BAYKHEDA | Closed | 336803.25 | 0 | 2021-03-29
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of chaur Land for Community / Development of chaur Land for Community | Land Development | 1722004052/LD/22012034548414 — KHEL MEDAN BAYKHEDA SCHOOL | Closed | 0 | 0 | 2021-04-01
DHAR / DHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004052/LD/71 — ग्रामीण क्रीडांगन खैल मैदान समतलीकरण प्रा वि‍ खामला बायखेडा | Completed | 122000 | 47090 | 2012-01-02 | 2012-12-08
DHAR / DHAR | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722004052/LD/72 — ग्रामीण क्रीडांगन खैल मैदान समतलीकरण मा वि‍ बायखेडा | Completed | 294000 | 97224 | 2011-12-07 | 2012-12-08
DHAR / DHAR | 2016-2017 | D--RURAL INFRASTUCTURE / Play Ground | Play Ground / Construction of Play field for Community | Construction of Play field | 1722004052/PG/9425893433 — Grameen Kridangan | Completed | 214760 | 177006.14 | 2017-02-02 | 2019-06-30
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034160004 — सीमेंट कांक्रीट आंतरिक मांर्ग | Deleted | 0 | 0 | 2013-04-14
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034202027 — सी का आ मा नि आदिवासी बस्‍ती मुख्‍य मार्ग से प्रा | Completed | 150000 | 148045 | 2014-03-05 | 2015-07-22
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034211418 — प्रधानमंत्री सड़क से स्कूल प्रागंण तक | Completed | 97000 | 98875 | 2014-03-05 | 2015-07-22
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004052/RC/22012034212321 — खेत सड़क बनेसिंह के खेत से रामेश्वर के खेत तक | Completed | 1367000 | 932575 | 2014-03-05 | 2016-11-18
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034286776 — C C Road Hanuman Mandeer Se Shankar Singh Ke Makan Tak | Completed | 122000 | 121981 | 2015-10-15 | 2016-08-12
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034293568 — C C Road Ramesh Ke Ghar Se School Tak | Completed | 121000 | 121038 | 2015-12-20 | 2017-09-25
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004052/RC/22012034300766 — Khet Road Udaysingh Ke Khet Se Jagadish Ke Khet Tak | Deleted | 0 | 0 | 2016-01-26
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004052/RC/22012034300768 — Khet Road Gabbusingh Ke Khet Se Thavarsingh Ke Khet Tak | Deleted | 0 | 0 | 2016-01-26
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034324536 — c c road | Closed | 0 | 0 | 2017-04-01
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004052/RC/22012034339130 — Sudur Road Baykheda Se Dedala Marg Ki Our | Completed | 1350000 | 1334095.69 | 2017-05-27 | 2020-08-22
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034347275 — C C Road Samandar Ke Makan Se Santosh Ke Makan Tak | Completed | 75000 | 73110 | 2017-06-01 | 2019-01-03
DHAR / DHAR | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Mitti Murram Road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004052/RC/22012034371345 — khet sadak | Closed | 0 | 0 | 2017-10-02
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034551293 — Cement concrete road muktidham se main road ki or bhag 1 | Completed | 47000 | 46930 | 2021-01-31 | 2022-04-04
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034565557 — Cement concrete road ramesh ke makan se kalu ke makan tak | Completed | 52000 | 51917 | 2021-05-06 | 2021-12-07
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004052/RC/22012034574563 — KHET SADAK NIRBHAY CHOUDHARY KE KHET SE ANTER SINGH SOLANKI KE KHET TAK KHAMLA | Ongoing | 1396693.52 | 949330.03 | 2021-06-25
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034575660 — c c road nirman kalu ke makan se eswar ke makan tak | Closed | 21000 | 0 | 2021-04-14
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034645481 — CEMENT CONCRETE CHOK PANCHAYAT BHAVAN KE SAMNE | Completed | 21000 | 19493 | 2023-10-19 | 2024-05-06
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/22012034825128 — CC Road Mangilal Ke Ghar Se Rajaram Ke Ghar Tak Baykheda | Completed | 35000 | 27459 | 2024-10-05 | 2025-02-24
DHAR / DHAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004052/RC/25651 — आंतरि‍क मार्ग बायखेडा से मुक्‍ि‍तधाम भाग 2 ग्रापं बायखेडा | Completed | 148000 | 131098 | 2011-10-05 | 2013-03-28
DHAR / DHAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722004052/RC/25661 — आंतरि‍क मार्ग बायखेडा से से नयापुरा भाग 2 ग्रापं बायखेडा | Completed | 486085 | 250578 | 2011-11-16 | 2013-12-10
DHAR / DHAR | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722004052/RC/25675 — आंतरि‍क मुरम सडक र्नि‍माण बायखेडा से नयापुरा भाग 3 बायखेडा | Completed | 486000 | 246378 | 2011-11-30 | 2013-11-20
DHAR / DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/25777 — सीमेंट कांक्रीट आंतरिक मार्ग निर्माण हिन्‍दूसिह के घर से सुनील के घर तक बायखेडा | Completed | 95000 | 30000 | 2013-01-24 | 2013-01-25
DHAR / DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/25792 — 1722004052/RC/25792 | Completed | 190000 | 77099 | 2013-01-03 | 2013-11-20
DHAR / DHAR | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722004052/RC/25793 — 1722004052/RC/25793 | Completed | 67000 | 47933 | 2013-01-21 | 2013-11-20
DHAR / DHAR | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/RS/22012034225671 — vyaktigat shochalay baykheda | Completed | 54000 | 18840 | 2014-05-17 | 2015-12-16
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/RS/22012034225884 — vyaktigat shochalay baykheda | Deleted | 54000 | 0 | 2014-03-04
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/RS/22012034225892 — vyaktigat shochalay khamala baykheda | Deleted | 54000 | 0 | 2014-03-04
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/RS/22012034225899 — vyaktigat shochalay baykheda 4 | Deleted | 54000 | 0 | 2014-03-04
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/RS/22012034225933 — vyaktigat shochalay baykheda 5 | Deleted | 54000 | 0 | 2014-03-04
DHAR / DHAR | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/RS/22012034225935 — vyaktigat shochalay khamla baykheda 6 | Deleted | 54000 | 0 | 2014-03-04
DHAR / DHAR | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722004052/RS/22012034288677 — Vyaktigat Sholay Baykheda | Deleted | 20000 | 0 | 2015-10-15
DHAR / DHAR | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004052/RS/22012034511888 — NALI NIRMAN HANUMAN MANDIR SE TALAB TAK | Closed | 0 | 0 | 2021-03-12
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004052/RS/22012034537431 — SBM CSP Samudaik Soak Pit Unit 10 Baykheda,Khamla | Closed | 59999.77 | 0 | 2022-01-13
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004052/RS/22012034537434 — SBM CSP Samudaik Soak Pit Unit 10 Baykheda,Khamla | Closed | 0 | 0 | 2021-04-01
DHAR / DHAR | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722004052/RS/22012034537437 — SBM CSP Samudaik Soak Pit Unit 05 Baykheda,Khamla | Closed | 0 | 0 | 2021-04-01
DHAR / DHAR | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004052/RS/22012034699720 — R C C NALI NIRMAN PANCHAYAT BHAVAN KE PASS WALA NALA | Completed | 39000 | 28683 | 2023-09-20 | 2025-02-11
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004052/RS/22012035130459 — Nali Nirman Hanuman Mandir Se Bawadi Tak Khamla | Completed | 19000 | 16524 | 2024-09-16 | 2025-04-23
DHAR / DHAR | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004052/RS/22012035136516 — सीमेंट कांक्रीट नाली निर्माण महेश राठौर के घर से भगवानसिंह के घर तक बायखेडा | Approved | 14000 | 0 | 2024-10-02
DHAR / DHAR | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Open/Covered Grey Water Drain for Comm / Construction of Open / Covered Grey Water/Storm Drain for Community | Solid and Liquid Waste Management | 1722004052/RS/22012035137831 — सीमेन्‍ट कांक्रीट नाली निर्माण चाढिया टंकी से स्‍कूल की ओर नये खंरजे के पास | Approved | 33000 | 0 | 2025-04-01
DHAR / DHAR | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004052/WC/22012034438059 — jal sangrahan sanrachana | Closed | 0 | 0 | 2016-01-26
DHAR / DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004052/WC/22012034442207 — Nala Trenching Kalyan Ke Khet Se | Closed | 0 | 0 | 2019-01-26
DHAR / DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004052/WC/22012034442208 — Bhu Sankal Pond Khadan Ke Pass | Completed | 338000 | 318496 | 2019-03-12 | 2020-09-10
DHAR / DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004052/WC/22012034448269 — Bhusankan Pound Khamala | Closed | 170000 | 0 | 2019-01-26
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034482542 — Recharge Pit Primary School Baykheda | Completed | 5134.63 | 176 | 2019-09-05 | 2020-10-10
DHAR / DHAR | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004052/WC/22012034518200 — nala trnching kary baikheda | Closed | 0 | 0 | 2019-10-02
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004052/WC/22012034547661 — nala trenching udai singh ke khet se samsang tak | Completed | 329019.6 | 119145.6 | 2020-05-30 | 2021-08-24
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004052/WC/22012034549249 — bhu sanklan pond bharat singh k khe ke pass | Completed | 377415.75 | 378403.2 | 2020-05-30 | 2020-09-10
DHAR / DHAR | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004052/WC/22012034603783 — NALA TRENCH KAMALSINGH KE KHET SE TALAB TAK BAYKHEDA | Physically Completed | 587472.75 | 575977.2 | 2020-12-30 | 2021-06-20
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004052/WC/22012034637998 — CTRA WORK SANKAN POND SCHOOL KI PICHE KHAMLA | Completed | 192767.79 | 188240.92 | 2021-04-14 | 2021-12-08
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004052/WC/22012034643032 — CTRA RWH WORK PRAVI KHAMLA BAYKHEDA | Completed | 5500 | 6948 | 2021-04-14 | 2021-09-25
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Roof top rain wat. har. str. in gov/panchayat bldg / Roof Top Rain Water harvesting for Government/Panchayat Buildings | Roof Water Harvesting on gov/panchayat bldg | 1722004052/WC/22012034643039 — CTRA RWH WORK MAVI BAYKHEDA | Completed | 5500 | 6948 | 2021-06-29 | 2021-09-16
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004052/WC/22012034648711 — CTRA SANKAN POND AAGANWADI KE PICHE BAYKHEDA | Completed | 203747.02 | 178993.92 | 2021-05-23 | 2021-12-08
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034679730 — CTRA RICHARGE PIT-1 TALAB WALA NALA BAYKHEDA | Completed | 13133.77 | 14408 | 2021-06-29 | 2021-09-25
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034679733 — CTRA RICHARGE PIT-2 TALAB WALA NALA BAYKHEDA | Completed | 13133.77 | 13133 | 2021-06-29 | 2021-09-25
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034679737 — CTRA RICHARGE PIT-3 TALAB WALA NALA BAYKHEDA | Completed | 13133.77 | 12092 | 2021-06-29 | 2021-12-08
DHAR / DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034679747 — CTRA RICHARGE PIT-1 SAMSAN WALA NALA BAYKHEDA | Closed | 13133.77 | 0 | 2022-04-23
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034679758 — CTRA RICHARGE PIT-2 SAMSAN WALA NALA BAYKHEDA | Closed | 13133.77 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034679759 — CTRA RICHARGE PIT-2 SAMSAN WALA NALA BAYKHEDA | Closed | 0 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034679764 — CTRA RICHARGE PIT 3 SAMSAN WALA NALA BAYKHEDA | Closed | 13133.77 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034681523 — CTRA RICHARGE PIT -3 SAMSAN WALA NALA BAYKHEDA | Closed | 0 | 0 | 2021-04-14
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034794148 — SBM ISP Individualay Soak Pit Unit 50 Baykheda,Khamla | Closed | 99999.74 | 0 | 2021-10-19
DHAR / DHAR | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722004052/WC/22012034794149 — SBM ISP Individualay Soak Pit Unit 50 Baykheda,Khamla | Closed | 0 | 0 | 2021-04-01
DHAR / DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004052/WC/22012034936066 — भू संकलन पोंद जीवन के खेत के पास बायखेड़ा | Completed | 417868.21 | 347451 | 2022-05-02 | 2026-03-08
DHAR / DHAR | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004052/WC/22012034936074 — भू संकलन पोंड सुभाष भील के खेत के पास खामला | Physically Completed | 421261.1 | 354463.83 | 2022-11-30 | 2026-04-14
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722004052/WC/22012035100043 — भू संकलन पोंड मुकेश कामदार के खेत के पास | Closed | 0 | 0 | 2023-08-16
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722004052/WC/22012035100046 — Nala trenching Gangaram ke khet se Dilip ke khet Tak | Closed | 0 | 0 | 2023-08-16
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722004052/WC/22012035165178 — Nala tranching karya | New | 0 | 0 | 2024-01-26
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004052/WC/22012035199177 — tank bherusingh ke khet ke pas | Closed | 0 | 0 | 2024-01-28
DHAR / DHAR | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004052/WC/22012035199354 — Mini percolation tank bherusingh ke khet ke pass | Closed | 0 | 0 | 2024-01-28
DHAR / DHAR | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722004052/WC/22012035239354 — Construction of Mini Percolation Tank Near Bajesing Lalsingh Farm on Khasara No.434/1 Baykheda | Physically Completed | 199709.8 | 86698 | 2025-01-10 | 2026-04-20
DHAR / DHAR | 2013-2014 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Farm Pond / Construction of Farm Ponds for Individuals | Farm Pond | 1722004052/WC/9993629606 — जल संग्रहण संरचना बायखेडा | Completed | 146000 | 145416 | 2013-06-15 | 2014-04-30
DHAR / DHAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004052/WC/9993629607 — जल संग्रहण संरचना खामला बायखेडा | Completed | 128000 | 127750 | 2013-06-08 | 2014-04-30
DHAR / DHAR | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722004052/WC/9993640364 — जल संग्रहण संरचना देदला रोड पर बायखेडा | Completed | 324000 | 207612 | 2013-12-21 | 2015-12-15
DHAR / DHAR | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation / Renovation of Community Water Harvesting Ponds for Community | Renovation of traditional water bodies | 1722004052/WH/19961245 — Ripair Of Nistar Talab | Deleted | 605000 | 0 | 2017-04-19
DHAR / DHAR | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722004052/WH/22012034333260 — Nstar Talab Jirnoddar | Completed | 605000 | 579690.02 | 2019-03-07 | 2020-07-29
DHAR / DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034836729 — Sumersingh Umrav Horti Plantation | Closed | 206310 | 0 | 2021-06-25
DHAR / DHAR | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722004/IF/22012034836730 — Bhagwan Brijgiri Horti Plantation | Closed | 206310 | 0 | 2021-06-25