## Work List
Exported on: 2026-10-25 10:00:14
Filters applied:
Data source: MGNREGA
District: All
Block: All
Panchayat: Sulavad
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005004/AV/22012034373655 — Panchayat Bhawan nirman sulawad | Completed | 579000 | 578526.96 | 2018-06-10 | 2021-12-02
DHAR / NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722005004/AV/22012034399702 — AANGANWADI BHAWAN NIRMAN NO.01 PRATHMIK SCHOOL KE PASS | Closed | 0 | 0 | 2019-04-04
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005004/AV/22012034574609 — RTW Dinig hall High school Sulawad | Closed | 0 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005004/AV/22012034603253 — Segregation shed nirman Sulawad | Closed | 298000 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005004/AV/22012034611493 — school boundary wall middile school Sulawad | Closed | 683000 | 0 | 2021-08-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005004/AV/22012034611495 — school boundary wall middile school Sulawad | Closed | 0 | 0 | 2021-08-01
DHAR / NALCHHA | 2010-2011 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005004/DP/2125 — शांतिवन कार्य सुलावड ग्राम पंचायत सुलावड | Completed | 311000 | 275058 | 2010-07-20 | 2016-03-30
DHAR / NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of GP for community / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005004/DP/22012034227871 — muktidham me shed nirman avm graund leving kary gram panchayat sulavad | Completed | 141000 | 140800.68 | 2015-12-03 | 2018-07-07
DHAR / NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005004/DP/22012034590567 — AKAM वसुधा वंदन अमृत वाटिका अमृत सरोवर तालाब खारवा सुलावड | Closed | 55847.4 | 0 | 2023-08-02
DHAR / NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation in fields-Horticulture-Community / Fields Block Plantation of Horticulture Trees for Community | Plantation | 1722005004/DP/22012034608979 — POSHAN WATIKA WORK(CNG) KASTURBA GANDHI BALIKA VIDHYALAYA WITH CHATRAWAS,GP SULAWAD | Ongoing | 441335.79 | 172260 | 2023-10-09
DHAR / NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005004/DP/9926694552 — व़क्षारोपण कार्य सुलावड | Deleted | 0 | 0 | 2012-12-24
DHAR / NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005004/DP/9926694555 — व्‍यक्तिगत शौचालय निर्माण युनिट क्रमांक 1 | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005004/DP/9926694556 — व्‍यक्तिगत शौचालय निर्माण युनिट क्रमांक 2 | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012034298784 — mukhaya mantri avash nirman bharat ramsingh | Completed | 15030 | 15030 | 2016-11-03 | 2017-07-22
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012034298785 — mukya mantriavash nirman ramesh ramsingh | Completed | 15300 | 14888 | 2016-11-17 | 2017-07-22
DHAR / NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012034298787 — mukya mantri avash nirma ramlal kasiram | Deleted | 0 | 0 | 2016-01-26
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012034298788 — mukhya mantri avash nirman ramlal kasiram | Completed | 15030 | 15035 | 2016-12-31 | 2017-07-22
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012034298790 — mukya mantri avash nirman santhosh narayan | Completed | 15030 | 14382 | 2016-11-03 | 2018-06-16
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012034312754 — PM Awas Yojna Mahesh Mulchand | Deleted | 0 | 0 | 2016-08-15
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012034312756 — PM Awas Yojna Kelash Sidhu Sulvad | Deleted | 0 | 0 | 2016-08-15
DHAR / NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722005004/IF/22012034317468 — warmicompost | Deleted | 0 | 0 | 2016-08-15
DHAR / NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Forestry Trees-Fields-Individuals / Block Plantation of Forestry Trees in Fields for Individuals | Plantation | 1722005004/IF/22012034343252 — वुक्षारोपण कार्य स्‍कूल परिसर सुलावड | Completed | 335000 | 279239 | 2017-06-01 | 2021-05-02
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005004/IF/22012034384561 — Platation Work 2 Heq. Sulavad | Deleted | 0 | 0 | 2018-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035480831 — khet talab harishankar patel | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035480834 — khet talab harishankar patel | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035480916 — khet talab harishankar patel khet par gram panchayat sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035480918 — khet talab harishankar patel khet par gram panchayat sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035481073 — khet talab harishankar patel khet par gram panchayat sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035481138 — khet talab harishankar patel khet par gram panchayat sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035483756 — khet talab harishankar pita jagannth gp sulawad | Physically Completed | 399679.74 | 340586.56 | 2025-05-18 | 2026-05-27
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035492863 — jgsa khet talab jagannath pita nathusing ke khet me gp sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035492936 — jgsa khet talab jagannath pita nathusing ke khet me gp sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035492972 — jgsa khet talab jagannath pita nathusing ke khet me gp sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035492995 — jgsa khet talab jagannath pita nathusing ke khet me gp sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035493008 — jgsa khet talab jagannath pita nathusing ke khet me gp sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035493023 — jgsa khet talab jagannath pita nathusing ke khet me gp sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035493111 — jgsa khet talab jagannath pita nathusing ke khet me gp sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035493424 — jgsa khet talab chaya pati arun patel ke khet me gp sulawad | Physically Completed | 363369.34 | 295640.56 | 2025-05-15 | 2026-05-27
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035519023 — khet talab ghani bai khet par gram panchayat sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722005004/IF/22012035519025 — khet talab ghani bai khet par gram panchayat sulawad | New | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012035596589 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105213632 | Physically Completed | 23490 | 20358 | 2025-08-27 | 2026-06-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012035597340 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127582138 | Approved | 23490 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/22012035597361 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764145 | Approved | 23490 | 0 | 2025-04-14
DHAR / NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005004/IF/9993731759 — मुख्यमंत्री आवास निर्माण कार्य भारत रामशिंह | Deleted | 0 | 0 | 2016-02-27
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/1260870 — Construction of IAY House -IAY REG. NO. MP1598946 | Completed | 15480 | 14964 | 2018-04-20 | 2018-07-21
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/1382580 — Construction of IAY House -IAY REG. NO. MP1447206 | Completed | 15480 | 15660 | 2018-04-20 | 2018-07-29
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/1421563 — Construction of IAY House -IAY REG. NO. MP2818764 | Completed | 15480 | 15660 | 2018-06-06 | 2018-07-29
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2570087 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4211743 | Completed | 17100 | 16910 | 2020-07-08 | 2020-12-30
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2570431 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4242432 | Completed | 17100 | 17106 | 2020-07-08 | 2021-05-09
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2573960 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4555451 | Completed | 17100 | 17139 | 2020-07-08 | 2021-05-09
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2574448 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4593062 | Completed | 17100 | 17100 | 2020-07-08 | 2021-01-02
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2577005 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4610228 | Completed | 17100 | 17119 | 2020-07-08 | 2021-01-02
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2577428 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4573256 | Completed | 17100 | 17127 | 2020-07-08 | 2021-05-09
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2586463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4133764 | Completed | 17100 | 17100 | 2020-07-08 | 2020-08-25
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2586678 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4227496 | Completed | 17100 | 17124 | 2020-07-08 | 2021-05-09
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2587417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4617537 | Completed | 17100 | 17159 | 2020-07-08 | 2021-05-09
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2595610 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4571008 | Completed | 17100 | 16973 | 2020-07-08 | 2021-05-09
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2781983 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP2818449 | Completed | 17100 | 11608 | 2021-04-05 | 2024-06-26
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2783765 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4575515 | Completed | 17100 | 15633 | 2021-04-09 | 2021-11-13
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2785338 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4517424 | Completed | 17100 | 17370 | 2021-04-09 | 2022-01-10
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2786287 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4541983 | Completed | 17100 | 17370 | 2021-04-17 | 2021-11-15
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2792833 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP5030355 | Completed | 17100 | 15054 | 2021-04-09 | 2021-11-13
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2984259 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP1908977 | Completed | 17100 | 17177 | 2021-08-07 | 2022-01-10
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2985410 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4247563 | Completed | 17100 | 16984 | 2021-04-09 | 2021-11-19
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/2988200 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP4559490 | Completed | 17100 | 16791 | 2021-04-09 | 2021-11-19
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/3671816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP105812019 | Completed | 18360 | 18249 | 2022-06-21 | 2024-07-26
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/3680075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764314 | Completed | 18360 | 17632 | 2022-06-23 | 2024-06-20
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/3967721 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106030092 | Completed | 18360 | 18360 | 2022-06-21 | 2022-10-23
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/3980112 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764402 | Completed | 18360 | 18360 | 2022-06-21 | 2022-10-04
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/4189538 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113519509 | Completed | 18360 | 18225 | 2022-06-30 | 2024-06-20
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/4239417 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149064408 | Closed | 18360 | 0 | 2022-06-28
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/4686887 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106027384 | Physically Completed | 23490 | 23229 | 2025-06-13 | 2026-06-20
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/4716122 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127584726 | Ongoing | 23490 | 19575 | 2025-08-25
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/5284851 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764441 | Approved | 23490 | 0 | 2025-02-28
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/5306069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147636461 | Physically Completed | 23490 | 10962 | 2026-03-02 | 2026-05-31
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/5368349 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117798887 | Approved | 23490 | 0 | 2025-03-21
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/5376385 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764427 | Physically Completed | 23490 | 7308 | 2026-03-02 | 2026-06-20
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/5376984 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115764339 | Physically Completed | 23490 | 22968 | 2025-10-13 | 2026-06-20
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/570773 — Construction of IAY House -IAY REG. NO. MP5021942 | Completed | 15030 | 10832 | 2017-02-01 | 2018-09-26
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/614415 — Construction of IAY House -IAY REG. NO. MP1886455 | Completed | 15030 | 16008 | 2017-02-25 | 2018-08-22
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/614743 — Construction of IAY House -IAY REG. NO. MP1969819 | Completed | 15030 | 14104 | 2017-03-04 | 2018-07-07
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/709043 — Construction of IAY House -IAY REG. NO. MP1548819 | Completed | 15030 | 14148 | 2018-02-01 | 2018-11-15
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/711116 — Construction of IAY House -IAY REG. NO. MP1575327 | Completed | 15030 | 15480 | 2018-02-01 | 2018-04-20
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/727266 — Construction of IAY House -IAY REG. NO. MP1886404 | Completed | 15030 | 15136 | 2017-05-24 | 2018-02-24
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/747898 — Construction of IAY House -IAY REG. NO. MP2465094 | Completed | 15030 | 15480 | 2017-09-21 | 2017-12-01
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/757387 — Construction of IAY House -IAY REG. NO. MP2837988 | Completed | 15030 | 15480 | 2018-02-01 | 2018-04-20
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005004/IF/IAY/773409 — Construction of IAY House -IAY REG. NO. MP3591976 | Completed | 15030 | 15480 | 2017-05-24 | 2017-12-13
DHAR / NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005004/LD/3799411576 — ग्रामीण क्रिकांगण मा वि के पास ग्राम पंचायत सुलावड | Completed | 500000 | 464326 | 2013-05-08 | 2015-06-30
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034158482 — मिटटी मुरम सडक कार्य खाखा हेण्‍ड पंप से खाखा नाले तक | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034158483 — मिटटी मुरम सडक कार्य खाखा हेण्‍ड पंप से खाखा नाले तक | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034158484 — मिटटी मुरम आंतरिक मार्ग एके बीएनरोड से उदयसिंह के भवन तक | Deleted | 0 | 0 | 2012-12-24
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/22012034158485 — पंच परमेश्‍वर सीसी रोड भेरूजी के मंदीर से बनेसिंह | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/22012034158486 — पंच परमेश्‍वर सीसी रोड भेरूजी के मंदीर से शाला भवन तक | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/22012034202789 — mandir se bhahadur ke ghar tak | Completed | 185000 | 178678 | 2014-02-06 | 2014-08-16
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034210463 — greval marg nirman achana kankad se madhu ramchand | Completed | 928000 | 716088.65 | 2014-02-27 | 2017-01-10
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034213257 — greval marg nirman fouji ke khet se chandan khedi | Deleted | 1467000 | 0 | 2014-03-06
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034214096 — graval marg madhusing ramchandra ke khat sa chanda | Deleted | 0 | 0 | 2014-02-25
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034214102 — graval marg madhu ramchandra ke khat sa chandan khadi kakad tak | Deleted | 0 | 0 | 2014-02-25
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034214104 — graval marg madhu ramchandra ke khat sa chandan khadi kakad tak | Deleted | 0 | 0 | 2014-02-25
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034214106 — graval marg madhu ramchandra ke khat sa chandan kh | Deleted | 1366000 | 0 | 2014-03-13
DHAR / NALCHHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/22012034223299 — cc rod madhymik school se bheruji k otletak | Deleted | 0 | 0 | 2014-06-12
DHAR / NALCHHA | 2014-2015 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/22012034223301 — cc rod madhymik.school sebhruji k otle tak | Completed | 275000 | 204509 | 2014-07-03 | 2015-06-30
DHAR / NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034295042 — c. m. khat sadak upyojana grawal marg nirman ram prasad ke khat se aatmaram kuwraji ke khat | Completed | 1495000 | 1497246.41 | 2016-01-07 | 2021-12-03
DHAR / NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034295404 — c.m. khat sadak upyojana grawal road nirman ramprasad raguvanshi ke khat se aatmaram ke khat | Deleted | 1495000 | 0 | 2016-01-05
DHAR / NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034300016 — kheth sadak nirman sulavad | Deleted | 0 | 0 | 2015-11-07
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005004/RC/22012034571502 — Khet sadk nirman narendra patel ke khet se kamal kamdar ke khet tak Sulawad | Physically Completed | 1496129.73 | 1379916.6 | 2021-05-25 | 2026-06-14
DHAR / NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/22012034848074 — CC ROAD SHANKAR MANDIR MATAJI MANDIR SE SURENDRA JAAT KE GHAR TAK SULAWAD | Ongoing | 44000 | 31581 | 2026-02-03
DHAR / NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/22012034848075 — CC ROAD MAIN ROAD SE MURLI PARMAR KE GHAR TAK SULAWAD | Ongoing | 136000 | 126324 | 2025-10-11
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/50008 — ख्‍श्‍खरंजा निर्माण सुलावड | Deleted | 0 | 0 | 2008-02-02
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/50009 — खरंजा निर्माण सुलावड | Completed | 400000 | 873585.6 | 2008-03-29 | 2009-12-30
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/50114 — ग्रेवल मार्ग निर्माण कार्य सुलावड से मेढवाडा कांकड तक लागत 5 लाख सुलावड | Completed | 0 | 0 | 2007-04-03 | 2009-03-25
DHAR / NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/50260 — ग्रेवल मार्ग सुलावड से हरि‍जन मोहल्‍ला मार्ग सुलावड RES | Completed | 0 | 592266.34 | 2010-03-02 | 2012-07-16
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/50606 — सुलावड् से गोशाला मार्ग ग्राम पंचायत सुलावड | Completed | 498000 | 202662 | 2011-05-20 | 2012-05-19
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/50607 — ग्रेवल रोड शाखा हेण्‍डपंप से चंदनखेडी काकड तक भाग एक ग्राम पंचायत सुलावड | Completed | 498000 | 466656 | 2011-05-20 | 2012-05-19
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/50608 — ग्रेवल रोड शाखा हेण्‍डपंप से चंदनखेडी काकड भाग दो ग्राम पंचायत सुलावड | Completed | 498000 | 461214 | 2011-05-20 | 2012-06-14
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/50801 — आंतरिक मार्ग प्रधानमंृी सडक से जयनारायण के घर तक ग्राम पंचायत सुलावड | Completed | 0 | 434664 | 2012-04-05 | 2012-12-16
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/50829 — सिमेंट कांक्रिट हनुमान मंदीर से मलखान मोरी के घर तक ग्राम पंचायत सुलावड | Completed | 371000 | 134176 | 2012-04-21 | 2013-07-10
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005004/RC/50935 — पंच परमेश्‍वर सी सी रोड जादू के मकान से दिलीप पटेल | Completed | 190000 | 145534 | 2013-02-21 | 2015-06-30
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/540 — गेवलमार्ग निमा्र्ण सूलावड से बक्‍साना भाग 1 | Completed | 200000 | 120835 | 2006-12-21 | 2009-03-25
DHAR / NALCHHA | 2005-2006 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/542 — ग्रेवल मार्ग निर्माण बक्‍साना से अचाना मार्ग भाग 2 सुलावड | Deleted | 200000 | 0 | 2006-02-02
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/543 — ग्रेचल मार्ग निर्माण सुलावड से अचाना भाग 1 सुलावड | Completed | 200000 | 385275 | 2007-02-22 | 2009-03-25
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/544 — ग्रेवल मार्ग निर्माण सुलावड से अचाना मार्ग भाग 2 सुलावड | Completed | 200000 | 267161 | 2007-03-01 | 2009-03-25
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005004/RC/545 — ग्रेवल मार्ग निर्माण सुलावड से बक्‍साना भाग 2 सुलावड | Completed | 200000 | 0 | 2007-02-08 | 2009-03-25
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Community / Construction of Compost Pit structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005004/RS/22012034532836 — SBM SCP Sulawad | Closed | 0 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1722005004/RS/22012034587181 — SBM compost pit nirman Panchayat Bhawan ke samne Sulawad | Closed | 20615.17 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Compost Pit for Groups / Construction of Compost Pit for Groups | Construction of NADEP/Vermi Compost Pit | 1722005004/RS/22012034587187 — SBM compost pit nirman Fulsing ke ghar ke pas Sulawad | Closed | 20615.17 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005004/RS/22012034601276 — SBM ILP Ramesh+Kishan+Setap+Pakol+Gangaran Sulawad | Closed | 20806.45 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005004/RS/22012034601280 — SBM ILP Tetiya+Budhiya+Budhiya+Amaersing+durgesh Sulawad | Closed | 20806.45 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005004/RS/22012034601282 — SBM ILP Mehatab+Ramsing+Mukhesh+Kudibai+Suresh Sulawad | Closed | 20806.45 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Soak Pit for Community / Construction of Soak Pit for Community | Solid and Liquid Waste Management | 1722005004/RS/22012034601285 — SBM ILP Suresh+Fulsing+Takur+Santosh+Savitri Sulawad | Closed | 20806.45 | 0 | 2021-04-01
DHAR / NALCHHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Construction of Community Sanitary Complex / Construction of Community Sanitary Complex | Community Sanitary Complex | 1722005004/RS/22012034699546 — सेग्रीगेशन शेड निर्माण कार्य ग्राम पंचायत सुलावड | Closed | 0 | 0 | 2023-04-01
DHAR / NALCHHA | 2023-2024 | D--RURAL INFRASTUCTURE / Rural Sanitation | Repair & Maint of NADEP Compost for Community / Repair and Maintenance of NADEP Compost structure for Community | Repaire and Maint of NADEP/Vermi Compost Pit | 1722005004/RS/22012034703187 — SEGREGATION SHED GRAM PANCHAYAT SULAWAD | Completed | 297000 | 260377.04 | 2023-10-03 | 2026-04-21
DHAR / NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005004/WC/22012034380387 — talab nirman sulawad | Closed | 0 | 0 | 2017-10-02
DHAR / NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012034427217 — sankan pond nirman gosala ke paas sulavad | Closed | 431000 | 0 | 2018-04-14
DHAR / NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012034427227 — sankan pond nirman puliya ke paas sulawad | Completed | 431000 | 400502 | 2019-01-17 | 2021-10-15
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005004/WC/22012034433651 — SANKON POND KARY AACHANA ROAD | Closed | 0 | 0 | 2019-04-04
DHAR / NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005004/WC/22012034636810 — CTRA- Nala traching shamsan ke piche | Closed | 0 | 0 | 2021-01-22
DHAR / NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005004/WC/22012034636815 — CTRA sankan pond Gosal ke pass | Closed | 0 | 0 | 2021-01-22
DHAR / NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Pebble graded Bund for Community / Construction of Pebble graded Bund for Community | Construction of Bund | 1722005004/WC/22012034636818 — CTRA sankan pond Achna road | Closed | 0 | 0 | 2021-01-22
DHAR / NALCHHA | 2020-2021 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722005004/WC/22012034636822 — CTRA Talab Nirman Pirbaba ke pas | Closed | 0 | 0 | 2021-01-22
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005004/WC/22012034649533 — CTRA Roof top water harvesting panchayat bhawan Sulawad | Completed | 23950.86 | 21946 | 2021-05-05 | 2021-07-05
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005004/WC/22012034649538 — CTRA Roof top water harvestig samudayik bhawan Sulawad | Completed | 21144.79 | 20476 | 2021-05-05 | 2021-07-05
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005004/WC/22012034649541 — CTRA Roof top water harvesting middile school Sulawad | Completed | 30307.87 | 26170 | 2021-05-28 | 2021-07-05
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005004/WC/22012034673571 — CTRA Roof top water harvesting High school Sulavad | Completed | 25596.01 | 21984 | 2021-05-12 | 2021-07-05
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter - openwell recharge for Comm / Construction of Sand filter for openwell recharge for Community | Well Recharge | 1722005004/WC/22012034708587 — CTRA Roof top water harvesting Upaaganwadi kefndra Sulawad | Closed | 0 | 0 | 2021-04-01
DHAR / NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012034986473 — amrat sarovar talab kharwa santosh jaat ke khet ke pass sulawad gp sulawad | Closed | 0 | 0 | 2022-04-25
DHAR / NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012034986474 — amrat sarovar talab kharwa santosh jaat ke khet ke pass sulawad gp sulawad | Closed | 0 | 0 | 2022-04-25
DHAR / NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012034986475 — amrat sarovar talab kharwa santosh jaat ke khet ke pass sulawad gp sulawad | Closed | 0 | 0 | 2022-04-25
DHAR / NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012035036684 — kamyuniti watar harvesting pond kharava sulavad | Closed | 0 | 0 | 2022-08-15
DHAR / NALCHHA | 2022-2023 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012035036685 — kamyuniti watar harvesting pond kharava sulavad | Closed | 0 | 0 | 2022-08-15
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012035038562 — community water harvesting pond kharava sulavad | Physically Completed | 461874.08 | 446005.39 | 2024-11-27 | 2026-04-15
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005004/WC/22012035163757 — RE | New | 0 | 0 | 2024-04-01
DHAR / NALCHHA | 2013-2014 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005004/WC/9993632024 — संकल पौण्‍ड निर्माण सुलावड | Deleted | 262000 | 0 | 2013-05-30
DHAR / NALCHHA | 2014-2015 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005004/WC/9993664535 — sankal pond nirman sodan mori ke khat ke paas | Deleted | 0 | 0 | 2014-06-13
DHAR / NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005004/WC/9993664538 — sunken pond nirman sodan mori ke khat ke paas | Completed | 513000 | 510316.64 | 2016-04-07 | 2018-07-05
DHAR / NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005004/WC/9993664540 — sunken pond nirman kumar bhatta | Completed | 513000 | 510541.6 | 2016-04-01 | 2018-07-05
DHAR / NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005004/WC/9993667436 — sankan pond nirman sulavad | Deleted | 0 | 0 | 2015-11-04
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovation of Fisheries Ponds for Community / Renovation of Fisheries Ponds for Community | Repair & maint of Pond/ Tank | 1722005004/WH/22012034452077 — Talab renovation pir wala Sulawad | Closed | 0 | 0 | 2021-04-01
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722/RC/22012034562751 — sudur sadak niman krashna ke khet sebhanwar patel tak sulawad se | Closed | 3374000 | 0 | 2021-01-14