## Work List
Exported on: 2026-09-09 22:32:51
Filters applied:
Data source: MGNREGA + VBGRAMG
District: All
Block: All
Panchayat: Bachhadavada
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722005009/AV/22012034370431 — Shanti Dham Nirman Bachhadawada | Completed | 180000 | 179656.4 | 2017-12-15 | 2019-01-10
DHAR / NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Bharat Nirman Seva Kendra / Construction of Gram Panchayat/Panchayat Bhavan Building for Community | Constr of GP Bhawan | 1722005009/AV/22012034373739 — Panchayat Bhawan nirman bachhadawada | Completed | 579000 | 587737 | 2018-06-20 | 2021-12-03
DHAR / NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Construction of Mitti Murram Roads for Community / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/AV/22012034447799 — Khel medan nirman panchayat bhawan ke samne bachhadawada | Completed | 162000 | 159409.18 | 2019-03-08 | 2021-07-05
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Kitchen Shed / Construction of Kitchen shed Building for Community | Constr of Kitchen Shed | 1722005009/AV/22012034572092 — RTW daining hall nirman m.s nirman bachdawada | Completed | 34464.45 | 29821 | 2021-08-14 | 2021-12-05
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of CmpOnd wall for gov schools for Comm / Construction of Compound wall for government schools for Community | Constr of Compound wall | 1722005009/AV/22012034589943 — boundry wall nirman m.s bachdawada | Physically Completed | 1019554.66 | 873866.01 | 2021-09-29 | 2026-06-27
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Anganwadi for community / Construction of Anganwadi Building for Community | Constr of Aganwadi | 1722005009/AV/22012034599050 — RTW DAINING HALL PRIMARY SCHOOL SILODAKHURD | Closed | 47685.39 | 0 | 2021-04-01
DHAR / NALCHHA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert for Community | Culvert | 1722005009/AV/22012034659371 — नाली निर्माण कार्य मेनरोड से पोपसिंह सिसोदिया के घर की ओर बछडावदा | Approved | 62000 | 0 | 2024-06-08
DHAR / NALCHHA | 2024-2025 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Constr of Culvert/cross drainage work for Comm / Construction of Culvert / cross drainage structues for Community | Culvert | 1722005009/AV/22012034659372 — नाली निर्माण कार्य मेनरोड से नंदराम जी टेलर के घर की ओर बछडावदा | Deleted | 40000 | 0 | 2024-06-16
DHAR / NALCHHA | 2008-2009 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Forest Protection / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005009/DP/2051 — VARKSHA ROPAN KARYA BACHADAVDA | Deleted | 199000 | 11700 | 2008-08-29
DHAR / NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Afforestation / Along the coast Afforestation using forestry Trees for Community | Plantation | 1722005009/DP/2190 — shantivan yojna bachdavada gram pachayat bachdavda | Completed | 125000 | 20001 | 2012-04-03 | 2012-11-26
DHAR / NALCHHA | 2016-2017 | D--RURAL INFRASTUCTURE / Anganwadi/Other Rural Infrastructure | Crematorium / Construction of Crematorium for Community | Construction of Crematorium | 1722005009/DP/22012034237420 — शमशान शेड निर्माण सिलोदा बुज़ुर्ग | Completed | 180000 | 177241.51 | 2017-01-23 | 2019-10-17
DHAR / NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Plantation / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005009/DP/22012034328801 — शांतिधाम निर्माण बछडावदा | Deleted | 0 | 0 | 2017-04-17
DHAR / NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1722005009/DP/22012034588663 — AKAM Vasudh Vandan Amrit Vatika Pachayat Bhavan Bachhadawada | Completed | 55847.4 | 23317 | 2023-08-11 | 2026-03-26
DHAR / NALCHHA | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Coastal Line Plantation-Horticulture-Community / Along the coast Line Plantation of Horticulture Trees for Community | Plantation | 1722005009/DP/22012034610775 — Phodh Ropan Kary Talab pal Bachhadawada | Ongoing | 430320.58 | 153446 | 2023-10-09
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1722005009/DP/22012034626084 — Plantation Anganvadi -02P arisar | Deleted | 0 | 0 | 2024-06-08
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation-Shelter Belt Trees (Comm) / Boundary Line Plantation of Shelter Belt Trees for Community | Plantation | 1722005009/DP/22012034626110 — Plantation Middil School Parisar | Ongoing | 198571.34 | 87480 | 2024-10-01
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Boundary Line Plantation of Forestry-Community / Boundary Line Plantation of Forestry Trees for Community | Plantation | 1722005009/DP/22012034626112 — Plantation Anganvadi -02 Parisar | Approved | 149537.42 | 0 | 2024-06-08
DHAR / NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Grass Land Development and Silvi-pasture / Development of Silvipasture Grassslands for Community | Grass Land Development | 1722005009/DP/9926694531 — मर्यादा अभियान ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Rural Drinking Water | DUGWELLS / Construction of Irrigation Open Well for Community | Construction of Well | 1722005009/DW/22012034354881 — Sarvjanik Kup Nirman Bachadawada | Closed | 0 | 0 | 2018-04-14
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Compost Pit / Construction of Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722005009/IF/22012034317269 — warmi copost | Suspended | 0 | 0 | 2021-01-01
DHAR / NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1722005009/IF/22012034339499 — Saskiy Pratmik School Bachadawda gp bachadawda | Completed | 335000 | 13942 | 2017-06-01 | 2019-09-15
DHAR / NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Block Plantation-Farm Forestry-Fields Individuals / Block Plantation of Farm Forestry Trees in Fields for Individuals | Plantation | 1722005009/IF/22012034368650 — Road Side Plantation Ghatabillod Road | Completed | 335000 | 10520 | 2017-08-03 | 2019-10-17
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005009/IF/22012034383873 — Platation Work 2 Heq. Bachadawada | Closed | 0 | 0 | 2018-04-14
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005009/IF/22012034383875 — Platation Work 2 Heq. silodkhurd bachadwada | Closed | 0 | 0 | 2018-04-14
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Plantation / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005009/IF/22012034384744 — Platation Work 2 Heq. Silodabujurg Bachandwada | Closed | 0 | 0 | 2018-04-14
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | DUGWELLS / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722005009/IF/22012034385641 — Kapil Dhara Kup | Closed | 0 | 0 | 2018-04-14
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Wasteland Block Plantation-Sericulture-Individuals / Wastelands Block Plantation of Sericulture Trees for Individuals | Plantation | 1722005009/IF/22012034609892 — Wracha ropan kary mukti dham me | Physically Completed | 390826.48 | 78090 | 2020-09-22 | 2020-12-20
DHAR / NALCHHA | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Coastal Shelter Belt-line plntation - Individual / Line Plantation of Coastal Shelter Belt Trees for Individuals | Plantation | 1722005009/IF/22012034615015 — vrchharopan kiran bai | Physically Completed | 85694.77 | 3990 | 2020-09-30 | 2020-12-20
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005009/IF/22012035583517 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP116664402 | Ongoing | 23490 | 0 | 2026-02-07
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005009/IF/22012035583552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116664402 | Deleted | 0 | 0 | 2025-06-08
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005009/IF/22012035585037 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP148718569 | Physically Completed | 23490 | 4698 | 2026-01-06 | 2026-06-24
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005009/IF/22012035612601 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP147819290 | Closed | 23490 | 0 | 2026-02-07
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005009/IF/22012035613057 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP147766772 | Physically Completed | 23490 | 7308 | 2026-02-07 | 2026-06-24
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of State scheme House for Individuals / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005009/IF/22012035613060 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO.MP117917762 | Ongoing | 23490 | 0 | 2026-02-07
DHAR / NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/9993683753 — इंदिरा आवाश निर्माण कार्य सीमा दशरथ ग्राम सिलोदा बुजुर्ग | Completed | 14000 | 12897 | 2015-11-30 | 2017-01-08
DHAR / NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/9993683762 — इन्दिरा आवास निर्माण कार्य सुगन बाई रामचंद्र | Completed | 14000 | 12738 | 2015-11-30 | 2017-01-08
DHAR / NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/9993683766 — इन्दिरा आवास निर्माण कार्य कलाबाई रूपसिंह | Completed | 14000 | 12738 | 2015-11-30 | 2017-01-08
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Houses (State Scheme) / Construction of State scheme Houses Building for Individuals | Rural Housing | 1722005009/IF/9993683770 — मुख्यमंत्री आवास निर्माण कार्य कन्हेयालाल बाबु | Completed | 14000 | 13296 | 2017-01-02 | 2017-11-30
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3689813 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115186750 | Physically Completed | 18360 | 18844 | 2022-10-15 | 2024-11-27
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3689863 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115191921 | Completed | 18360 | 15708 | 2022-09-24 | 2022-12-31
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3689893 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115194175 | Completed | 18360 | 17374 | 2022-08-23 | 2023-07-04
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3718702 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117917019 | Completed | 18360 | 17374 | 2022-08-19 | 2023-07-04
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3727299 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121351663 | Completed | 18360 | 17136 | 2022-08-19 | 2022-11-22
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3747855 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118208411 | Completed | 18360 | 17748 | 2022-06-23 | 2022-11-12
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3767170 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118458919 | Completed | 18360 | 15657 | 2022-08-23 | 2023-07-04
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/3819720 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116664288 | Completed | 18360 | 17340 | 2022-06-14 | 2022-10-04
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4189861 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106073786 | Physically Completed | 18360 | 18071 | 2022-09-24 | 2024-11-21
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4190709 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115187912 | Completed | 18360 | 18156 | 2022-09-24 | 2022-12-31
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4190723 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115200015 | Completed | 18360 | 18156 | 2022-09-24 | 2022-12-31
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4191307 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116394252 | Completed | 18360 | 16728 | 2022-08-23 | 2022-11-22
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4192136 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118513601 | Completed | 18360 | 17136 | 2022-08-19 | 2022-11-22
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4196042 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124320240 | Completed | 18360 | 15300 | 2022-10-15 | 2024-01-11
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4557320 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115190255 | Completed | 21870 | 21627 | 2024-10-25 | 2025-04-01
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4570793 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116782718 | Completed | 21870 | 21627 | 2024-10-09 | 2025-04-01
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4574078 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117926342 | Physically Completed | 23490 | 9135 | 2026-01-27 | 2026-02-26
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4606015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124306599 | Completed | 21870 | 21627 | 2024-10-09 | 2025-04-01
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/4724532 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147847721 | Approved | 27000 | 0 | 2024-09-24
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5245476 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147758469 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5251820 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP143213859 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5253647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126104526 | Physically Completed | 23490 | 3915 | 2025-08-26 | 2026-03-29
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5253864 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP150715551 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5255523 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118208680 | Ongoing | 27000 | 4200 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5260606 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118211345 | Completed | 23490 | 20880 | 2025-04-11 | 2025-10-15
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5266024 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147712360 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5267804 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116680294 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5273094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119714449 | Physically Completed | 23490 | 9396 | 2026-01-06 | 2026-01-29
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5274885 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116672222 | Completed | 23490 | 23229 | 2025-04-28 | 2025-10-15
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5277500 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116664431 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5280232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP126105773 | Ongoing | 27000 | 7830 | 2025-08-26
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5280463 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119494032 | Ongoing | 27000 | 12789 | 2025-07-23
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5281094 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121350617 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5283343 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124322276 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5285504 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116781556 | Completed | 23490 | 23229 | 2025-05-05 | 2025-10-15
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5287233 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117917510 | Ongoing | 27000 | 17226 | 2025-09-24
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5288684 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116378787 | Ongoing | 27000 | 10962 | 2025-05-19
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5289237 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP121351154 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5289747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147995478 | Physically Completed | 23490 | 16704 | 2026-01-06 | 2026-05-17
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5290814 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115191901 | Ongoing | 27000 | 11484 | 2025-04-11
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5292253 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124316667 | Completed | 23490 | 20619 | 2025-04-28 | 2025-10-15
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5295883 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116763684 | Ongoing | 27000 | 11508 | 2025-06-24
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5303683 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP124320939 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5308115 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151361732 | Ongoing | 27000 | 7308 | 2025-06-25
DHAR / NALCHHA | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5311232 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147729022 | Physically Completed | 27000 | 8400 | 2025-02-18 | 2026-09-04
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5314791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116672263 | Ongoing | 27000 | 10701 | 2025-06-24
DHAR / NALCHHA | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5323158 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119494050 | Approved | 27000 | 0 | 2025-02-18
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5326806 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116773511 | Completed | 23490 | 8091 | 2025-05-19 | 2026-07-25
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5328599 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119882987 | Ongoing | 27000 | 0 | 2025-07-23
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5335216 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116672102 | Completed | 23490 | 20097 | 2025-04-28 | 2025-10-15
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5337113 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP151028274 | Completed | 23490 | 21663 | 2025-05-05 | 2025-10-15
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5340418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147719320 | Ongoing | 27000 | 10725 | 2026-01-06
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5341758 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP147517705 | Completed | 23490 | 23490 | 2025-04-11 | 2025-10-15
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5342382 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116664520 | Ongoing | 27000 | 0 | 2025-07-23
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/5574265 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP119886206 | Ongoing | 27000 | 0 | 2025-06-09
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/558397 — Construction of IAY House -IAY REG. NO. MP3604242 | Completed | 15030 | 15480 | 2017-03-01 | 2017-12-01
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/644896 — Construction of IAY House -IAY REG. NO. MP1360290 | Completed | 15030 | 15136 | 2017-02-26 | 2017-11-30
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/646601 — Construction of IAY House -IAY REG. NO. MP1700942 | Completed | 15030 | 14620 | 2017-02-26 | 2017-12-27
DHAR / NALCHHA | 2016-2017 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/651713 — Construction of IAY House -IAY REG. NO. MP3856179 | Completed | 15030 | 14792 | 2017-02-26 | 2017-08-20
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/731639 — Construction of IAY House -IAY REG. NO. MP2011271 | Completed | 15030 | 860 | 2017-06-01 | 2018-08-15
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/731703 — Construction of IAY House -IAY REG. NO. MP2013051 | Completed | 15030 | 16168 | 2017-06-01 | 2017-12-27
DHAR / NALCHHA | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005009/IF/IAY/754599 — Construction of IAY House -IAY REG. NO. MP2712847 | Completed | 15030 | 14276 | 2017-06-01 | 2018-01-13
DHAR / NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005009/LD/22012034228620 — व़क्षारोपण कार्य शांतिवन के आसपास ग्राम पंचायत बछडावदा | Completed | 52000 | 19175 | 2015-09-11 | 2018-07-08
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Fallow Land for Community / Development of Fallow Land for Community | Land Development | 1722005009/LD/22012034569124 — khel medan nirman middle school bachdawada | Closed | 218006.41 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1722005009/LD/22012034569125 — khel medan nirman middle school bachdawada | Closed | 0 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Construction of Earthen graded Bund for Community / Construction of Earthen graded Bund for Community | Construction of Bund | 1722005009/LD/22012034569126 — khel medan nirman middle school bachdawada | Closed | 0 | 0 | 2021-04-01
DHAR / NALCHHA | 2024-2025 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005009/LD/22012034944192 — Nali nirman kary main road se popsing sirsodiya ke ghar ki aur bachhadawada | Ongoing | 61000 | 7533 | 2025-02-05
DHAR / NALCHHA | 2024-2025 | D--RURAL INFRASTUCTURE / Land Development | Drainage of Waterlogged Land for Community / Drainage of Community Waterlogged Land | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005009/LD/22012034944244 — Nali Nirman Kary Main Road se Nandram Ke Ghar Ki Or | Approved | 39000 | 0 | 2024-06-16
DHAR / NALCHHA | 2011-2012 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Land Development | Development of Waste Land / Levelling/shaping of Wasteland Land for Community | Land Development | 1722005009/LD/911 — ग्रामीण क्रिडांगन बछडावदा ग्राम पंचायत बछडावदा | Completed | 0 | 463384 | 2012-01-17 | 2012-04-24
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/02008 — ग्रेवल मार्ग बछडावदा से सर्फराज ग्राम पंचायत बछडावदा | Completed | 0 | 209600 | 2006-05-10 | 2007-06-14
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/1001 — ग्रेवल मार्ग निमार्ण बछडावदा से निजामपुरा बछडावदा | Completed | 0 | 219360 | 2007-01-13 | 2007-06-14
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/15006 — GREVAL MARG SARFRAJ MARG SE SILODA BUGURG MARG KE MADHY | Completed | 500000 | 360882 | 2007-01-13 | 2010-10-18
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034158371 — मुरम मार्ग निर्माण कार्य घाटाबिलोद मार्ग से नारायणपुरा ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034158375 — khet sadak graval road निर्माण ईजीएस शाला से घाटाब | Completed | 1081000 | 10804 | 2014-03-08 | 2015-07-20
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034158376 — मुरम माग घाटा बिल्‍लोद मार्ग से बिड मार्ग तक | Deleted | 0 | 0 | 2012-12-24
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034158396 — मुरम मार्ग निर्माण कार्य बछडावदा से सर्फराज मार्ग भाग 3 ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034158397 — ग्रेवल मार्ग निर्माण कार्य सिलोदा बुजुर्ग मार्ग से प्रहलाद सेठ के खेत तक ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/22012034158402 — पंच परमेश्‍वर सी सी मार्ग ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/22012034158403 — पंच परमेश्‍वर सी सी मार्ग सिलोदा ग्राम पंचायत बछडा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034158404 — ग्रेवल मार्ग निर्माण सिलोदा गाव से पुलिया तक ग्राम बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034158405 — ग्रेवल मार्ग निर्माण कार्य सिलोदा मार्ग से जमनालाल पाटीदार वाला मार्ग ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/22012034164704 — विधायक निधि सीसी रोड सिलोदाबुजुर्ग बछडावदा | Completed | 179000 | 174850 | 2013-05-05 | 2014-04-15
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/22012034182421 — पंच परमेश्‍वर सी सी रोड टेलर के घर से chamar wali | Completed | 206000 | 80592 | 2013-09-18 | 2015-07-20
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/22012034188498 — पंच परमेश्‍वर सी सी रोड टेलर के घर से राम मंदिर तक | Completed | 229000 | 158034 | 2013-09-29 | 2015-07-20
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/22012034191325 — पंच परमेश्‍वर सीसी रोड टेलर के घर से चमार पाला पुल | Completed | 206000 | 5017 | 2013-05-15 | 2015-07-20
DHAR / NALCHHA | 2013-2014 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034211986 — KHET SADAK GRAVAL MARGE BHARAT RAMCHANDRA KE KHET | Completed | 895000 | 779605.43 | 2014-03-08 | 2018-08-13
DHAR / NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034369735 — khet sadak nirman bhicholi se baksana | Closed | 0 | 0 | 2017-10-02
DHAR / NALCHHA | 2017-2018 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034369736 — khet sadak nirman bhicholi se bacadavda | Closed | 0 | 0 | 2017-10-02
DHAR / NALCHHA | 2018-2019 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034370255 — Gravel Road Siloda se Biloda | Closed | 0 | 0 | 2018-04-14
DHAR / NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of WBM Roads for Community / Construction of WBM Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034437545 — hanuman mandir se tejaji ke mandir tak | Closed | 0 | 0 | 2019-04-04
DHAR / NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034511895 — Bachhadawda sudur sadak badpura se nijampura tak | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1722005009/RC/22012034511898 — khet sadak ghanshyam chuodhari ke khet se prakash patel ke khet tak | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1722005009/RC/22012034511901 — khet sadak sohan thakur ke khet se amrasingh ji ke khet tak | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | D--RURAL INFRASTUCTURE / Rural Connectivity | Repair & maint of Gravel Road Roads for Comm / Repair and maintenance of Gravel Road Roads for Community | Repair & maint of Road | 1722005009/RC/22012034511905 — sudur shadak shonan ke ghar se smrshig ke ghar thak | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034542615 — Construction of Khet Sadak Yogendra Patel ke Khet se Prakash Patel ke khet tak Village Bachhadawada | Completed | 1498870.35 | 1475335.84 | 2020-09-30 | 2021-12-07
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034554076 — pipe puliya nirman panchayat bhavan ke samne bachdavda | Closed | 0 | 0 | 2020-11-14
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034554077 — pipe puliya nirman madhyamik school ke samne bachdavda | Closed | 0 | 0 | 2020-11-24
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034554078 — pipe puliya nirman puniya ke ghar ke pas bachdavda | Closed | 0 | 0 | 2020-11-24
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Construction of Gravel Road Roads for Community / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/22012034560197 — Sudur Gram Sampark Sadak Gravel Marg Shamshan se Bhicholi Marg Tak | Completed | 1499451.69 | 1416449.2 | 2021-02-21 | 2022-07-20
DHAR / NALCHHA | 2025-2026 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/22012034851479 — CC ROAD KAMAL KAPALIYA KE GHAR SE HARIRAM KE GHAR KI OR BACHHADAWADA | Approved | 31000 | 0 | 2025-08-16
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50073 — ग्रेवल मार्ग बछडावदा से दीग्‍ठान भाग 2 बछडावदा | Completed | 0 | 202100 | 2008-01-25 | 2009-01-09
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50074 — ग्रेवल मार्ग मुरमीकरण कार्य बछडावदा से नारायणपुरा बछडावदा | Completed | 0 | 48000 | 2008-01-01 | 2009-01-09
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50075 — ग्रेवल मार्ग बछडावदा से ‍भीचौली भाग 2 बछडावदा | Completed | 0 | 209990 | 2008-01-25 | 2009-12-26
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50078 — पाईप पुलिया निर्माण बछडावदा से भिचौली मार्ग पर | Completed | 0 | 105750 | 2007-07-03 | 2009-12-06
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50115 — हयुम पाइप कलवड कु2मार कराि‍इडया से बछडावदा मार्ग 3 नग फलस काजवें 5 नग | Completed | 0 | 2027709.6 | 2007-05-26 | 2012-07-11
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50124 — ग्रेवल मार्ग बछडावदा से चम्‍बलबरोदा | Completed | 0 | 53000 | 2008-01-03 | 2009-04-08
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50127 — पाईप पुलि‍या क्रमांक 02 बछडावदा | Completed | 0 | 76000 | 2007-04-27 | 2009-12-06
DHAR / NALCHHA | 2007-2008 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50128 — पाईप पुलि‍या क्रमांक 01 सि‍लोदाबुजूर्ग मार्ग पर बछडावदा | Completed | 0 | 0 | 2007-04-12 | 2009-12-06
DHAR / NALCHHA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50205 — ग्रेवल मार्ग बछडावदा से भीचोली भाग 2 ग्राम पंचा बछडावदा लागत 5 लाख | Completed | 0 | 0 | 2009-01-25 | 2014-08-06
DHAR / NALCHHA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50364 — Grewal Marg Nirman Sarfaraj Road Se Chambalbaroda Road Ke Bich Bachadawada | Completed | 0 | 214590 | 2009-03-01 | 2012-07-11
DHAR / NALCHHA | 2008-2009 | D--RURAL INFRASTUCTURE / Rural Connectivity | Gravel Road / Construction of Gravel Road Roads for Community | Construction of Road and Culvert | 1722005009/RC/50395 — Gravel Marg Sarfraj Marg to Chambalbaroda Marg Bachdawada | Deleted | 500000 | 0 | 2009-02-01
DHAR / NALCHHA | 2009-2010 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50446 — Gravel Marg Nijampura Marg to kakriya Khal tak Bachadawada | Completed | 500000 | 316906 | 2009-06-08 | 2012-04-05
DHAR / NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50554 — ग्रेवल मार्ग निर्माण सिलोदा बुजुर्ग से दिग्‍ठान भाग 01 ग्राम पंचायत बछडावदा | Completed | 0 | 0 | 2010-11-01 | 2012-04-02
DHAR / NALCHHA | 2010-2011 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50563 — मुरम रोड सिलोदाबुजुर्ग से दिग्‍ठान भाग 2 ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2010-11-01
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50646 — मुरम मार्ग निर्माण कार्य चम्‍बलबरोदा मार्ग से उसखाना तक ग्राम बछडावदा ग्राम पंचायत बछडावदा | Completed | 0 | 636228 | 2011-05-03 | 2012-07-11
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50647 — मुरम मार्ग निर्माण कार्य सिलोदाबुजुर्ग से दिग्‍ठान मार्ग भाग 03 ग्राम बछडावदा ग्राम पंचायत बछडावदा | Completed | 0 | 340576 | 2011-06-09 | 2012-07-11
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50675 — मुरम मार्ग निर्माण कार्य निजामपुरा मार्ग से चंबलबरोदा तक ग्राम पंचायत बछडावदा | Completed | 498000 | 282796 | 2011-06-10 | 2012-08-15
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50702 — मुरम मार्ग निर्माण सिलोदा बुजुर्ग से दिग्‍ठान भाग 04 ग्राम पंचायत बछडावदा | Completed | 0 | 473506 | 2011-09-16 | 2011-10-08
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50703 — मुरम मार्ग निर्माण दिगठान मार्ग से क़ष्‍ण मंदिर खेत भाग 02 ग्राम पंचायत बछडावदा | Completed | 0 | 480196 | 2011-10-28 | 2012-05-10
DHAR / NALCHHA | 2011-2012 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50704 — मुरम मार्ग निर्माण कार्य दिगठान से क़ष्‍ण मंदिर खेत भाग 01 ग्राम पंचायत बछडावदा | Completed | 0 | 473404 | 2011-10-07 | 2012-05-10
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50791 — ग्रेवल मार्ग निर्माण रामेश्‍वर के मकान से सिलोदा मार्ग ग्राम पंचायत बछडावदा | Completed | 0 | 284856 | 2012-04-01 | 2013-05-30
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50792 — मुरम मार्ग भेरू राठौड के खेत से कन्‍हैयालाल के खेत तक ग्राम पंचायत बछडावदा | Completed | 0 | 239976 | 2012-04-01 | 2012-05-28
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/50826 — सिमेंट कांक्रीट खरंजा पंचपरमेश्‍वर रामेश्‍वर के घर से सिलोदा मार्ग ग्राम पंचायत बछडावदा | Completed | 247000 | 44000 | 2012-04-30 | 2012-03-31
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/50837 — मुरम मार्ग निर्माण कार्य बछडावदा से चंबलबरोदा मार्ग भाग 02 ग्राम पंचायत बछडावदा | Completed | 497000 | 371712 | 2012-04-01 | 2012-06-28
DHAR / NALCHHA | 2012-2013 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/50863 — pachparmever jitendre maharaj ke ghar se jagdish mangilal ke khet tak gram pachayat bachdavada | Completed | 110000 | 109208 | 2012-04-03 | 2012-05-25
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/6006 — ग्रेवल मार्ग सिलोदाबुजर्ग से बछडावदा | Completed | 200000 | 368400 | 2006-04-19 | 2007-03-31
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/6007 — ग्रेवल मार्ग बधरावदा से भिचोली | Completed | 0 | 390390 | 2006-05-24 | 2007-04-15
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Earthern road / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/6008 — ग्रेवल मार्ग निर्माण बछडावदा से दिग्‍ठान, बछडावदा | Completed | 195000 | 97860 | 2007-01-13 | 2007-06-14
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Sand Moram / Construction of Mitti Murram Roads for Community | Construction of Road and Culvert | 1722005009/RC/823 — Hume pipe celvent to Bachhdawda Siloda road | Completed | 2921000 | 1795078 | 2006-12-28 | 2012-05-10
DHAR / NALCHHA | 2006-2007 | D--RURAL INFRASTUCTURE / Rural Connectivity | Cement Concrete / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722005009/RC/824 — ग्रेवल मार्ग बछडावदा से सिलोदा | Completed | 3393000 | 259721.8 | 2006-12-11 | 2012-04-02
DHAR / NALCHHA | 2015-2016 | D--RURAL INFRASTUCTURE / Rural Sanitation | Individual Household Latrines / Construction of Single Unit Toilets for Individual | Construction of Toilets | 1722005009/RS/22012034287083 — vyaktigat shochalay ka niman group 01 bachadawada | Completed | 24000 | 19997 | 2015-10-13 | 2017-08-20
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005009/RS/22012034579196 — SBM COMPOST PIT BACHHADAWADA | Closed | 19262.58 | 0 | 2021-04-01
DHAR / NALCHHA | 2021-2022 | D--RURAL INFRASTUCTURE / Rural Sanitation | Constr of Vermi Compost structure for Community / Construction of Vermi Compost structure for Community | Construction of NADEP/Vermi Compost Pit | 1722005009/RS/22012034579202 — SBM COMPOST PIT SILODA BUZURG | Closed | 19262.58 | 0 | 2021-04-01
DHAR / NALCHHA | 2006-2007 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/100 — खेत तालाब ग्‍यारसीबाई सीताराम बछडावदा | Completed | 0 | 0 | 2006-05-25 | 2007-04-15
DHAR / NALCHHA | 2016-2017 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Earthen Dam / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034317816 — sankan pond nirman | Closed | 0 | 0 | 2016-10-02
DHAR / NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034447037 — bhu sankan pond rameshwar ke khet ke paas | Completed | 320000 | 262214.54 | 2019-03-10 | 2021-06-30
DHAR / NALCHHA | 2018-2019 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005009/WC/22012034447088 — bhu sankand pond shamsan ghat ke pass | Completed | 509000 | 464778.98 | 2019-03-15 | 2021-06-30
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722005009/WC/22012034516068 — shankan pond gordhan ke khet ke pass | Completed | 455496.37 | 361756 | 2020-03-14 | 2021-05-18
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1722005009/WC/22012034518699 — boldar chek dem gambhir ramkishan | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1722005009/WC/22012034518700 — boldar chek dem radhesyam nandram | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Wasteland Block Plantation-Forstry-Community / Wasteland Block Plantation of Forestry Trees for Community | Plantation | 1722005009/WC/22012034518701 — boldar chek dem bhihari prahlad | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005009/WC/22012034518702 — boldar chek dem rameshwar badreelal | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005009/WC/22012034518703 — boldar chek dem dilip govind | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005009/WC/22012034518704 — boldar chek dem amar singh kesar singh | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Water Absorption Trench Trench for Comm / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005009/WC/22012034518705 — boldar chek dem vandana govind | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034518706 — boldar chek dem sanjay jagdish | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034518707 — boldar chek dem gajannd ramkishan | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034518708 — boldar chek dem laxman singh chhogalal | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034518709 — boldar chek dem dilip ramlal | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Boulder Anicut Check Dam for Community / Construction of Boulder Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034518710 — boldar chek dem manohar gorelal | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Brushwood Check Dam for Community / Construction of Brushwood Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012034518711 — boldar chek dem ramlal chhogalal | Closed | 0 | 0 | 2019-11-23
DHAR / NALCHHA | 2020-2021 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Construction of Earthen Spur for Community / Construction of Earthen Spur for Community | Construction of Spur | 1722005009/WC/22012034555257 — Nalha Trenching Panchayat to Shantidham Bachhadawada | Completed | 232700.78 | 204820 | 2020-09-12 | 2021-05-10
DHAR / NALCHHA | 2019-2020 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Mini Percolation Tank for Community | Construction of Percolation Tank | 1722005009/WC/22012034583314 — nala treching school ke samne bachhadawda | Closed | 103931.58 | 0 | 2020-01-26
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722005009/WC/22012034637313 — CTRA roof water harvesting rajev gandhi seva kendra par | Completed | 47908.22 | 21548 | 2021-05-04 | 2021-05-18
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1722005009/WC/22012034642082 — CTRA form pond community kamal patel ke khet ke paas | Completed | 231245.49 | 120152 | 2021-05-03 | 2023-12-05
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1722005009/WC/22012034642090 — CTRA form pond community bansidhar kapasiya ke khet ke pass | Completed | 231245.49 | 227049.97 | 2021-04-16 | 2021-10-20
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1722005009/WC/22012034642097 — nalla tranching ghanshyam ke khet ke pass | Closed | 0 | 0 | 2021-04-04
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1722005009/WC/22012034642102 — nalla tranching kamal patel ke khet ke paas | Closed | 0 | 0 | 2021-04-04
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1722005009/WC/22012034642113 — nalla tranching kamal tailor ke khet ke pass | Closed | 0 | 0 | 2021-04-04
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Water Conservation and Water Harvesting | Construction of Fisheries Ponds for Community / Construction of Fisheries Ponds for Community | Construction of Tank | 1722005009/WC/22012034642117 — nalla tranching shamshchamar paal tak an ghat se | Closed | 0 | 0 | 2021-04-04
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722005009/WC/22012034642133 — CTRA roof water harvesting jila sahkari godon bachdawada | Closed | 24301.95 | 0 | 2021-04-04
DHAR / NALCHHA | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Recharge Pits for Community / Construction of Recharge Pits for Community | Construction of Recharge Pits | 1722005009/WC/22012034642136 — CTRA roof water harvesting jila sahkari godon bachdawada | Completed | 27184.96 | 25206 | 2021-05-04 | 2021-05-18
DHAR / NALCHHA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005009/WC/22012035109721 — नाला ट्रेचिंग कार्य खार नाला घनश्याम के खेत के पास | Deleted | 0 | 0 | 2023-08-16
DHAR / NALCHHA | 2023-2024 | D--RURAL INFRASTUCTURE / Water Conservation and Water Harvesting | Constr of Flood/ Diversion Channel for Community / Construction of Flood/ Diversion Channel for Community | Construction of Water Drain/Diversion Channel/Drainage/Field Channel | 1722005009/WC/22012035109722 — नाला ट्रेचिंग कार्य खार नाला घनश्याम के खेत के पास | Completed | 102664.01 | 62466 | 2023-09-24 | 2024-06-24
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/22012035163755 — NISTAR TALAB | Deleted | 0 | 0 | 2024-04-01
DHAR / NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005009/WC/22012035272571 — JGSA BORWEL RECHARGE STRUCTRE TALAB PAL BACHHADAWADA | Closed | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005009/WC/22012035272613 — JGSA BORWEL RECHARGE STRUCTRE BHICHOLI ROAD BACHHADAWADA | Closed | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005009/WC/22012035272651 — JGSA BORWEL RECHARGE STRUCTRE PANCHYAT PARISAR BACHHADAWADA | Closed | 0 | 0 | 2025-04-14
DHAR / NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005009/WC/22012035285721 — JGSA BORWEL RECHARGE STRUCTRE BHICHOLI ROAD BACHHADAWADA | Physically Completed | 33877.2 | 25421.5 | 2025-05-08 | 2026-06-27
DHAR / NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005009/WC/22012035285730 — JGSA BORWEL RECHARGE STRUCTRE TALAB PAL BACHHADAWADA | Physically Completed | 33877.2 | 25421.5 | 2025-05-08 | 2026-04-15
DHAR / NALCHHA | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Sand filter-Borewell recharge for Comm / Construction of Sand filter for borewell recharge for Community | Well Recharge | 1722005009/WC/22012035285741 — JGSA BORWEL RECHARGE STRUCTRE PANCHYAT PARISAR BACHHADAWADA | Physically Completed | 33877.2 | 25421.5 | 2025-05-08 | 2026-04-15
DHAR / NALCHHA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/80541 — नि‍स्‍तार तालाब बछडावदा उन्‍नयन कार्य WRD | Completed | 0 | 3414949.08 | 2009-06-17 | 2012-03-26
DHAR / NALCHHA | 2009-2010 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005009/WC/80883 — STOP DEM KAKRIYA KHAL BACHDAVDA | Deleted | 500000 | 39200 | 2009-06-30
DHAR / NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Water Absorption Trench / Construction of Water Absorption Trench for Community | Construction of Trench | 1722005009/WC/9993628167 — तालाब गहरीकरण सिलोदाबुजुर्ग ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2012-2013 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Check Dam / Construction of Masonry/CC Check Dam for Community | Construction of Check Dam/Stop Dam | 1722005009/WC/9993628168 — स्‍टाप डेम निर्माण कार्य ग्राम पंचायत बछडावदा | Deleted | 0 | 0 | 2012-12-25
DHAR / NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boulder Check / Construction of Boulder Check Dam for Community | Boulder Check/Gully Plug | 1722005009/WC/9993667443 — बोल्‍डर चैक डेम बछडावदा | Deleted | 0 | 0 | 2016-01-26
DHAR / NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Boulder Check / Construction of Boulder Check Dam for Community | Boulder Check/Gully Plug | 1722005009/WC/9993667444 — बोल्‍डर चैक डेम निर्माण नाले पर बछडावदा | Deleted | 0 | 0 | 2016-01-26
DHAR / NALCHHA | 2015-2016 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Sunken Pond / Construction of Community Water Harvesting Ponds | Farm Pond | 1722005009/WC/9993667445 — संकन पौण्‍ड श्‍मशान घाट के पास बछाडवदा | Deleted | 0 | 0 | 2016-01-26
DHAR / NALCHHA | 2017-2018 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Renovation of traditional water bodies | Renovtion of Community Ponds for Comm / Renovation of Community Water Harvesting Ponds for Community | Repair & maint of Pond/ Tank | 1722005009/WH/19961754 — Nistar Talab Jjirnodhar Bachhadawada | Completed | 594000 | 241408 | 2017-05-26 | 2019-06-01
DHAR / NALCHHA | 2018-2019 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034445902 — horticulture plantation madan ramsingh silodabujurg | Physically Completed | 172520 | 50048 | 2018-12-18 | 2021-01-18
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034836695 — Horticulture plantation inder aganath silodabujurg | Physically Completed | 180000 | 59508.79 | 2021-10-07 | 2026-06-02
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034836697 — Horticulture plantation kanhaiyalal babulal silodabujurg | Physically Completed | 180000 | 77753.79 | 2021-10-07 | 2026-06-02
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034896669 — rama babulal Horticulture palntensn | Closed | 0 | 0 | 2021-07-12
DHAR / NALCHHA | 2021-2022 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034903917 — Vasharopn kary horticulchar vibhag rama babulal siloda buzurg | Closed | 179000 | 0 | 2021-07-12
DHAR / NALCHHA | 2023-2024 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Block Plantation-Hort-Trees in fields-Individuals / Block Plantation of Horticulture Trees in fields for Individuals | Plantation | 1722005/IF/22012034905309 — Vasharopn kary horticulchar vibhag shugni bai ramchandr siloda buzurg | Completed | 214000 | 35114 | 2023-09-14 | 2025-02-21
DHAR / NALCHHA | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Line Plntation of Shelter Belt for Individual / Line Plantation of Shelter Belt Trees for Individuals | Plantation | 1722005/IF/22012035058502 — Horticulture plantantion sugnabai ramchhandar | Closed | 335000 | 0 | 2022-08-14