## Work List
Exported on: 2026-09-07 06:47:41
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Kathodiya
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005024/DP/22012034628417 — Plantation work at shamshan ghat Kathdiya part 2 | New | 0 | 0 | 2024-10-02
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation of Forestry-in Fields-Community / Block Plantation of Forestry Trees in Fields for Community | Plantation | 1722005024/DP/22012034628418 — Plantation work at shamshan ghat Kathdiya part 2 | Ongoing | 476430.48 | 0 | 2024-10-28
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1722005024/IC/22012034885512 — वृक्षारोपण कार्य श्मशान घाट पर भाग 2 | New | 0 | 0 | 2024-08-15
DHAR / NALCHHA | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Micro Irrigation Works | Construction of water courses Canal for Community / Construction of water courses for Community | Construction of Canal | 1722005024/IC/22012034885970 — खेत तालाब प्रेम नारायण के खेत पर कठोडिया | New | 0 | 0 | 2024-10-02
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1722005024/IF/22012035359985 — khet Talab nirman karya at Santosh ke khet par GP Kathodiya | Ongoing | 299205.55 | 20700 | 2025-04-23
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Levelling/shaping of Fallow land for Individuals / Levelling/shaping of Wasteland / Fallow land for Individuals | Land Development | 1722005024/IF/22012035360003 — khet Talab nirman karya at Girdhari ke khet par GP Kathodiya | Ongoing | 299205.55 | 0 | 2025-05-17
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5415634 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120417724 | Physically Completed | 23490 | 0 | 2025-04-29 | 2026-08-04
DHAR / NALCHHA | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/5416063 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP120252207 | Physically Completed | 23490 | 0 | 2025-06-03 | 2026-08-04
DHAR / NALCHHA | 2015-2016 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | IAY Houses / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722005024/IF/IAY/97109 — Construction of IAY House -IAY REG. NO. MP-22-005-024-001/16 | Approved | 27000 | 0 | 2015-10-16