## Work List
Exported on: 2026-10-11 23:08:22
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Khedi Balvari
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006029/IC/22012034888529 — Sarvajanik kup bondariyapura jhiran khedibalwari | New | 0 | 0 | 2025-01-26
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Micro Irrigation Works | Construction of Irrigation Open Well for Community / Construction of Irrigation Well for Community | Construction of Well | 1722006029/IC/22012034888530 — Sarvajanik kup patelpura jhiran khedibalwari | New | 0 | 0 | 2025-01-26
DHAR / GANDHWANI | 2017-2018 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006029/IF/22012034337054 — कपिलधारा कुप नहारसिंह जामसिंह | Physically Completed | 200000 | 0 | 2017-05-09 | 2026-08-11
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006029/IF/22012035444067 — JGSA 2025 Khet Talab Nirman nura jamsingh khedi balwari | Physically Completed | 147621.16 | 0 | 2025-05-16 | 2026-07-06
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006029/IF/22012035444088 — JGSA 2025 Khet Talab Nirman surban jamsingh khedi balwari | Physically Completed | 147621.16 | 0 | 2025-05-16 | 2026-07-06
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006029/IF/22012035444101 — JGSA 2025 Khet Talab Nirman sundriya madan khedibalwari | Ongoing | 147621.16 | 0 | 2025-05-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006029/IF/22012035444118 — JGSA 2025 Khet Talab Nirman mohansingh jamsingh khedibalwari | Ongoing | 147621.16 | 0 | 2025-05-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006029/IF/22012035444126 — JGSA 2025 Khet Talab Nirman bisan thansingh khedibalwari | Ongoing | 147621.16 | 0 | 2025-05-16
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006029/IF/22012035444199 — JGSA 2025 Khet Talab Nirman mahesh nasru khedibalwari | Physically Completed | 147621.16 | 0 | 2025-05-16 | 2026-07-06
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Pond for Individual | Farm Pond | 1722006029/IF/22012035444259 — JGSA 2025 Khet Talab Nirman shiv kanya bhuresingh khedi balwari | Ongoing | 147621.16 | 0 | 2025-06-06
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035444278 — JGSA 2025 Recharge Structure Kapildhara Kup inbhan jamsingh khedibalwari | Physically Completed | 25899.46 | 0 | 2025-05-07 | 2026-07-13
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035444289 — JGSA 2025 Recharge Structure Kapildhara Kup sarju bai bonddar khedibalwai | Physically Completed | 25899.46 | 0 | 2025-05-07 | 2026-07-13
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035444305 — JGSA 2025 Recharge Structure Kapildhara Kup bhangda rupsingh khedibalwari | Physically Completed | 25899.46 | 0 | 2025-05-07 | 2026-07-13
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035444330 — JGSA 2025 Recharge Structure Kapildhara Kup kishor thansingh khedibalwari | Physically Completed | 25899.46 | 0 | 2025-05-07 | 2026-07-13
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035444350 — JGSA 2025 Recharge Structure Kapildhara Kup richhu sumiya khedibalwari | Ongoing | 25899.46 | 0 | 2025-05-07
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035479719 — JGSA 2025 Recharge Structure Kapildhara Kup Naharsingh Jamsingh Khedi Balwari | Approved | 25899.46 | 0 | 2025-05-01
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035479742 — JGSA 2025 Recharge Structure Kapildhara Kup Indersingh Sheru Khedi Balwari | Physically Completed | 25899.46 | 0 | 2025-05-28 | 2026-07-13
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035479765 — JGSA 2025 Recharge Structure Kapildhara Kup Bhuwansingh Versingh Khedi Balwari | Ongoing | 25899.46 | 0 | 2025-05-28
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035479799 — JGSA 2025 Recharge Structure Kapildhara Kup Chagan Magiya Khedi Balwari | Approved | 25899.46 | 0 | 2025-05-01
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand-Filled Groundwater Recharge in Dug Well for Individual | Well Recharge | 1722006029/IF/22012035479835 — JGSA 2025 Recharge Structure Kapildhara Kup Nurla Vesta Khedi Balwari | Physically Completed | 25899.46 | 0 | 2025-05-28 | 2026-07-13
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Well for Individual | Construction of Well | 1722006029/IF/22012035652699 — Kapildhara Kup Bhuru Richa Rojabayda Khedibalwari | New | 0 | 0 | 2025-04-16
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4535419 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102419555 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4549260 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106552854 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4549753 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106749285 | Completed | 23490 | 0 | 2025-01-29 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4562997 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115023306 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4576707 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117764989 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4579227 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118655567 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4671207 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106867827 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4673447 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117765846 | Completed | 23490 | 0 | 2024-12-17 | 2026-08-11
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4673841 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118041980 | Completed | 23490 | 0 | 2025-01-29 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4690069 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113844000 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4692398 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115023138 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4701639 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118395540 | Completed | 23490 | 0 | 2025-01-15 | 2026-07-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4735187 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP102433958 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-25
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4755364 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118041712 | Completed | 23490 | 2100 | 2025-01-29 | 2026-10-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4755365 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118042283 | Ongoing | 27000 | 2100 | 2025-08-18
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4755368 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118043633 | Completed | 23490 | 0 | 2024-12-17 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/4888966 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118392367 | Ongoing | 27000 | 2100 | 2025-04-07
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5357473 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113919668 | Completed | 23490 | 0 | 2025-05-03 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5357522 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106869437 | Ongoing | 27000 | 0 | 2025-08-05
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5357598 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118376656 | Approved | 27000 | 0 | 2025-03-07
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5359470 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113849061 | Ongoing | 27000 | 4200 | 2026-08-06
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5359537 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106615056 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5360791 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113846769 | Ongoing | 27000 | 17700 | 2025-09-26
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5361581 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115023271 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5361648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP115022986 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5361899 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114059128 | Completed | 23490 | 0 | 2025-05-03 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5365176 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP103544254 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5366807 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106553612 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-21
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5367816 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113462290 | Ongoing | 27000 | 18000 | 2026-06-06
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5368217 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106821252 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5369549 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113904637 | Ongoing | 27000 | 4200 | 2026-02-27
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5371444 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113907299 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5374828 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118395130 | Completed | 27000 | 9800 | 2025-08-05 | 2026-09-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5375262 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106551947 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-25
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5376219 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113898447 | Ongoing | 27000 | 15900 | 2026-08-03
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5382223 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113854681 | Ongoing | 27000 | 15600 | 2026-07-23
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5382552 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113905804 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5383075 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106848154 | Completed | 23490 | 0 | 2025-05-03 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5384245 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118390216 | Approved | 27000 | 0 | 2025-04-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5390491 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106613711 | Completed | 23490 | 0 | 2025-05-03 | 2026-07-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5391593 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106863994 | Ongoing | 27000 | 6300 | 2025-08-05
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5397747 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113906773 | Completed | 23490 | 0 | 2025-04-16 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5403746 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114059182 | Completed | 23490 | 0 | 2025-05-03 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5404948 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113863788 | Ongoing | 27000 | 16800 | 2025-10-29
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5407865 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113844685 | Completed | 27000 | 12600 | 2025-10-29 | 2026-10-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5410613 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106841565 | Completed | 23490 | 0 | 2025-05-03 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5410626 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106852719 | Completed | 23490 | 0 | 2025-05-03 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5581620 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106551673 | Ongoing | 27000 | 4200 | 2026-02-27
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5581699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118384247 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5581704 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118395949 | Ongoing | 27000 | 13800 | 2025-10-29
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5581810 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP113863881 | Completed | 23490 | 0 | 2025-10-29 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5582204 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106550899 | Completed | 23490 | 0 | 2025-06-30 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5582332 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106829232 | Ongoing | 27000 | 2800 | 2025-05-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5582335 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106786163 | Completed | 27000 | 2100 | 2025-06-30 | 2026-09-18
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5582647 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118394768 | Ongoing | 27000 | 21300 | 2025-10-29
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5596642 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118376859 | Completed | 27000 | 2100 | 2025-10-29 | 2026-09-18
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5596643 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118377620 | Completed | 23490 | 0 | 2025-08-18 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5596697 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106624380 | Ongoing | 27000 | 8400 | 2026-02-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5597201 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114762502 | Completed | 23490 | 2100 | 2026-03-25 | 2026-07-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5597761 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118439257 | Completed | 27000 | 6300 | 2025-10-29 | 2026-10-03
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5597762 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118439313 | Ongoing | 27000 | 2100 | 2025-09-26
DHAR / GANDHWANI | 2026-2027 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5598036 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP118377181 | Completed | 23490 | 2100 | 2026-05-12 | 2026-07-25
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5693418 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP106748367 | Approved | 27000 | 0 | 2025-06-04
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House for Individual | Rural Housing | 1722006029/IF/IAY/5696736 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114901421 | Ongoing | 27000 | 2100 | 2025-10-29
DHAR / GANDHWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722006029/RC/22012034823120 — C.C. Road Rozabayda Mujaldapura Khedibalwari | Approved | 0 | 0 | 2024-04-14
DHAR / GANDHWANI | 2024-2025 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Road for Community | Constr of Cement Concrete Roads | 1722006029/RC/22012034826256 — Construction of cement concrete Raod at Rojabaydha mujaldapura khedibalvari | Approved | 0 | 0 | 2024-04-14
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Mini Percolation Tank for Comm / Construction of Percolation Tank for Community | Construction of Percolation Tank | 1722006029/WC/22012035166650 — निस्तार तालाब निर्माण बड वाला नाला झरण खेडी बलवारी | New | 0 | 0 | 2024-04-12
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006029/WC/22012035248842 — Nistar tank pipar wala nala Rojabediya khedi balwari | Approved | 0 | 0 | 2025-01-26
DHAR / GANDHWANI | 2026-2027 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Water Harvesting Pond for Community | Construction of Tank | 1722006029/WC/22012035248843 — Nistar tank kundal wala nala Rojabediya khedi balwari | Ongoing | 1212062.04 | 0 | 2026-07-16
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006029/WC/22012035249362 — boulder wall nirman kary jhiran khedibalwari | Completed | 300094.39 | 0 | 2025-03-08 | 2026-08-11
DHAR / GANDHWANI | 2024-2025 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Masonry/CC Anicut for Community / Construction of Masonry Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006029/WC/22012035249363 — boulder wall nirman kary sindhi nala jhiran khedibalwari | Completed | 350548.68 | 0 | 2025-02-21 | 2026-08-11