## Work List
Exported on: 2026-09-15 11:00:38
Filters applied:
Data source: VBGRAMG
District: All
Block: All
Panchayat: Moripura
Status: Any
Financial year: All
New work type: All
District / Block / Panchayat | Financial year | Master category / Category | Work type / Work type (new module) | New work type | Work code / name | Status | Sanc. wage / material | Wage / material booked (since inception) | Work Started Date | Work Completed Date
DHAR / GANDHWANI | 2019-2020 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Community / Construction of Irrigation Open Well for Community | Construction of Well | 1722006038/DP/22012034445076 — सार्वजनीक कुप मसानीयापुरा | Ongoing | 445000 | 0 | 2019-04-30
DHAR / GANDHWANI | 2023-2024 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Drought Proofing | Block Plantation-Farm Forestry in fields for Comm / Block Plantation of Farm Forestry Trees in fields for Community | Plantation | 1722006038/DP/22012034588802 — Plantation Work Meri Mati Mera Desh M.S. Parisar Moripura | Ongoing | 55847.4 | 1500 | 2023-08-13
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Drought Proofing | Construction of Irrigation Open Well for Groups / Construction of Irrigation Open Well for Groups | Construction of Well | 1722006038/DP/22012034613762 — सार्वजनिक कूप निर्माण तालाब के पास मोरीपुरा | New | 0 | 0 | 2024-04-12
DHAR / GANDHWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722006038/IF/22012034593330 — पशु शेड निर्माण दिनेश भोल्‍या मोरीपुरा | Ongoing | 63531.21 | 0 | 2020-08-22
DHAR / GANDHWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722006038/IF/22012034593331 — पशु शेड निर्माण रमेश मिटटु मोरीपुरा | Ongoing | 63531.21 | 0 | 2020-08-22
DHAR / GANDHWANI | 2020-2021 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Goat Shelter for Individuals / Construction of Goat Shelter for Individuals | Goat Shelter | 1722006038/IF/22012034593332 — पशु शेड निर्माण नेपाल मगन मोरीपुरा | Ongoing | 63531.21 | 0 | 2020-08-22
DHAR / GANDHWANI | 2023-2024 | D--RURAL INFRASTUCTURE / Works on Individuals Land (Category IV) | Constr of Berkeley Compost Pit for Individual / Construction of Berkeley Compost Pit for Individual | Construction of NADEP/Vermi Compost Pit | 1722006038/IF/22012035219608 — कपिल धारा कूप निर्माण देवकीबाई मुनसिंह | New | 0 | 0 | 2024-01-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Cattle Shelter for Individuals / Construction of Cattle Shelter for Individuals | Cattle Shed | 1722006038/IF/22012035245248 — पशु शेड निर्माण राजु शंकर नरगांवापुरा मोरीपुरा | Approved | 0 | 0 | 2024-07-06
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006038/IF/22012035294429 — Kapil dhara vijay uchawal | New | 0 | 0 | 2024-10-02
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of Irrigation Open Well for Individuals / Construction of Irrigation Open Well for Individuals | Construction of Well | 1722006038/IF/22012035294434 — Kapil dhara kup nirman vijay uchawal | New | 0 | 0 | 2024-10-02
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Construction of Recharge Pits for Individuals / Construction of Recharge Pits for Individuals | Construction of Recharge Pits | 1722006038/IF/22012035390580 — JGSA 2025 recharge structure kapil dhara kup nirman rupsingh naharsingh moripura | New | 0 | 0 | 2025-04-17
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412209 — JGSA 2025 recharge structure kapil dhara pratam moripura | Ongoing | 25899.46 | 0 | 2025-05-01
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412353 — JGSA 2025 recharge structure kapil dhara juwansingh ditiya moripura | Physically Completed | 25899.46 | 0 | 2025-05-01 | 2026-08-07
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412381 — JGSA 2025 recharge structure kapil dhara kup rupsingh moripura | Physically Completed | 25899.46 | 0 | 2025-05-01 | 2026-08-21
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412423 — JGSA 2025 recharge structure kapil dhara kup gulab sekdiya moripura | Ongoing | 25899.46 | 0 | 2025-05-01
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412508 — JGSA 2025 recharge structure kapil dhara kup antersingh moripura | Ongoing | 25899.46 | 0 | 2025-05-01
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412614 — JGSA 2025 recharge structure kapil dhara kup vesta pratap moripura | Ongoing | 25899.46 | 0 | 2025-05-26
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412668 — JGSA 2025 recharge structure kapil dhara kup ansingh hussen moripura | Physically Completed | 25899.46 | 0 | 2025-05-01 | 2026-08-21
DHAR / GANDHWANI | 2025-2026 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Works on Individuals Land (Category IV) | Constr of Sand filter-openwell recharge for Indiv / Construction of Sand filter for Openwell recharge for Individual | Well Recharge | 1722006038/IF/22012035412703 — JGSA 2025 recharge structure kapil dhara kup jamsingh ratan moripura | Physically Completed | 25899.46 | 0 | 2025-05-01 | 2026-08-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Construction of Farm Ponds for Individuals / Construction of Farm Ponds for Individuals | Farm Pond | 1722006038/IF/22012035497859 — JGSA 2025 khet talab Nirman Karya Dinesh Hamarsingh Moripura | Approved | 147621.16 | 0 | 2025-04-15
DHAR / GANDHWANI | 2022-2023 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4040015 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114651745 | Completed | 23490 | 0 | 2022-07-06 | 2026-08-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4574713 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117713242 | Completed | 23490 | 0 | 2024-09-26 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4576515 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117717172 | Completed | 23490 | 0 | 2024-10-03 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4632111 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127715505 | Completed | 23490 | 0 | 2024-09-26 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4632138 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127725336 | Completed | 23490 | 0 | 2024-09-26 | 2026-08-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4632140 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127725771 | Completed | 23490 | 0 | 2024-09-26 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4636695 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130236431 | Completed | 23490 | 0 | 2024-09-26 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4636699 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130236908 | Completed | 23490 | 0 | 2024-12-23 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4663214 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149276871 | Completed | 23490 | 0 | 2024-09-26 | 2026-07-24
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4672379 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP116677945 | Completed | 23490 | 0 | 2024-12-06 | 2026-08-21
DHAR / GANDHWANI | 2024-2025 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/4696467 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117717637 | Completed | 23490 | 0 | 2024-10-16 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5246849 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149276245 | Physically Completed | 23490 | 0 | 2025-06-18 | 2026-08-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5247714 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149276313 | Completed | 23490 | 0 | 2025-06-18 | 2026-08-21
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5270092 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149276695 | Completed | 23490 | 0 | 2025-06-18 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5281254 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP114651340 | Completed | 23490 | 0 | 2025-06-18 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5292950 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117536356 | Ongoing | 27000 | 6300 | 2025-06-18
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5306727 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117716837 | Ongoing | 27000 | 2100 | 2025-06-18
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5316776 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128776554 | Completed | 23490 | 0 | 2025-07-28 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5317511 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130236398 | Completed | 23490 | 0 | 2025-06-18 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5328754 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP127717134 | Ongoing | 27000 | 0 | 2025-08-28
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5329022 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128776433 | Completed | 23490 | 0 | 2025-08-07 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5331263 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP128776639 | Ongoing | 27000 | 1566 | 2025-06-18
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5361622 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP149277158 | Completed | 23490 | 0 | 2025-06-18 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5608648 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117537264 | Completed | 23490 | 0 | 2025-07-28 | 2026-07-24
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5693735 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP130236384 | Ongoing | 27000 | 0 | 2025-08-28
DHAR / GANDHWANI | 2025-2026 | B--INDIVIDUAL ASSETS FOR VULNERABLESECTIONS (ONLY FOR HOUSEHOLDS IN PARAGRAPH 5) / Works on Individuals Land (Category IV) | Constr of PMAY-G House for Individuals / Construction of PMAY-G House Building for Individuals | Rural Housing | 1722006038/IF/IAY/5695837 — Construction of PMAY-G House for Individuals -PMAY-G REG. NO. MP117537010 | Physically Completed | 23490 | 1566 | 2025-08-18 | 2026-08-21
DHAR / GANDHWANI | 2020-2021 | D--RURAL INFRASTUCTURE / Rural Connectivity | Constr of Cement Concrete Roads for Comm / Construction of Cement Concrete Roads for Community | Constr of Cement Concrete Roads | 1722006038/RC/22012034555244 — Costruction Of Pipe Culvert Khariya wala Nale par Moripura | Ongoing | 200000 | 0 | 2021-02-21
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Constr of Earthen Check Dam for Community / Construction of Earthen Check Dam for Community | Construction of Check Dam/Stop Dam | 1722006038/WC/22012034444772 — RFR URI RIVER NISTAR TANK GOTHAN WALA NALA NO.02 | Ongoing | 642000 | 0 | 2021-11-13
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Community Water Harvesting Ponds / Construction of Community Water Harvesting Ponds | Construction of Tank | 1722006038/WC/22012034623753 — R.F.R URI RIVAR NALA TRECHING MASYANIYAPURA MORIPURA | Ongoing | 612999.58 | 0 | 2021-04-09
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1722006038/WC/22012034653670 — CTRA con of gully pluge nirman kariy satpudeeya moripura | Ongoing | 218813.34 | 0 | 2021-04-18
DHAR / GANDHWANI | 2021-2022 | A--PUBLIC WORKS RELATING TO NATURAL RESOURCES MANAGEMENT / Water Conservation and Water Harvesting | Construction of Earthen Gully Plugs for Community / Construction of Earthen Gully Plugs for Community | Boulder Check/Gully Plug | 1722006038/WC/22012034653740 — CTRA con of gully pluge nirman karya ukalapar moripura | Ongoing | 212613.39 | 0 | 2021-04-19